## About
Past-Due Order Analysis ¦ Manufacturer One (aerospace components)
All data in this workbook is synthetic. Item numbers, customers, orders, dates and dollar amounts are invented; only the shape of the problem is real.
Report Date | 2022-06-11
The story
The problem | More than $10M in past-due orders. The daily past-due list from the master planner had gone from daily, to weekly, to 'whenever'. The message from above: make more work orders and the past-due number will drop.
The question | On a Saturday overtime shift with an hour to spare: how much of this can Planning actually move?
Step 1 | Past Due Report tab: the raw ~2,000-line daily export. Most columns up front are noise. The last column, O/P, is the one that matters: O = Operations (on the floor or at a vendor), P = Planning.
Step 2 | Filtered on O/P. About 1,500 lines were O's. Moved the P's to their own sheet (Planning Work).
Step 3 | XLOOKUP each Item Number against the Do Not Make List (engineering holds; nothing gets built without approval). ~300 more lines out.
Step 4 | ~200 lines left. Conditional formatting to flag items with multiple orders, so work orders could be combined.
Step 5 | Worked the list: flagged lines already tied to a work order, created work orders (short-shipping where it moved the number), found credit holds, and logged component shortages with the $ they were holding up.
Result | See the Dashboard tab: ~$72k tied to work orders (existing or created that day), ~$36k on credit hold, and hard dollar figures for component shortages. Most of the past-due $ was never Planning's to fix.
Added now | Days Past Due, Aging Bucket and Status columns, plus the aging-bucket chart: what I'd add if the report landed on my desk today.
How to read it
Navy header | Columns from the original ERP past-due export
Blue header | Columns I added that Saturday
Green header | Columns I'd add today (Days Past Due, Aging Bucket, Status)
Blue text | Manual entries (work orders, shortages, report date)
Black text | Formulas
Orange fill | Item Number with more than one open order (combine work orders)
Tabs
Dashboard | Summary, funnel, status $, aging buckets, shortage $ by component
Planning Work | The P lines, with the lookups and the work that got done
Past Due Report | Raw export, as received
Do Not Make List | Engineering-hold items
Credit Hold List | Customers on credit hold
Note on C5: Input. Every Days Past Due and aging-bucket formula keys off this one cell (named range ReportDate).

## Dashboard
PAST-DUE ORDER ANALYSIS
Manufacturer One ¦ Report date 06/11/2022 ¦ synthetic data
Total past-due $ |  | Operations (O) share | Planning actionable $ | Tied to a work order |  | On credit hold | Held by shortages
10214737.46 |  | 85.41% | 435737.83 | 72399.84 |  | 36249.92 | 118600.34
1. The funnel: what Planning could actually move |  |  |  | 3. Past-due $ by aging bucket
Stage | Lines | Ext Price $ | % of Past-Due $ | Days Past Due | Lines | Operations (O) $ | Planning (P) $
All past-due lines | 1987 | 10214737.46 | 100% | 1-30 | 526 | 2557154.83 | 201360.01
Operations (O): not Planning's | 1492 | 8724895.67 | 85.41% | 31-60 | 473 | 2070237.04 | 339911.89
Planning (P) | 495 | 1489841.79 | 14.59% | 61-90 | 396 | 1787976.93 | 259034.18
P on Do Not Make List | 297 | 1054103.96 | 10.32% | 90+ | 592 | 2309526.87 | 689535.71
P actionable | 198 | 435737.83 | 4.266% | Total | 1987 | 8724895.67 | 1489841.79
|  |  |  | Check: ties to funnel | OK
2. What happened to the actionable P lines |  |  |  | 4. Component shortages: the $ they hold up
Status | Lines | Ext Price $ | WO Ext Price $ | Missing Component | Lines | Order $ Held | Missing Qty
WO In Progress | 24 | 42907.4 | 35258.13 | CMP-633-T | 8 | 28973.27 | 224
WO Created (Today) | 19 | 43387.46 | 37141.71 | CMP-685-R | 3 | 15827.46 | 174
Credit Hold | 13 | 36249.92 | 0 | CMP-503-F | 3 | 11495.22 | 131
Component Shortage | 34 | 118600.34 | 118600.34 | CMP-386-S | 2 | 10510.6 | 73
Open - No Action | 108 | 194592.71 | 0 | CMP-512-T | 4 | 9663 | 155
Total actionable | 198 | 435737.83 | 191000.18 | CMP-512-R | 2 | 7453.4 | 103
Check: ties to funnel | OK |  |  | CMP-430-R | 1 | 7451.15 | 140
WO Ext Price = Work Order Qty x Unit Price, so short-shipped lines count only what ships. |  |  |  | CMP-625-S | 4 | 7295.42 | 138
|  |  |  | CMP-734-T | 3 | 6637.96 | 170
|  |  |  | CMP-382-F | 1 | 6342.38 | 22
|  |  |  | CMP-535-F | 2 | 5941.88 | 67
|  |  |  | CMP-640-F | 1 | 1008.6 | 6
|  |  |  | Total | 34 | 118600.34 | 1403

## Planning Work
Sales Order | Cust # | Order Date | Promise Date | Item Number | Qty | Unit Price | Ext Price | O/P | Days Past Due | Aging Bucket | Do Not Make (XLOOKUP) | Credit Hold (XLOOKUP) | # Orders for Item | Work Order # | Work Order Date | Work Order Qty | Missing Component | Missing Qty | WO Ext Price | Status
489661 | C10525 | 2022-02-25 | 2022-04-18 | AC-1060-10 | 27 | 197 | 5319 | P | 54 | 31-60 |  |  | 4 | 7712393 | 2022-03-02 | 27 | CMP-685-R | 54 | 5319 | Component Shortage
489444 | C10824 | 2022-01-09 | 2022-04-18 | AC-1060-10 | 39 | 41.38 | 1613.82 | P | 54 | 31-60 |  |  | 4 | [6 empty] | Open - No Action
489541 | C10787 | 2022-04-11 | 2022-05-19 | AC-1060-10 | 33 | 34.07 | 1124.31 | P | 23 | 1-30 |  |  | 4 | 7710359 | 2022-04-17 | 33 |  |  | 1124.31 | WO In Progress
489714 | C10758 | 2022-03-25 | 2022-06-05 | AC-1060-10 | 23 | 40.4 | 929.2 | P | 6 | 1-30 |  | Over Credit Limit | 4 | [6 empty] | Credit Hold
487675 | C10251 | 2021-07-29 | 2021-09-16 | AC-1084-B | 19 | 81.93 | 1556.67 | P | 268 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487855 | C10170 | 2021-07-24 | 2021-12-01 | AC-1084-B | 8 | 171.38 | 1371.04 | P | 192 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
488181 | C10824 | 2022-03-07 | 2022-05-14 | AC-1084-B | 24 | 63.33 | 1519.92 | P | 28 | 1-30 | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
489730 | C10664 | 2022-02-05 | 2022-04-09 | AC-1166-B | 31 | 120.2 | 3726.2 | P | 63 | 61-90 |  |  | 2 | [6 empty] | Open - No Action
488886 | C10316 | 2022-03-24 | 2022-05-30 | AC-1166-B | 17 | 203.64 | 3461.88 | P | 12 | 1-30 |  |  | 2 | 7712222 | 2022-04-05 | 17 | CMP-386-S | 17 | 3461.88 | Component Shortage
489207 | C10436 | 2021-06-10 | 2021-08-11 | AC-1231-10 | 33 | 65.13 | 2149.29 | P | 304 | 90+ |  |  | 5 | [6 empty] | Open - No Action
488892 | C10860 | 2021-11-30 | 2022-04-09 | AC-1231-10 | 39 | 118.95 | 4639.05 | P | 63 | 61-90 |  |  | 5 | 7711052 | 2022-06-11 | 31 |  |  | 3687.45 | WO Created (Today)
489155 | C10305 | 2022-01-05 | 2022-04-29 | AC-1231-10 | 29 | 170.26 | 4937.54 | P | 43 | 31-60 |  | Over Credit Limit | 5 | [6 empty] | Credit Hold
489316 | C10273 | 2022-02-01 | 2022-05-10 | AC-1231-10 | 17 | 87.93 | 1494.81 | P | 32 | 31-60 |  |  | 5 | [6 empty] | Open - No Action
488879 | C10936 | 2022-02-13 | 2022-05-14 | AC-1231-10 | 36 | 123.34 | 4440.24 | P | 28 | 1-30 |  |  | 5 | [6 empty] | Open - No Action
488839 | C10316 | 2021-02-28 | 2021-07-06 | AC-1293-A | 46 | 122.34 | 5627.64 | P | 340 | 90+ | Engineering Hold - Material Deviation |  | 1 | [6 empty] | Do Not Make
489307 | C10852 | 2022-01-20 | 2022-02-18 | AC-1347-B | 6 | 29.94 | 179.64 | P | 113 | 90+ |  |  | 2 | 7710557 | 2022-01-22 | 4 |  |  | 119.76 | WO In Progress
489134 | C10332 | 2021-11-05 | 2022-03-22 | AC-1347-B | 19 | 182.45 | 3466.55 | P | 81 | 61-90 |  |  | 2 | 7711605 | 2021-11-10 | 19 | CMP-512-R | 19 | 3466.55 | Component Shortage
489091 | C10824 | 2021-08-04 | 2021-12-18 | AC-1392-B | 13 | 31.26 | 406.38 | P | 175 | 90+ |  |  | 2 | [6 empty] | Open - No Action
489677 | C10973 | 2021-12-08 | 2022-04-06 | AC-1392-B | 22 | 113.35 | 2493.7 | P | 66 | 61-90 |  |  | 2 | [6 empty] | Open - No Action
488506 | C10222 | 2021-06-01 | 2021-09-23 | AC-1448-02 | 59 | 112.2 | 6619.8 | P | 261 | 90+ | Engineering Hold - Drawing Rev Pending |  | 2 | [6 empty] | Do Not Make
487866 | C10817 | 2021-06-29 | 2021-11-12 | AC-1448-02 | 4 | 54.23 | 216.92 | P | 211 | 90+ | Engineering Hold - Drawing Rev Pending |  | 2 | [6 empty] | Do Not Make
489636 | C10238 | 2022-03-30 | 2022-05-13 | AC-1459-B | 17 | 87.07 | 1480.19 | P | 29 | 1-30 |  |  | 1 | 7710491 | 2022-04-01 | 17 |  |  | 1480.19 | WO In Progress
488233 | C10824 | 2021-09-28 | 2022-01-24 | AC-1514-10 | 58 | 116.82 | 6775.56 | P | 138 | 90+ | Engineering Hold - NCR Open |  | 2 | [6 empty] | Do Not Make
487716 | C10331 | 2022-02-16 | 2022-03-31 | AC-1514-10 | 47 | 133.96 | 6296.12 | P | 72 | 61-90 | Engineering Hold - NCR Open |  | 2 | [6 empty] | Do Not Make
489627 | C10321 | 2022-02-10 | 2022-04-14 | AC-1565-05 | 27 | 64.07 | 1729.89 | P | 58 | 31-60 |  |  | 1 | [6 empty] | Open - No Action
487896 | C10526 | 2021-05-23 | 2021-06-23 | AC-1570-02 | 13 | 41.8 | 543.4 | P | 353 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488551 | C10860 | 2021-05-29 | 2021-10-05 | AC-1570-02 | 24 | 78.42 | 1882.08 | P | 249 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487830 | C10688 | 2021-12-14 | 2022-02-03 | AC-1570-02 | 8 | 88.86 | 710.88 | P | 128 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487445 | C10327 | 2021-12-14 | 2022-03-11 | AC-1570-02 | 58 | 95.67 | 5548.86 | P | 92 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488810 | C10852 | 2021-12-07 | 2022-01-26 | AC-1599-03 | 18 | 120.87 | 2175.66 | P | 136 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
487881 | C10752 | 2022-04-15 | 2022-06-08 | AC-1599-03 | 23 | 148.93 | 3425.39 | P | 3 | 1-30 | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
488595 | C10787 | 2021-07-12 | 2021-10-19 | AC-1601-05 | 19 | 98.77 | 1876.63 | P | 235 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488580 | C10544 | 2021-09-19 | 2022-01-13 | AC-1601-05 | 46 | 89.9 | 4135.4 | P | 149 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
487480 | C10752 | 2022-03-04 | 2022-05-04 | AC-1601-05 | 57 | 155.8 | 8880.6 | P | 38 | 31-60 | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488828 | C10331 | 2021-12-26 | 2022-02-08 | AC-1648-A | 29 | 113.39 | 3288.31 | P | 123 | 90+ | Engineering Hold - First Article Rejected |  | 2 | [6 empty] | Do Not Make
488699 | C10544 | 2022-01-13 | 2022-04-21 | AC-1648-A | 39 | 174.06 | 6788.34 | P | 51 | 31-60 | Engineering Hold - First Article Rejected |  | 2 | [6 empty] | Do Not Make
488959 | C10456 | 2021-09-08 | 2021-10-22 | AC-1773-02 | 5 | 28.06 | 140.3 | P | 232 | 90+ |  |  | 2 | [6 empty] | Open - No Action
489669 | C10519 | 2022-03-24 | 2022-05-16 | AC-1773-02 | 8 | 29.44 | 235.52 | P | 26 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
489332 | C10273 | 2021-04-25 | 2021-07-27 | AC-1787-01 | 24 | 60.71 | 1457.04 | P | 319 | 90+ |  |  | 2 | 7711526 | 2021-05-06 | 24 | CMP-734-T | 96 | 1457.04 | Component Shortage
489561 | C10530 | 2021-10-10 | 2022-02-15 | AC-1787-01 | 7 | 179.34 | 1255.38 | P | 116 | 90+ |  |  | 2 | 7711273 | 2021-10-13 | 7 | CMP-512-T | 14 | 1255.38 | Component Shortage
488645 | C10695 | 2021-06-21 | 2021-07-21 | AC-1883-02 | 42 | 93.67 | 3934.14 | P | 325 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
487654 | C10817 | 2021-09-29 | 2021-12-21 | AC-1883-02 | 11 | 56.78 | 624.58 | P | 172 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
487523 | C10519 | 2022-01-12 | 2022-05-08 | AC-1883-02 | 16 | 51.92 | 830.72 | P | 34 | 31-60 | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
489387 | C10544 | 2021-11-14 | 2022-03-26 | AC-1891-03 | 28 | 135.11 | 3783.08 | P | 77 | 61-90 |  |  | 3 | 7710530 | 2021-11-18 | 22 |  |  | 2972.42 | WO In Progress
489377 | C10852 | 2022-04-03 | 2022-05-02 | AC-1891-03 | 35 | 212.89 | 7451.15 | P | 40 | 31-60 |  |  | 3 | 7711304 | 2022-04-14 | 35 | CMP-430-R | 140 | 7451.15 | Component Shortage
489612 | C10544 | 2022-01-11 | 2022-05-14 | AC-1891-03 | 6 | 73.12 | 438.72 | P | 28 | 1-30 |  |  | 3 | 7712304 | 2022-01-16 | 6 | CMP-633-T | 12 | 438.72 | Component Shortage
488040 | C10316 | 2021-09-29 | 2022-01-28 | AC-1894-02 | 31 | 70.81 | 2195.11 | P | 134 | 90+ | Engineering Hold - Drawing Rev Pending |  | 1 | [6 empty] | Do Not Make
489165 | C10966 | 2022-01-09 | 2022-05-23 | AC-1960-B | 34 | 120.58 | 4099.72 | P | 19 | 1-30 |  |  | 1 | 7710477 | 2022-01-17 | 26 |  |  | 3135.08 | WO In Progress
488436 | C10501 | 2021-10-16 | 2022-01-02 | AC-2081-A | 19 | 50.67 | 962.73 | P | 160 | 90+ | Engineering Hold - First Article Rejected |  | 1 | [6 empty] | Do Not Make
487757 | C10273 | 2021-07-07 | 2021-10-11 | AC-2092-01 | 17 | 139.47 | 2370.99 | P | 243 | 90+ | Engineering Hold - First Article Rejected |  | 1 | [6 empty] | Do Not Make
487786 | C10940 | 2021-11-13 | 2022-02-09 | AC-2133-01 | 7 | 112.36 | 786.52 | P | 122 | 90+ | Engineering Hold - NCR Open |  | 1 | [6 empty] | Do Not Make
489216 | C10249 | 2022-02-03 | 2022-05-11 | AC-2135-A | 9 | 69.52 | 625.68 | P | 31 | 31-60 |  | Over Credit Limit | 2 | [6 empty] | Credit Hold
489012 | C10281 | 2022-01-23 | 2022-06-06 | AC-2135-A | 7 | 119.71 | 837.97 | P | 5 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
489342 | C10436 | 2021-10-25 | 2022-01-17 | AC-2168-05 | 3 | 75.9 | 227.7 | P | 145 | 90+ |  |  | 1 | [6 empty] | Open - No Action
489003 | C10589 | 2022-02-08 | 2022-05-11 | AC-2250-05 | 27 | 110.26 | 2977.02 | P | 31 | 31-60 |  |  | 2 | [6 empty] | Open - No Action
489106 | C10305 | 2021-12-27 | 2022-05-14 | AC-2250-05 | 38 | 106.27 | 4038.26 | P | 28 | 1-30 |  | Over Credit Limit | 2 | [6 empty] | Credit Hold
487605 | C10327 | 2021-08-14 | 2021-09-11 | AC-2274-A | 30 | 136.26 | 4087.8 | P | 273 | 90+ | Engineering Hold - Drawing Rev Pending |  | 2 | [6 empty] | Do Not Make
487670 | C10695 | 2021-12-10 | 2022-04-12 | AC-2274-A | 40 | 73.24 | 2929.6 | P | 60 | 31-60 | Engineering Hold - Drawing Rev Pending |  | 2 | [6 empty] | Do Not Make
488916 | C10746 | 2021-05-29 | 2021-09-03 | AC-2322-03 | 32 | 114.35 | 3659.2 | P | 281 | 90+ |  |  | 3 | [6 empty] | Open - No Action
489760 | C10305 | 2022-03-21 | 2022-04-26 | AC-2322-03 | 32 | 158.89 | 5084.48 | P | 46 | 31-60 |  | Over Credit Limit | 3 | [6 empty] | Credit Hold
489153 | C10936 | 2022-04-02 | 2022-05-04 | AC-2322-03 | 27 | 110.22 | 2975.94 | P | 38 | 31-60 |  |  | 3 | 7712138 | 2022-04-04 | 27 | CMP-512-T | 108 | 2975.94 | Component Shortage
488366 | C10186 | 2021-10-03 | 2021-12-04 | AC-2334-02 | 41 | 59.19 | 2426.79 | P | 189 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488665 | C10280 | 2021-10-10 | 2022-02-22 | AC-2334-02 | 33 | 69.43 | 2291.19 | P | 109 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488812 | C10936 | 2022-01-06 | 2022-04-09 | AC-2334-02 | 53 | 40.67 | 2155.51 | P | 63 | 61-90 | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488465 | C10806 | 2021-12-30 | 2022-02-26 | AC-2349-05 | 29 | 113.04 | 3278.16 | P | 105 | 90+ | Engineering Hold - Drawing Rev Pending |  | 1 | [6 empty] | Do Not Make
488842 | C10950 | 2022-02-25 | 2022-04-14 | AC-2356-05 | 5 | 115.52 | 577.6 | P | 58 | 31-60 |  |  | 2 | 7711976 | 2022-03-09 | 5 | CMP-512-T | 5 | 577.6 | Component Shortage
489399 | C10501 | 2022-03-14 | 2022-05-28 | AC-2356-05 | 2 | 128.28 | 256.56 | P | 14 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
488389 | C10860 | 2021-12-06 | 2022-04-17 | AC-2363-03 | 36 | 160.32 | 5771.52 | P | 55 | 31-60 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
487806 | C10238 | 2021-12-24 | 2022-04-30 | AC-2363-03 | 59 | 168.56 | 9945.04 | P | 42 | 31-60 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
488631 | C10501 | 2021-11-09 | 2021-12-17 | AC-2364-01 | 20 | 144.57 | 2891.4 | P | 176 | 90+ | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
488441 | C10456 | 2021-11-24 | 2022-02-08 | AC-2364-01 | 26 | 119.6 | 3109.6 | P | 123 | 90+ | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487510 | C10817 | 2022-01-12 | 2022-04-18 | AC-2364-01 | 32 | 124.29 | 3977.28 | P | 54 | 31-60 | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487859 | C10526 | 2022-03-25 | 2022-04-28 | AC-2364-01 | 43 | 108.33 | 4658.19 | P | 44 | 31-60 | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487839 | C10385 | 2022-02-09 | 2022-05-04 | AC-2371-A | 4 | 131.7 | 526.8 | P | 38 | 31-60 | Engineering Hold - NCR Open |  | 1 | [6 empty] | Do Not Make
487409 | C10461 | 2021-02-24 | 2021-06-14 | AC-2415-B | 6 | 126.22 | 757.32 | P | 362 | 90+ | Engineering Hold - NCR Open |  | 6 | [6 empty] | Do Not Make
488482 | C10316 | 2021-08-17 | 2021-09-18 | AC-2415-B | 21 | 86.17 | 1809.57 | P | 266 | 90+ | Engineering Hold - NCR Open |  | 6 | [6 empty] | Do Not Make
487549 | C10526 | 2021-12-18 | 2022-03-09 | AC-2415-B | 9 | 110.19 | 991.71 | P | 94 | 90+ | Engineering Hold - NCR Open |  | 6 | [6 empty] | Do Not Make
488586 | C10264 | 2021-10-31 | 2022-03-19 | AC-2415-B | 47 | 65.07 | 3058.29 | P | 84 | 61-90 | Engineering Hold - NCR Open |  | 6 | [6 empty] | Do Not Make
487941 | C10752 | 2022-01-29 | 2022-03-19 | AC-2415-B | 50 | 48.08 | 2404 | P | 84 | 61-90 | Engineering Hold - NCR Open |  | 6 | [6 empty] | Do Not Make
487959 | C10950 | 2022-02-03 | 2022-05-20 | AC-2415-B | 28 | 146.76 | 4109.28 | P | 22 | 1-30 | Engineering Hold - NCR Open |  | 6 | [6 empty] | Do Not Make
488134 | C10526 | 2021-10-09 | 2022-01-31 | AC-2723-03 | 26 | 77 | 2002 | P | 131 | 90+ | Engineering Hold - First Article Rejected |  | 2 | [6 empty] | Do Not Make
488563 | C10817 | 2022-02-17 | 2022-05-08 | AC-2723-03 | 55 | 110.87 | 6097.85 | P | 34 | 31-60 | Engineering Hold - First Article Rejected |  | 2 | [6 empty] | Do Not Make
489447 | C10951 | 2022-01-08 | 2022-03-27 | AC-2726-B | 21 | 32.72 | 687.12 | P | 76 | 61-90 |  |  | 2 | 7710992 | 2022-06-11 | 21 |  |  | 687.12 | WO Created (Today)
488920 | C10695 | 2022-04-12 | 2022-05-27 | AC-2726-B | 39 | 128.65 | 5017.35 | P | 15 | 1-30 |  |  | 2 | 7711656 | 2022-04-18 | 39 | CMP-633-T | 39 | 5017.35 | Component Shortage
487423 | C10273 | 2021-12-24 | 2022-02-04 | AC-2790-10 | 60 | 137.02 | 8221.2 | P | 127 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
487694 | C10940 | 2022-03-22 | 2022-04-28 | AC-2790-10 | 44 | 74.95 | 3297.8 | P | 44 | 31-60 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
487988 | C10568 | 2021-06-10 | 2021-09-16 | AC-2827-02 | 5 | 69.2 | 346 | P | 268 | 90+ | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
488819 | C10331 | 2021-08-09 | 2021-10-19 | AC-2827-02 | 5 | 174.59 | 872.95 | P | 235 | 90+ | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
487769 | C10746 | 2022-02-25 | 2022-04-07 | AC-2827-02 | 22 | 73.23 | 1611.06 | P | 65 | 61-90 | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
487808 | C10951 | 2021-12-15 | 2022-04-14 | AC-2827-02 | 29 | 169.8 | 4924.2 | P | 58 | 31-60 | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
487571 | C10256 | 2022-03-14 | 2022-05-24 | AC-2827-02 | 37 | 166.65 | 6166.05 | P | 18 | 1-30 | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
488532 | C10936 | 2021-12-02 | 2022-03-14 | AC-2849-B | 17 | 94.35 | 1603.95 | P | 89 | 61-90 | Engineering Hold - Customer Spec Change |  | 1 | [6 empty] | Do Not Make
488415 | C10786 | 2021-07-02 | 2021-11-17 | AC-2870-A | 24 | 161.15 | 3867.6 | P | 206 | 90+ | Engineering Hold - First Article Rejected |  | 3 | [6 empty] | Do Not Make
488395 | C10461 | 2021-10-04 | 2022-01-09 | AC-2870-A | 8 | 81.72 | 653.76 | P | 153 | 90+ | Engineering Hold - First Article Rejected |  | 3 | [6 empty] | Do Not Make
487913 | C10706 | 2021-12-24 | 2022-04-15 | AC-2870-A | 54 | 48.31 | 2608.74 | P | 57 | 31-60 | Engineering Hold - First Article Rejected |  | 3 | [6 empty] | Do Not Make
488964 | C10273 | 2022-02-03 | 2022-05-03 | AC-2887-A | 16 | 111.46 | 1783.36 | P | 39 | 31-60 |  |  | 1 | 7710739 | 2022-06-11 | 16 |  |  | 1783.36 | WO Created (Today)
488122 | C10331 | 2021-11-26 | 2022-03-14 | AC-2960-10 | 7 | 117.7 | 823.9 | P | 89 | 61-90 | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487800 | C10951 | 2022-01-06 | 2022-03-19 | AC-2960-10 | 16 | 76.56 | 1224.96 | P | 84 | 61-90 | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487366 | C10281 | 2022-02-19 | 2022-06-01 | AC-2960-10 | 39 | 138.1 | 5385.9 | P | 10 | 1-30 | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
488809 | C10498 | 2022-02-27 | 2022-06-05 | AC-2960-10 | 57 | 102.04 | 5816.28 | P | 6 | 1-30 | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487730 | C10461 | 2021-12-20 | 2022-02-02 | AC-2967-A | 49 | 100.94 | 4946.06 | P | 129 | 90+ | Engineering Hold - Material Deviation |  | 1 | [6 empty] | Do Not Make
489226 | C10385 | 2022-03-05 | 2022-04-19 | AC-2988-A | 13 | 46.34 | 602.42 | P | 53 | 31-60 |  |  | 1 | [6 empty] | Open - No Action
489219 | C10461 | 2021-10-19 | 2021-12-08 | AC-3001-01 | 4 | 88.14 | 352.56 | P | 185 | 90+ |  |  | 1 | [6 empty] | Open - No Action
488160 | C10950 | 2021-11-12 | 2021-12-20 | AC-3047-05 | 29 | 139.14 | 4035.06 | P | 173 | 90+ | Engineering Hold - NCR Open |  | 2 | [6 empty] | Do Not Make
488030 | C10526 | 2021-11-27 | 2022-04-13 | AC-3047-05 | 45 | 173.07 | 7788.15 | P | 59 | 31-60 | Engineering Hold - NCR Open |  | 2 | [6 empty] | Do Not Make
488155 | C10456 | 2021-06-12 | 2021-08-19 | AC-3053-03 | 55 | 130.28 | 7165.4 | P | 296 | 90+ | Engineering Hold - Material Deviation |  | 1 | [6 empty] | Do Not Make
488456 | C10273 | 2021-04-08 | 2021-07-23 | AC-3060-02 | 33 | 179.42 | 5920.86 | P | 323 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488619 | C10568 | 2021-11-13 | 2021-12-25 | AC-3060-02 | 43 | 109.53 | 4709.79 | P | 168 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488082 | C10321 | 2022-02-09 | 2022-04-18 | AC-3060-02 | 36 | 40.36 | 1452.96 | P | 54 | 31-60 | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
489298 | C10568 | 2022-03-18 | 2022-04-25 | AC-3086-05 | 2 | 61.08 | 122.16 | P | 47 | 31-60 |  |  | 1 | 7711211 | 2022-06-11 | 1 |  |  | 61.08 | WO Created (Today)
487742 | C10281 | 2021-04-29 | 2021-08-08 | AC-3103-B | 10 | 129.45 | 1294.5 | P | 307 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
488783 | C10746 | 2021-04-23 | 2021-09-06 | AC-3103-B | 59 | 167.77 | 9898.43 | P | 278 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
487640 | C10170 | 2021-05-04 | 2021-07-12 | AC-3141-10 | 20 | 119.08 | 2381.6 | P | 334 | 90+ | Engineering Hold - Drawing Rev Pending |  | 1 | [6 empty] | Do Not Make
489167 | C10385 | 2022-01-09 | 2022-03-21 | AC-3147-10 | 6 | 33.11 | 198.66 | P | 82 | 61-90 |  |  | 1 | [6 empty] | Open - No Action
488053 | C10589 | 2021-04-01 | 2021-05-27 | AC-3151-05 | 15 | 86.61 | 1299.15 | P | 380 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488308 | C10806 | 2021-06-19 | 2021-07-25 | AC-3151-05 | 14 | 144.43 | 2022.02 | P | 321 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488421 | C10461 | 2022-02-03 | 2022-03-19 | AC-3151-05 | 58 | 118.59 | 6878.22 | P | 84 | 61-90 | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488611 | C10568 | 2021-12-31 | 2022-04-04 | AC-3151-05 | 51 | 146.87 | 7490.37 | P | 68 | 61-90 | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
489487 | C10526 | 2022-01-19 | 2022-03-24 | AC-3196-A | 28 | 89.47 | 2505.16 | P | 79 | 61-90 |  |  | 4 | [6 empty] | Open - No Action
489700 | C10498 | 2021-12-23 | 2022-04-09 | AC-3196-A | 8 | 67.87 | 542.96 | P | 63 | 61-90 |  |  | 4 | [6 empty] | Open - No Action
489290 | C10249 | 2022-01-20 | 2022-04-15 | AC-3196-A | 38 | 139.46 | 5299.48 | P | 57 | 31-60 |  | Over Credit Limit | 4 | [6 empty] | Credit Hold
489368 | C10273 | 2022-04-29 | 2022-06-10 | AC-3196-A | 6 | 56.75 | 340.5 | P | 1 | 1-30 |  |  | 4 | [6 empty] | Open - No Action
487872 | C10900 | 2021-05-13 | 2021-06-16 | AC-3231-10 | 49 | 50.03 | 2451.47 | P | 360 | 90+ | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488387 | C10688 | 2021-12-05 | 2022-01-07 | AC-3231-10 | 13 | 86.29 | 1121.77 | P | 155 | 90+ | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488102 | C10966 | 2022-02-01 | 2022-04-20 | AC-3231-10 | 37 | 152.8 | 5653.6 | P | 52 | 31-60 | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488758 | C10530 | 2022-04-15 | 2022-05-14 | AC-3231-10 | 39 | 168.08 | 6555.12 | P | 28 | 1-30 | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488747 | C10806 | 2021-11-22 | 2022-03-10 | AC-3257-03 | 43 | 68.63 | 2951.09 | P | 93 | 90+ | Engineering Hold - Customer Spec Change |  | 1 | [6 empty] | Do Not Make
489740 | C10752 | 2021-12-28 | 2022-04-17 | AC-3277-05 | 10 | 44.72 | 447.2 | P | 55 | 31-60 |  |  | 4 | 7710116 | 2022-01-07 | 7 |  |  | 313.04 | WO In Progress
489615 | C10385 | 2022-01-01 | 2022-05-14 | AC-3277-05 | 5 | 32.63 | 163.15 | P | 28 | 1-30 |  |  | 4 | 7710055 | 2022-01-12 | 3 |  |  | 97.89 | WO In Progress
489500 | C10455 | 2022-04-12 | 2022-05-30 | AC-3277-05 | 12 | 94.59 | 1135.08 | P | 12 | 1-30 |  |  | 4 | [6 empty] | Open - No Action
489594 | C10256 | 2022-01-16 | 2022-06-01 | AC-3277-05 | 14 | 48.09 | 673.26 | P | 10 | 1-30 |  |  | 4 | [6 empty] | Open - No Action
489174 | C10706 | 2022-02-01 | 2022-05-04 | AC-3285-10 | 2 | 27.23 | 54.46 | P | 38 | 31-60 |  |  | 1 | 7711159 | 2022-06-11 | 1 |  |  | 27.23 | WO Created (Today)
487817 | C10688 | 2021-03-19 | 2021-07-03 | AC-3287-02 | 44 | 70.61 | 3106.84 | P | 343 | 90+ | Engineering Hold - Drawing Rev Pending |  | 3 | [6 empty] | Do Not Make
487632 | C10273 | 2021-05-19 | 2021-07-09 | AC-3287-02 | 14 | 179.23 | 2509.22 | P | 337 | 90+ | Engineering Hold - Drawing Rev Pending |  | 3 | [6 empty] | Do Not Make
488398 | C10385 | 2022-01-03 | 2022-05-11 | AC-3287-02 | 14 | 107.21 | 1500.94 | P | 31 | 31-60 | Engineering Hold - Drawing Rev Pending |  | 3 | [6 empty] | Do Not Make
488793 | C10316 | 2021-06-26 | 2021-08-15 | AC-3359-A | 37 | 107.1 | 3962.7 | P | 300 | 90+ | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
488774 | C10860 | 2021-08-27 | 2021-09-27 | AC-3359-A | 35 | 104.32 | 3651.2 | P | 257 | 90+ | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487491 | C10273 | 2021-11-16 | 2021-12-15 | AC-3359-A | 9 | 157.79 | 1420.11 | P | 178 | 90+ | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487770 | C10966 | 2021-11-11 | 2022-02-11 | AC-3359-A | 21 | 41.73 | 876.33 | P | 120 | 90+ | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
488590 | C10852 | 2021-03-07 | 2021-06-12 | AC-3396-01 | 50 | 165.35 | 8267.5 | P | 364 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487416 | C10252 | 2021-09-21 | 2021-12-04 | AC-3396-01 | 56 | 104.65 | 5860.4 | P | 189 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487993 | C10331 | 2022-02-25 | 2022-05-20 | AC-3396-01 | 26 | 71.96 | 1870.96 | P | 22 | 1-30 | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
488343 | C10498 | 2021-07-06 | 2021-08-21 | AC-3471-10 | 18 | 146.96 | 2645.28 | P | 294 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
487919 | C10350 | 2021-10-31 | 2022-01-01 | AC-3471-10 | 45 | 51.58 | 2321.1 | P | 161 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488841 | C10264 | 2021-09-20 | 2022-02-02 | AC-3471-10 | 59 | 41.74 | 2462.66 | P | 129 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
489097 | C10758 | 2022-02-11 | 2022-03-26 | AC-3542-03 | 37 | 69.85 | 2584.45 | P | 77 | 61-90 |  | Over Credit Limit | 2 | [6 empty] | Credit Hold
489385 | C10752 | 2022-01-16 | 2022-05-01 | AC-3542-03 | 37 | 87.06 | 3221.22 | P | 41 | 31-60 |  |  | 2 | 7710160 | 2022-01-27 | 37 |  |  | 3221.22 | WO In Progress
489416 | C10273 | 2021-12-31 | 2022-03-15 | AC-3584-05 | 21 | 177.07 | 3718.47 | P | 88 | 61-90 |  |  | 1 | 7711401 | 2022-01-06 | 21 | CMP-535-F | 21 | 3718.47 | Component Shortage
489391 | C10787 | 2021-07-04 | 2021-09-21 | AC-3592-B | 36 | 85.29 | 3070.44 | P | 263 | 90+ |  |  | 2 | [6 empty] | Open - No Action
489605 | C10530 | 2022-01-22 | 2022-06-05 | AC-3592-B | 13 | 62.32 | 810.16 | P | 6 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
489267 | C10377 | 2021-11-01 | 2021-12-26 | AC-3628-10 | 11 | 48.65 | 535.15 | P | 167 | 90+ |  |  | 1 | [6 empty] | Open - No Action
488673 | C10211 | 2021-03-17 | 2021-06-28 | AC-3665-03 | 46 | 137.39 | 6319.94 | P | 348 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487890 | C10852 | 2021-10-14 | 2021-12-18 | AC-3665-03 | 60 | 83.39 | 5003.4 | P | 175 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488476 | C10420 | 2021-08-18 | 2021-12-19 | AC-3665-03 | 46 | 105.07 | 4833.22 | P | 174 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487473 | C10940 | 2021-12-23 | 2022-03-04 | AC-3665-03 | 47 | 132.06 | 6206.82 | P | 99 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487950 | C10526 | 2021-04-27 | 2021-07-15 | AC-3675-B | 46 | 165.91 | 7631.86 | P | 331 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487778 | C10222 | 2021-12-08 | 2022-01-12 | AC-3675-B | 19 | 54.08 | 1027.52 | P | 150 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
488600 | C10321 | 2021-10-05 | 2022-02-11 | AC-3675-B | 60 | 144.39 | 8663.4 | P | 120 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
488008 | C10420 | 2021-07-03 | 2021-09-15 | AC-3696-02 | 58 | 70.42 | 4084.36 | P | 269 | 90+ | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
487970 | C10973 | 2021-06-27 | 2021-11-06 | AC-3696-02 | 24 | 162.15 | 3891.6 | P | 217 | 90+ | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
487663 | C10817 | 2022-01-13 | 2022-02-24 | AC-3696-02 | 14 | 46.93 | 657.02 | P | 107 | 90+ | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
488405 | C10787 | 2021-12-08 | 2022-03-20 | AC-3696-02 | 28 | 99.33 | 2781.24 | P | 83 | 61-90 | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
487360 | C10806 | 2021-04-14 | 2021-08-06 | AC-3755-02 | 57 | 77.46 | 4415.22 | P | 309 | 90+ | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
488294 | C10281 | 2021-11-24 | 2022-03-20 | AC-3755-02 | 40 | 149.17 | 5966.8 | P | 83 | 61-90 | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
488185 | C10436 | 2022-03-02 | 2022-04-14 | AC-3755-02 | 37 | 153.55 | 5681.35 | P | 58 | 31-60 | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
488194 | C10824 | 2021-12-20 | 2022-04-19 | AC-3755-02 | 14 | 46.58 | 652.12 | P | 53 | 31-60 | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
487964 | C10940 | 2022-02-18 | 2022-06-07 | AC-3755-02 | 40 | 68.75 | 2750 | P | 4 | 1-30 | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
489247 | C10519 | 2021-11-27 | 2022-04-16 | AC-3870-01 | 6 | 76.2 | 457.2 | P | 56 | 31-60 |  |  | 1 | 7712132 | 2021-12-08 | 6 | CMP-503-F | 12 | 457.2 | Component Shortage
489471 | C10256 | 2022-01-10 | 2022-03-05 | AC-3878-05 | 9 | 83.83 | 754.47 | P | 98 | 90+ |  |  | 1 | [6 empty] | Open - No Action
488109 | C10456 | 2021-03-07 | 2021-06-05 | AC-3912-03 | 26 | 90.35 | 2349.1 | P | 371 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
488198 | C10456 | 2021-03-03 | 2021-07-04 | AC-3912-03 | 42 | 158.52 | 6657.84 | P | 342 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
488694 | C10940 | 2021-05-24 | 2021-07-28 | AC-3912-03 | 7 | 179.67 | 1257.69 | P | 318 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
487764 | C10170 | 2022-01-31 | 2022-03-25 | AC-3912-03 | 60 | 70.61 | 4236.6 | P | 78 | 61-90 | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
487979 | C10256 | 2021-03-01 | 2021-07-15 | AC-3929-10 | 13 | 44.29 | 575.77 | P | 331 | 90+ | Engineering Hold - First Article Rejected |  | 5 | [6 empty] | Do Not Make
488273 | C10519 | 2021-05-30 | 2021-08-19 | AC-3929-10 | 17 | 81.81 | 1390.77 | P | 296 | 90+ | Engineering Hold - First Article Rejected |  | 5 | [6 empty] | Do Not Make
487457 | C10900 | 2021-05-17 | 2021-09-11 | AC-3929-10 | 46 | 99.93 | 4596.78 | P | 273 | 90+ | Engineering Hold - First Article Rejected |  | 5 | [6 empty] | Do Not Make
488310 | C10455 | 2021-09-14 | 2021-10-31 | AC-3929-10 | 39 | 44.18 | 1723.02 | P | 223 | 90+ | Engineering Hold - First Article Rejected |  | 5 | [6 empty] | Do Not Make
488371 | C10332 | 2022-01-23 | 2022-02-26 | AC-3929-10 | 32 | 154.1 | 4931.2 | P | 105 | 90+ | Engineering Hold - First Article Rejected |  | 5 | [6 empty] | Do Not Make
488909 | C10756 | 2022-04-09 | 2022-05-26 | AC-4011-03 | 25 | 103.06 | 2576.5 | P | 16 | 1-30 |  | Over Credit Limit | 1 | [6 empty] | Credit Hold
489015 | C10461 | 2021-06-17 | 2021-09-03 | AC-4074-03 | 8 | 109.06 | 872.48 | P | 281 | 90+ |  |  | 4 | [6 empty] | Open - No Action
489187 | C10420 | 2022-01-20 | 2022-04-10 | AC-4074-03 | 8 | 34.98 | 279.84 | P | 62 | 61-90 |  |  | 4 | [6 empty] | Open - No Action
489351 | C10436 | 2021-12-31 | 2022-05-05 | AC-4074-03 | 13 | 135.06 | 1755.78 | P | 37 | 31-60 |  |  | 4 | [6 empty] | Open - No Action
489004 | C10456 | 2022-04-07 | 2022-05-08 | AC-4074-03 | 2 | 50.97 | 101.94 | P | 34 | 31-60 |  |  | 4 | 7710407 | 2022-04-17 | 1 |  |  | 50.97 | WO In Progress
487425 | C10806 | 2021-05-04 | 2021-07-01 | AC-4082-10 | 40 | 92.06 | 3682.4 | P | 345 | 90+ | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
487364 | C10273 | 2021-05-25 | 2021-07-26 | AC-4082-10 | 5 | 81.25 | 406.25 | P | 320 | 90+ | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
488542 | C10461 | 2021-07-02 | 2021-08-14 | AC-4082-10 | 33 | 149.85 | 4945.05 | P | 301 | 90+ | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
487907 | C10973 | 2021-10-29 | 2021-12-23 | AC-4082-10 | 15 | 116.08 | 1741.2 | P | 170 | 90+ | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
488782 | C10238 | 2021-12-04 | 2022-03-21 | AC-4082-10 | 27 | 59.18 | 1597.86 | P | 82 | 61-90 | Engineering Hold - Material Deviation |  | 5 | [6 empty] | Do Not Make
489312 | C10752 | 2022-02-10 | 2022-03-22 | AC-4109-05 | 35 | 159.55 | 5584.25 | P | 81 | 61-90 |  |  | 5 | 7711455 | 2022-02-16 | 35 | CMP-633-T | 35 | 5584.25 | Component Shortage
489569 | C10830 | 2021-12-16 | 2022-04-28 | AC-4109-05 | 11 | 304.44 | 3348.84 | P | 44 | 31-60 |  |  | 5 | 7712540 | 2021-12-18 | 11 | CMP-625-S | 44 | 3348.84 | Component Shortage
489146 | C10264 | 2022-02-23 | 2022-05-18 | AC-4109-05 | 6 | 110.5 | 663 | P | 24 | 1-30 |  |  | 5 | 7711496 | 2022-03-03 | 6 | CMP-734-T | 6 | 663 | Component Shortage
489334 | C10238 | 2022-04-25 | 2022-06-07 | AC-4109-05 | 4 | 99.17 | 396.68 | P | 4 | 1-30 |  |  | 5 | [6 empty] | Open - No Action
489587 | C10900 | 2022-03-30 | 2022-06-08 | AC-4109-05 | 19 | 117.1 | 2224.9 | P | 3 | 1-30 |  |  | 5 | [6 empty] | Open - No Action
489597 | C10830 | 2021-08-11 | 2021-10-17 | AC-4162-03 | 2 | 72.21 | 144.42 | P | 237 | 90+ |  |  | 1 | 7711825 | 2021-08-23 | 2 | CMP-633-T | 2 | 144.42 | Component Shortage
489706 | C10695 | 2021-05-20 | 2021-08-08 | AC-4212-B | 38 | 82.33 | 3128.54 | P | 307 | 90+ |  |  | 2 | [6 empty] | Open - No Action
489320 | C10332 | 2021-11-27 | 2022-02-02 | AC-4212-B | 35 | 83.89 | 2936.15 | P | 129 | 90+ |  |  | 2 | [6 empty] | Open - No Action
487596 | C10170 | 2021-04-21 | 2021-08-22 | AC-4215-05 | 52 | 44.15 | 2295.8 | P | 293 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488560 | C10252 | 2022-04-08 | 2022-05-11 | AC-4215-05 | 56 | 172.86 | 9680.16 | P | 31 | 31-60 | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
487559 | C10786 | 2022-02-27 | 2022-05-26 | AC-4215-05 | 18 | 68.44 | 1231.92 | P | 16 | 1-30 | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
487751 | C10281 | 2021-12-14 | 2022-04-16 | AC-4250-A | 41 | 81.45 | 3339.45 | P | 56 | 31-60 | Engineering Hold - NCR Open |  | 1 | [6 empty] | Do Not Make
489326 | C10280 | 2022-02-12 | 2022-04-30 | AC-4304-A | 30 | 28.33 | 849.9 | P | 42 | 31-60 |  |  | 1 | [6 empty] | Open - No Action
489033 | C10377 | 2021-03-12 | 2021-07-20 | AC-4307-01 | 15 | 45.85 | 687.75 | P | 326 | 90+ |  |  | 6 | [6 empty] | Open - No Action
489553 | C10377 | 2021-12-23 | 2022-03-15 | AC-4307-01 | 6 | 168.1 | 1008.6 | P | 88 | 61-90 |  |  | 6 | 7712242 | 2022-01-04 | 6 | CMP-640-F | 6 | 1008.6 | Component Shortage
489799 | C10170 | 2021-12-04 | 2022-04-15 | AC-4307-01 | 29 | 108.26 | 3139.54 | P | 57 | 31-60 |  |  | 6 | [6 empty] | Open - No Action
489687 | C10256 | 2022-01-15 | 2022-05-05 | AC-4307-01 | 39 | 134.01 | 5226.39 | P | 37 | 31-60 |  |  | 6 | [6 empty] | Open - No Action
488961 | C10327 | 2022-04-01 | 2022-06-04 | AC-4307-01 | 13 | 57.19 | 743.47 | P | 7 | 1-30 |  |  | 6 | [6 empty] | Open - No Action
489685 | C10377 | 2022-04-01 | 2022-06-05 | AC-4307-01 | 26 | 184.95 | 4808.7 | P | 6 | 1-30 |  |  | 6 | 7712489 | 2022-04-11 | 26 | CMP-685-R | 52 | 4808.7 | Component Shortage
488322 | C10331 | 2021-06-13 | 2021-09-12 | AC-4386-01 | 49 | 50.72 | 2485.28 | P | 272 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
488749 | C10936 | 2021-10-17 | 2021-12-04 | AC-4386-01 | 4 | 127.07 | 508.28 | P | 189 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
487626 | C10498 | 2021-07-31 | 2021-12-06 | AC-4386-01 | 10 | 121.15 | 1211.5 | P | 187 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
487711 | C10377 | 2021-11-28 | 2022-04-12 | AC-4386-01 | 41 | 76.74 | 3146.34 | P | 60 | 31-60 | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
489021 | C10251 | 2022-02-27 | 2022-05-19 | AC-4512-A | 32 | 129.7 | 4150.4 | P | 23 | 1-30 |  |  | 1 | [6 empty] | Open - No Action
488032 | C10251 | 2021-11-07 | 2022-03-15 | AC-4597-10 | 39 | 91.76 | 3578.64 | P | 88 | 61-90 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
487363 | C10951 | 2022-03-10 | 2022-05-04 | AC-4597-10 | 37 | 83.76 | 3099.12 | P | 38 | 31-60 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
489750 | C10377 | 2022-01-30 | 2022-03-22 | AC-4600-10 | 23 | 97.21 | 2235.83 | P | 81 | 61-90 |  |  | 5 | [6 empty] | Open - No Action
489772 | C10170 | 2021-11-18 | 2022-03-25 | AC-4600-10 | 19 | 52.06 | 989.14 | P | 78 | 61-90 |  |  | 5 | 7710258 | 2021-11-21 | 10 |  |  | 520.6 | WO In Progress
489065 | C10752 | 2022-03-08 | 2022-04-05 | AC-4600-10 | 11 | 120.33 | 1323.63 | P | 67 | 61-90 |  |  | 5 | [6 empty] | Open - No Action
489028 | C10560 | 2022-01-03 | 2022-04-14 | AC-4600-10 | 8 | 137.77 | 1102.16 | P | 58 | 31-60 |  |  | 5 | [6 empty] | Open - No Action
489273 | C10305 | 2022-03-24 | 2022-05-12 | AC-4600-10 | 27 | 99.79 | 2694.33 | P | 30 | 1-30 |  | Over Credit Limit | 5 | [6 empty] | Credit Hold
487431 | C10456 | 2021-02-01 | 2021-06-12 | AC-4607-A | 45 | 146.36 | 6586.2 | P | 364 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
488274 | C10455 | 2021-11-29 | 2022-01-04 | AC-4607-A | 5 | 159.17 | 795.85 | P | 158 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
487501 | C10950 | 2022-03-01 | 2022-04-16 | AC-4645-05 | 42 | 42.58 | 1788.36 | P | 56 | 31-60 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
488269 | C10688 | 2021-12-27 | 2022-04-24 | AC-4645-05 | 25 | 157.61 | 3940.25 | P | 48 | 31-60 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
488408 | C10560 | 2021-05-13 | 2021-09-12 | AC-4690-10 | 37 | 131.58 | 4868.46 | P | 272 | 90+ | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
487638 | C10752 | 2022-02-03 | 2022-03-25 | AC-4690-10 | 55 | 43.9 | 2414.5 | P | 78 | 61-90 | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
488074 | C10456 | 2022-03-21 | 2022-05-01 | AC-4690-10 | 55 | 152 | 8360 | P | 41 | 31-60 | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
488704 | C10560 | 2022-01-17 | 2022-05-05 | AC-4690-10 | 14 | 179.94 | 2519.16 | P | 37 | 31-60 | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
489349 | C10273 | 2021-12-04 | 2022-04-02 | AC-4709-01 | 25 | 66.82 | 1670.5 | P | 70 | 61-90 |  |  | 1 | [6 empty] | Open - No Action
489783 | C10966 | 2021-12-27 | 2022-04-05 | AC-4777-10 | 21 | 100.91 | 2119.11 | P | 67 | 61-90 |  |  | 1 | [6 empty] | Open - No Action
488564 | C10519 | 2021-11-30 | 2022-04-02 | AC-4792-10 | 37 | 179.62 | 6645.94 | P | 70 | 61-90 | Engineering Hold - Material Deviation |  | 1 | [6 empty] | Do Not Make
489766 | C10966 | 2021-08-08 | 2021-10-28 | AC-4801-02 | 26 | 161.73 | 4204.98 | P | 226 | 90+ |  |  | 1 | 7712282 | 2021-08-19 | 26 | CMP-633-T | 26 | 4204.98 | Component Shortage
487931 | C10530 | 2021-08-14 | 2021-11-08 | AC-4825-B | 40 | 82.51 | 3300.4 | P | 215 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488687 | C10281 | 2021-12-04 | 2022-04-11 | AC-4825-B | 51 | 179.21 | 9139.71 | P | 61 | 61-90 | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488064 | C10461 | 2021-12-16 | 2022-04-21 | AC-4825-B | 17 | 75.39 | 1281.63 | P | 51 | 31-60 | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
489280 | C10385 | 2022-01-20 | 2022-05-05 | AC-4830-03 | 18 | 126.39 | 2275.02 | P | 37 | 31-60 |  |  | 2 | 7710180 | 2022-01-26 | 12 |  |  | 1516.68 | WO In Progress
489601 | C10256 | 2022-05-06 | 2022-06-10 | AC-4830-03 | 10 | 83.7 | 837 | P | 1 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
487925 | C10936 | 2021-07-26 | 2021-10-11 | AC-4873-10 | 50 | 46.63 | 2331.5 | P | 243 | 90+ | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
487614 | C10568 | 2021-10-27 | 2022-01-05 | AC-4873-10 | 38 | 58.4 | 2219.2 | P | 157 | 90+ | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488242 | C10695 | 2022-01-11 | 2022-03-19 | AC-4873-10 | 38 | 60.13 | 2284.94 | P | 84 | 61-90 | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488784 | C10824 | 2022-02-14 | 2022-04-05 | AC-4873-10 | 19 | 76.81 | 1459.39 | P | 67 | 61-90 | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488917 | C10498 | 2021-10-28 | 2021-12-05 | AC-4972-05 | 40 | 130.86 | 5234.4 | P | 188 | 90+ |  |  | 6 | 7710044 | 2021-11-07 | 29 |  |  | 3794.94 | WO In Progress
489562 | C10752 | 2021-10-30 | 2022-03-01 | AC-4972-05 | 24 | 119.83 | 2875.92 | P | 102 | 90+ |  |  | 6 | [6 empty] | Open - No Action
488976 | C10830 | 2022-03-02 | 2022-04-23 | AC-4972-05 | 35 | 252.06 | 8822.1 | P | 49 | 31-60 |  |  | 6 | 7711793 | 2022-03-07 | 35 | CMP-503-F | 35 | 8822.1 | Component Shortage
489653 | C10706 | 2022-01-10 | 2022-04-23 | AC-4972-05 | 28 | 251.74 | 7048.72 | P | 49 | 31-60 |  |  | 6 | 7711744 | 2022-01-20 | 28 | CMP-386-S | 56 | 7048.72 | Component Shortage
489585 | C10560 | 2022-01-15 | 2022-05-03 | AC-4972-05 | 7 | 127.23 | 890.61 | P | 39 | 31-60 |  |  | 6 | 7710252 | 2022-01-17 | 7 |  |  | 890.61 | WO In Progress
489256 | C10170 | 2022-02-11 | 2022-05-28 | AC-4972-05 | 39 | 136.81 | 5335.59 | P | 14 | 1-30 |  |  | 6 | [6 empty] | Open - No Action
488140 | C10568 | 2021-05-30 | 2021-09-21 | AC-4980-01 | 40 | 95.01 | 3800.4 | P | 263 | 90+ | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
488428 | C10530 | 2021-12-10 | 2022-03-30 | AC-4980-01 | 57 | 67.05 | 3821.85 | P | 73 | 61-90 | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
488806 | C10860 | 2021-12-31 | 2022-04-06 | AC-4980-01 | 55 | 69.16 | 3803.8 | P | 66 | 61-90 | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
488648 | C10706 | 2022-02-24 | 2022-04-20 | AC-4980-01 | 43 | 44.57 | 1916.51 | P | 52 | 31-60 | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
488829 | C10568 | 2022-01-10 | 2022-04-30 | AC-4980-01 | 32 | 68.68 | 2197.76 | P | 42 | 31-60 | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
487837 | C10560 | 2021-07-23 | 2021-10-06 | AC-5066-03 | 25 | 84.33 | 2108.25 | P | 248 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
487453 | C10332 | 2021-11-06 | 2022-03-20 | AC-5066-03 | 39 | 138.5 | 5401.5 | P | 83 | 61-90 | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
488514 | C10316 | 2022-01-07 | 2022-03-24 | AC-5066-03 | 12 | 108.83 | 1305.96 | P | 79 | 61-90 | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
488234 | C10331 | 2022-02-28 | 2022-05-11 | AC-5066-03 | 55 | 125.33 | 6893.15 | P | 31 | 31-60 | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
487488 | C10436 | 2021-03-26 | 2021-06-24 | AC-5069-03 | 38 | 132.73 | 5043.74 | P | 352 | 90+ | Engineering Hold - NCR Open |  | 2 | [6 empty] | Do Not Make
488313 | C10331 | 2021-07-26 | 2021-09-18 | AC-5069-03 | 16 | 155.86 | 2493.76 | P | 266 | 90+ | Engineering Hold - NCR Open |  | 2 | [6 empty] | Do Not Make
488404 | C10544 | 2021-09-04 | 2021-10-11 | AC-5085-05 | 5 | 54.96 | 274.8 | P | 243 | 90+ | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488721 | C10688 | 2021-08-28 | 2021-10-20 | AC-5085-05 | 33 | 177.06 | 5842.98 | P | 234 | 90+ | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488530 | C10273 | 2021-12-01 | 2022-04-09 | AC-5085-05 | 35 | 47.68 | 1668.8 | P | 63 | 61-90 | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
488337 | C10420 | 2022-02-02 | 2022-04-17 | AC-5085-05 | 10 | 114.67 | 1146.7 | P | 55 | 31-60 | Engineering Hold - Material Deviation |  | 4 | [6 empty] | Do Not Make
489268 | C10830 | 2021-09-25 | 2022-01-29 | AC-5092-02 | 29 | 128.56 | 3728.24 | P | 133 | 90+ |  |  | 2 | [6 empty] | Open - No Action
489407 | C10900 | 2021-12-09 | 2022-04-20 | AC-5092-02 | 9 | 119.3 | 1073.7 | P | 52 | 31-60 |  |  | 2 | [6 empty] | Open - No Action
489533 | C10238 | 2021-12-06 | 2022-04-03 | AC-5120-A | 38 | 61.29 | 2329.02 | P | 69 | 61-90 |  |  | 2 | [6 empty] | Open - No Action
489260 | C10688 | 2022-01-04 | 2022-05-01 | AC-5120-A | 16 | 128.99 | 2063.84 | P | 41 | 31-60 |  |  | 2 | [6 empty] | Open - No Action
489158 | C10251 | 2021-12-21 | 2022-04-07 | AC-5148-01 | 11 | 77.98 | 857.78 | P | 65 | 61-90 |  |  | 2 | [6 empty] | Open - No Action
489093 | C10806 | 2022-02-17 | 2022-04-27 | AC-5148-01 | 32 | 35 | 1120 | P | 45 | 31-60 |  |  | 2 | [6 empty] | Open - No Action
489485 | C10501 | 2022-01-07 | 2022-04-16 | AC-5424-05 | 25 | 195.09 | 4877.25 | P | 56 | 31-60 |  |  | 3 | 7711686 | 2022-01-11 | 25 | CMP-633-T | 50 | 4877.25 | Component Shortage
489660 | C10806 | 2022-03-18 | 2022-05-21 | AC-5424-05 | 19 | 94.38 | 1793.22 | P | 21 | 1-30 |  |  | 3 | [6 empty] | Open - No Action
489690 | C10455 | 2022-02-20 | 2022-06-09 | AC-5424-05 | 33 | 41.62 | 1373.46 | P | 2 | 1-30 |  |  | 3 | [6 empty] | Open - No Action
487618 | C10695 | 2021-03-07 | 2021-06-05 | AC-5486-03 | 45 | 154.7 | 6961.5 | P | 371 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
487378 | C10327 | 2021-04-03 | 2021-06-15 | AC-5486-03 | 12 | 133.3 | 1599.6 | P | 361 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
489670 | C10170 | 2022-03-24 | 2022-05-17 | AC-5686-01 | 23 | 106.2 | 2442.6 | P | 25 | 1-30 |  |  | 1 | [6 empty] | Open - No Action
487860 | C10806 | 2021-05-08 | 2021-09-13 | AC-5713-01 | 38 | 166.71 | 6334.98 | P | 271 | 90+ | Engineering Hold - First Article Rejected |  | 2 | [6 empty] | Do Not Make
488262 | C10238 | 2021-07-12 | 2021-11-23 | AC-5713-01 | 27 | 149.08 | 4025.16 | P | 200 | 90+ | Engineering Hold - First Article Rejected |  | 2 | [6 empty] | Do Not Make
488953 | C10973 | 2021-11-26 | 2022-03-30 | AC-5805-10 | 6 | 103.21 | 619.26 | P | 73 | 61-90 |  |  | 4 | [6 empty] | Open - No Action
488921 | C10787 | 2022-01-02 | 2022-04-29 | AC-5805-10 | 12 | 133.59 | 1603.08 | P | 43 | 31-60 |  |  | 4 | [6 empty] | Open - No Action
489463 | C10824 | 2022-03-02 | 2022-05-26 | AC-5805-10 | 39 | 95.58 | 3727.62 | P | 16 | 1-30 |  |  | 4 | 7710325 | 2022-03-04 | 32 |  |  | 3058.56 | WO In Progress
488955 | C10498 | 2022-03-20 | 2022-06-07 | AC-5805-10 | 19 | 106.88 | 2030.72 | P | 4 | 1-30 |  |  | 4 | 7710601 | 2022-04-01 | 14 |  |  | 1496.32 | WO In Progress
488766 | C10456 | 2021-04-23 | 2021-07-01 | AC-5901-A | 20 | 160.38 | 3207.6 | P | 345 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
487799 | C10860 | 2021-04-29 | 2021-09-11 | AC-5901-A | 59 | 162.31 | 9576.29 | P | 273 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
487676 | C10817 | 2021-03-26 | 2021-07-21 | AC-6019-B | 10 | 157.92 | 1579.2 | P | 325 | 90+ | Engineering Hold - First Article Rejected |  | 1 | [6 empty] | Do Not Make
488856 | C10501 | 2021-11-30 | 2022-01-21 | AC-6078-10 | 17 | 129.33 | 2198.61 | P | 141 | 90+ |  |  | 2 | 7710865 | 2022-06-11 | 11 |  |  | 1422.63 | WO Created (Today)
489790 | C10280 | 2022-02-13 | 2022-04-24 | AC-6078-10 | 26 | 26.13 | 679.38 | P | 48 | 31-60 |  |  | 2 | 7710005 | 2022-02-19 | 26 |  |  | 679.38 | WO In Progress
488676 | C10817 | 2021-02-28 | 2021-07-08 | AC-6102-10 | 41 | 111.55 | 4573.55 | P | 338 | 90+ | Engineering Hold - NCR Open |  | 1 | [6 empty] | Do Not Make
489381 | C10589 | 2021-11-27 | 2022-04-03 | AC-6113-02 | 32 | 54.41 | 1741.12 | P | 69 | 61-90 |  |  | 1 | [6 empty] | Open - No Action
489427 | C10746 | 2021-12-21 | 2022-03-27 | AC-6130-05 | 3 | 113.55 | 340.65 | P | 76 | 61-90 |  |  | 3 | [6 empty] | Open - No Action
489039 | C10327 | 2021-11-25 | 2022-04-11 | AC-6130-05 | 39 | 130.11 | 5074.29 | P | 61 | 61-90 |  |  | 3 | 7710807 | 2022-06-11 | 39 |  |  | 5074.29 | WO Created (Today)
489056 | C10264 | 2022-02-28 | 2022-05-05 | AC-6130-05 | 9 | 83.4 | 750.6 | P | 37 | 31-60 |  |  | 3 | [6 empty] | Open - No Action
488996 | C10238 | 2022-02-13 | 2022-05-26 | AC-6196-A | 17 | 100.03 | 1700.51 | P | 16 | 1-30 |  |  | 1 | [6 empty] | Open - No Action
489710 | C10461 | 2021-08-28 | 2021-12-24 | AC-6197-02 | 2 | 217.72 | 435.44 | P | 169 | 90+ |  |  | 3 | 7712182 | 2021-09-06 | 2 | CMP-625-S | 4 | 435.44 | Component Shortage
489264 | C10688 | 2022-01-08 | 2022-03-24 | AC-6197-02 | 22 | 63.98 | 1407.56 | P | 79 | 61-90 |  |  | 3 | 7711042 | 2022-06-11 | 10 |  |  | 639.8 | WO Created (Today)
488874 | C10316 | 2022-03-14 | 2022-04-23 | AC-6197-02 | 10 | 182.91 | 1829.1 | P | 49 | 31-60 |  |  | 3 | 7712415 | 2022-03-25 | 10 | CMP-633-T | 20 | 1829.1 | Component Shortage
487998 | C10589 | 2021-10-11 | 2022-02-04 | AC-6271-03 | 34 | 70.11 | 2383.74 | P | 127 | 90+ | Engineering Hold - First Article Rejected |  | 3 | [6 empty] | Do Not Make
487780 | C10385 | 2022-01-02 | 2022-03-22 | AC-6271-03 | 4 | 133.76 | 535.04 | P | 81 | 61-90 | Engineering Hold - First Article Rejected |  | 3 | [6 empty] | Do Not Make
488505 | C10377 | 2022-01-02 | 2022-05-14 | AC-6271-03 | 14 | 113.09 | 1583.26 | P | 28 | 1-30 | Engineering Hold - First Article Rejected |  | 3 | [6 empty] | Do Not Make
488823 | C10973 | 2021-07-28 | 2021-09-15 | AC-6493-05 | 37 | 56.56 | 2092.72 | P | 269 | 90+ | Engineering Hold - Drawing Rev Pending |  | 1 | [6 empty] | Do Not Make
489069 | C10664 | 2022-01-20 | 2022-05-09 | AC-6501-05 | 6 | 76.61 | 459.66 | P | 33 | 31-60 |  |  | 1 | [6 empty] | Open - No Action
488447 | C10951 | 2021-06-10 | 2021-09-02 | AC-6549-A | 33 | 109.84 | 3624.72 | P | 282 | 90+ | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
487986 | C10455 | 2021-09-06 | 2021-10-12 | AC-6549-A | 54 | 157.98 | 8530.92 | P | 242 | 90+ | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
487841 | C10377 | 2021-12-24 | 2022-03-24 | AC-6549-A | 21 | 173.06 | 3634.26 | P | 79 | 61-90 | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
488762 | C10951 | 2022-02-13 | 2022-04-10 | AC-6549-A | 12 | 161.43 | 1937.16 | P | 62 | 61-90 | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
488469 | C10170 | 2021-12-30 | 2022-05-09 | AC-6549-A | 20 | 105.1 | 2102 | P | 33 | 31-60 | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
489721 | C10525 | 2021-05-08 | 2021-07-06 | AC-6604-01 | 5 | 59.49 | 297.45 | P | 340 | 90+ |  |  | 1 | [6 empty] | Open - No Action
489409 | C10238 | 2021-12-27 | 2022-04-04 | AC-6614-05 | 19 | 108.3 | 2057.7 | P | 68 | 61-90 |  |  | 1 | [6 empty] | Open - No Action
489137 | C10332 | 2022-03-14 | 2022-04-18 | AC-6632-01 | 24 | 48.97 | 1175.28 | P | 54 | 31-60 |  |  | 4 | 7710451 | 2022-03-17 | 24 |  |  | 1175.28 | WO In Progress
488849 | C10706 | 2022-01-14 | 2022-04-22 | AC-6632-01 | 6 | 114.35 | 686.1 | P | 50 | 31-60 |  |  | 4 | [6 empty] | Open - No Action
489048 | C10951 | 2022-01-06 | 2022-05-23 | AC-6632-01 | 37 | 108.99 | 4032.63 | P | 19 | 1-30 |  |  | 4 | [6 empty] | Open - No Action
489455 | C10525 | 2022-01-13 | 2022-06-02 | AC-6632-01 | 2 | 78.75 | 157.5 | P | 9 | 1-30 |  |  | 4 | [6 empty] | Open - No Action
488903 | C10211 | 2021-06-25 | 2021-10-10 | AC-6670-10 | 19 | 59.52 | 1130.88 | P | 244 | 90+ |  |  | 2 | [6 empty] | Open - No Action
489791 | C10940 | 2022-04-24 | 2022-06-03 | AC-6670-10 | 25 | 69.87 | 1746.75 | P | 8 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
489546 | C10456 | 2022-04-04 | 2022-06-09 | AC-6682-10 | 36 | 71.54 | 2575.44 | P | 2 | 1-30 |  |  | 1 | 7711223 | 2022-06-11 | 25 |  |  | 1788.5 | WO Created (Today)
487578 | C10951 | 2021-05-02 | 2021-06-24 | AC-6702-02 | 36 | 178.49 | 6425.64 | P | 352 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
487885 | C10252 | 2021-11-18 | 2022-01-05 | AC-6702-02 | 6 | 41.45 | 248.7 | P | 157 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
487566 | C10385 | 2022-04-20 | 2022-06-07 | AC-6702-02 | 49 | 135.77 | 6652.73 | P | 4 | 1-30 | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
489183 | C10950 | 2021-11-24 | 2022-04-05 | AC-6706-05 | 26 | 127.13 | 3305.38 | P | 67 | 61-90 |  |  | 1 | 7711204 | 2022-06-11 | 26 |  |  | 3305.38 | WO Created (Today)
489503 | C10436 | 2021-05-03 | 2021-06-21 | AC-6713-10 | 35 | 98.93 | 3462.55 | P | 355 | 90+ |  |  | 3 | 7710860 | 2022-06-11 | 19 |  |  | 1879.67 | WO Created (Today)
489603 | C10461 | 2021-12-22 | 2022-04-04 | AC-6713-10 | 34 | 132.88 | 4517.92 | P | 68 | 61-90 |  |  | 3 | 7711915 | 2021-12-25 | 34 | CMP-734-T | 68 | 4517.92 | Component Shortage
488931 | C10664 | 2022-02-26 | 2022-05-21 | AC-6713-10 | 14 | 119.87 | 1678.18 | P | 21 | 1-30 |  |  | 3 | 7711092 | 2022-06-11 | 14 |  |  | 1678.18 | WO Created (Today)
488403 | C10824 | 2021-01-25 | 2021-06-10 | AC-6792-B | 45 | 82.77 | 3724.65 | P | 366 | 90+ | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
488508 | C10211 | 2021-08-30 | 2021-10-01 | AC-6792-B | 4 | 53.29 | 213.16 | P | 253 | 90+ | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
488147 | C10170 | 2021-12-16 | 2022-03-23 | AC-6792-B | 38 | 85.06 | 3232.28 | P | 80 | 61-90 | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
488301 | C10746 | 2022-03-06 | 2022-04-09 | AC-6792-B | 43 | 137.73 | 5922.39 | P | 63 | 61-90 | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
487727 | C10973 | 2021-12-05 | 2022-04-24 | AC-6792-B | 60 | 126.47 | 7588.2 | P | 48 | 31-60 | Engineering Hold - Customer Spec Change |  | 5 | [6 empty] | Do Not Make
487734 | C10695 | 2021-08-20 | 2021-12-13 | AC-6827-05 | 39 | 161.74 | 6307.86 | P | 180 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488203 | C10695 | 2021-11-18 | 2022-01-28 | AC-6827-05 | 27 | 175.15 | 4729.05 | P | 134 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487610 | C10544 | 2022-01-28 | 2022-04-15 | AC-6827-05 | 17 | 126.4 | 2148.8 | P | 57 | 31-60 | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488647 | C10951 | 2022-01-25 | 2022-04-21 | AC-6827-05 | 45 | 135.57 | 6100.65 | P | 51 | 31-60 | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
489436 | C10900 | 2022-02-05 | 2022-04-01 | AC-6854-01 | 34 | 116.83 | 3972.22 | P | 71 | 61-90 |  |  | 2 | [6 empty] | Open - No Action
489718 | C10436 | 2022-02-01 | 2022-05-31 | AC-6854-01 | 40 | 171.93 | 6877.2 | P | 11 | 1-30 |  |  | 2 | 7712442 | 2022-02-12 | 40 | CMP-633-T | 40 | 6877.2 | Component Shortage
489642 | C10951 | 2022-01-07 | 2022-03-21 | AC-6859-A | 8 | 152.05 | 1216.4 | P | 82 | 61-90 |  |  | 2 | 7711925 | 2022-01-16 | 8 | CMP-625-S | 16 | 1216.4 | Component Shortage
489181 | C10331 | 2021-11-17 | 2022-03-30 | AC-6859-A | 24 | 39.1 | 938.4 | P | 73 | 61-90 |  |  | 2 | [6 empty] | Open - No Action
488380 | C10170 | 2022-01-11 | 2022-05-07 | AC-6861-01 | 10 | 101.1 | 1011 | P | 35 | 31-60 | Engineering Hold - NCR Open |  | 1 | [6 empty] | Do Not Make
489282 | C10501 | 2022-01-14 | 2022-05-30 | AC-6921-B | 22 | 105.98 | 2331.56 | P | 12 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
489703 | C10264 | 2022-04-07 | 2022-06-10 | AC-6921-B | 6 | 45.42 | 272.52 | P | 1 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
488637 | C10455 | 2021-08-09 | 2021-11-18 | AC-7019-10 | 42 | 148.83 | 6250.86 | P | 205 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
487906 | C10752 | 2022-02-09 | 2022-05-08 | AC-7019-10 | 16 | 129.52 | 2072.32 | P | 34 | 31-60 | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
488055 | C10264 | 2021-10-02 | 2021-12-11 | AC-7062-10 | 22 | 131.57 | 2894.54 | P | 182 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
488167 | C10321 | 2022-01-15 | 2022-04-13 | AC-7062-10 | 13 | 60.42 | 785.46 | P | 59 | 31-60 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
488713 | C10852 | 2021-03-23 | 2021-08-07 | AC-7108-10 | 41 | 149.6 | 6133.6 | P | 308 | 90+ | Engineering Hold - Drawing Rev Pending |  | 3 | [6 empty] | Do Not Make
488539 | C10280 | 2021-12-09 | 2022-04-05 | AC-7108-10 | 42 | 176.99 | 7433.58 | P | 67 | 61-90 | Engineering Hold - Drawing Rev Pending |  | 3 | [6 empty] | Do Not Make
488278 | C10526 | 2022-04-05 | 2022-05-31 | AC-7108-10 | 45 | 78.37 | 3526.65 | P | 11 | 1-30 | Engineering Hold - Drawing Rev Pending |  | 3 | [6 empty] | Do Not Make
488091 | C10695 | 2021-06-14 | 2021-07-29 | AC-7176-02 | 31 | 120.18 | 3725.58 | P | 317 | 90+ | Engineering Hold - First Article Rejected |  | 2 | [6 empty] | Do Not Make
488571 | C10251 | 2022-04-07 | 2022-05-19 | AC-7176-02 | 9 | 131.98 | 1187.82 | P | 23 | 1-30 | Engineering Hold - First Article Rejected |  | 2 | [6 empty] | Do Not Make
487390 | C10936 | 2021-10-12 | 2021-11-24 | AC-7219-A | 58 | 88.07 | 5108.06 | P | 199 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487563 | C10824 | 2021-08-26 | 2021-12-15 | AC-7219-A | 44 | 58.25 | 2563 | P | 178 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487399 | C10664 | 2021-12-20 | 2022-02-26 | AC-7219-A | 17 | 87.91 | 1494.47 | P | 105 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488276 | C10695 | 2021-12-25 | 2022-03-20 | AC-7219-A | 44 | 111.77 | 4917.88 | P | 83 | 61-90 | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488623 | C10456 | 2021-08-24 | 2021-11-07 | AC-7338-02 | 11 | 120.01 | 1320.11 | P | 216 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
487584 | C10544 | 2021-12-16 | 2022-03-30 | AC-7338-02 | 50 | 84.56 | 4228 | P | 73 | 61-90 | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
489581 | C10752 | 2022-01-20 | 2022-03-09 | AC-7348-02 | 29 | 133.25 | 3864.25 | P | 94 | 90+ |  |  | 2 | [6 empty] | Open - No Action
489515 | C10455 | 2021-12-24 | 2022-03-28 | AC-7348-02 | 16 | 116 | 1856 | P | 75 | 61-90 |  |  | 2 | [6 empty] | Open - No Action
487721 | C10966 | 2021-03-22 | 2021-06-10 | AC-7375-B | 20 | 109.54 | 2190.8 | P | 366 | 90+ | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
487544 | C10568 | 2021-05-15 | 2021-07-27 | AC-7375-B | 19 | 125.91 | 2392.29 | P | 319 | 90+ | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
487975 | C10951 | 2022-01-15 | 2022-02-17 | AC-7375-B | 15 | 78.66 | 1179.9 | P | 114 | 90+ | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
487978 | C10706 | 2022-02-21 | 2022-04-13 | AC-7375-B | 16 | 70.74 | 1131.84 | P | 59 | 31-60 | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
488172 | C10973 | 2022-01-23 | 2022-04-17 | AC-7375-B | 34 | 114.74 | 3901.16 | P | 55 | 31-60 | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
487796 | C10264 | 2021-04-12 | 2021-08-29 | AC-7397-01 | 4 | 113.27 | 453.08 | P | 286 | 90+ | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
488318 | C10186 | 2021-11-23 | 2022-01-14 | AC-7397-01 | 60 | 168.34 | 10100.4 | P | 148 | 90+ | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
488656 | C10170 | 2022-01-11 | 2022-04-12 | AC-7397-01 | 49 | 134.06 | 6568.94 | P | 60 | 31-60 | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
488800 | C10498 | 2022-03-13 | 2022-05-22 | AC-7397-01 | 27 | 87.39 | 2359.53 | P | 20 | 1-30 | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
488329 | C10170 | 2021-03-21 | 2021-06-25 | AC-7457-B | 25 | 96.81 | 2420.25 | P | 351 | 90+ | Engineering Hold - First Article Rejected |  | 6 | [6 empty] | Do Not Make
487493 | C10688 | 2021-07-13 | 2021-08-25 | AC-7457-B | 59 | 154.56 | 9119.04 | P | 290 | 90+ | Engineering Hold - First Article Rejected |  | 6 | [6 empty] | Do Not Make
488710 | C10170 | 2021-05-16 | 2021-09-11 | AC-7457-B | 20 | 130.13 | 2602.6 | P | 273 | 90+ | Engineering Hold - First Article Rejected |  | 6 | [6 empty] | Do Not Make
487683 | C10498 | 2021-11-02 | 2022-02-10 | AC-7457-B | 19 | 133.23 | 2531.37 | P | 121 | 90+ | Engineering Hold - First Article Rejected |  | 6 | [6 empty] | Do Not Make
488207 | C10746 | 2022-01-07 | 2022-04-17 | AC-7457-B | 21 | 50.05 | 1051.05 | P | 55 | 31-60 | Engineering Hold - First Article Rejected |  | 6 | [6 empty] | Do Not Make
487877 | C10950 | 2022-01-07 | 2022-05-13 | AC-7457-B | 39 | 87 | 3393 | P | 29 | 1-30 | Engineering Hold - First Article Rejected |  | 6 | [6 empty] | Do Not Make
487550 | C10568 | 2021-05-07 | 2021-08-24 | AC-7555-03 | 26 | 173.42 | 4508.92 | P | 291 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487717 | C10238 | 2021-11-04 | 2021-12-27 | AC-7555-03 | 8 | 169.24 | 1353.92 | P | 166 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487533 | C10806 | 2021-11-27 | 2022-02-22 | AC-7555-03 | 16 | 153.99 | 2463.84 | P | 109 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
488970 | C10530 | 2022-01-21 | 2022-05-06 | AC-7567-01 | 39 | 93.03 | 3628.17 | P | 36 | 31-60 |  |  | 1 | 7710653 | 2022-06-11 | 39 |  |  | 3628.17 | WO Created (Today)
487516 | C10830 | 2021-06-01 | 2021-07-07 | AC-7572-B | 34 | 51.99 | 1767.66 | P | 339 | 90+ | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
488368 | C10817 | 2021-08-29 | 2021-11-05 | AC-7572-B | 47 | 40.83 | 1919.01 | P | 218 | 90+ | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
488137 | C10316 | 2021-09-23 | 2021-12-16 | AC-7572-B | 60 | 53.32 | 3199.2 | P | 177 | 90+ | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
488385 | C10519 | 2022-01-12 | 2022-04-20 | AC-7572-B | 21 | 159.21 | 3343.41 | P | 52 | 31-60 | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
488046 | C10746 | 2022-04-18 | 2022-05-21 | AC-7572-B | 29 | 54.98 | 1594.42 | P | 21 | 1-30 | Engineering Hold - NCR Open |  | 5 | [6 empty] | Do Not Make
488412 | C10746 | 2021-06-08 | 2021-07-24 | AC-7582-02 | 11 | 79.31 | 872.41 | P | 322 | 90+ | Engineering Hold - Drawing Rev Pending |  | 2 | [6 empty] | Do Not Make
488126 | C10252 | 2021-07-27 | 2021-12-03 | AC-7582-02 | 44 | 73.08 | 3215.52 | P | 190 | 90+ | Engineering Hold - Drawing Rev Pending |  | 2 | [6 empty] | Do Not Make
489199 | C10688 | 2022-02-24 | 2022-06-06 | AC-7644-B | 21 | 105.52 | 2215.92 | P | 5 | 1-30 |  |  | 1 | 7712079 | 2022-03-01 | 21 | CMP-503-F | 84 | 2215.92 | Component Shortage
487528 | C10461 | 2021-10-21 | 2022-02-07 | AC-7794-A | 36 | 103.02 | 3708.72 | P | 124 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487824 | C10526 | 2021-11-09 | 2022-03-01 | AC-7794-A | 54 | 140.35 | 7578.9 | P | 102 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487900 | C10852 | 2022-04-13 | 2022-05-29 | AC-7794-A | 20 | 158.47 | 3169.4 | P | 13 | 1-30 | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
489085 | C10331 | 2022-03-20 | 2022-06-05 | AC-7811-02 | 23 | 131.82 | 3031.86 | P | 6 | 1-30 |  |  | 1 | [6 empty] | Open - No Action
487846 | C10824 | 2021-11-20 | 2022-02-19 | AC-7879-05 | 53 | 166.09 | 8802.77 | P | 112 | 90+ | Engineering Hold - Material Deviation |  | 1 | [6 empty] | Do Not Make
489352 | C10787 | 2021-10-26 | 2021-12-27 | AC-7894-02 | 8 | 88.17 | 705.36 | P | 166 | 90+ |  |  | 2 | [6 empty] | Open - No Action
489532 | C10951 | 2021-12-28 | 2022-03-24 | AC-7894-02 | 22 | 288.29 | 6342.38 | P | 79 | 61-90 |  |  | 2 | 7711345 | 2022-01-01 | 22 | CMP-382-F | 22 | 6342.38 | Component Shortage
489519 | C10758 | 2022-03-10 | 2022-04-14 | AC-7933-10 | 3 | 133.82 | 401.46 | P | 58 | 31-60 |  | Over Credit Limit | 2 | [6 empty] | Credit Hold
489736 | C10327 | 2022-04-23 | 2022-05-25 | AC-7933-10 | 21 | 189.85 | 3986.85 | P | 17 | 1-30 |  |  | 2 | 7712022 | 2022-05-03 | 21 | CMP-512-R | 84 | 3986.85 | Component Shortage
489458 | C10830 | 2022-03-23 | 2022-05-20 | AC-7953-A | 17 | 59.85 | 1017.45 | P | 22 | 1-30 |  |  | 2 | 7710090 | 2022-04-02 | 8 |  |  | 478.8 | WO In Progress
489607 | C10251 | 2022-04-22 | 2022-06-09 | AC-7953-A | 14 | 125.44 | 1756.16 | P | 2 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
489664 | C10752 | 2022-01-02 | 2022-03-31 | AC-7956-01 | 36 | 112.97 | 4066.92 | P | 72 | 61-90 |  |  | 3 | [6 empty] | Open - No Action
488946 | C10544 | 2021-12-12 | 2022-04-10 | AC-7956-01 | 21 | 113.58 | 2385.18 | P | 62 | 61-90 |  |  | 3 | [6 empty] | Open - No Action
489745 | C10746 | 2022-04-17 | 2022-05-18 | AC-7956-01 | 6 | 112.93 | 677.58 | P | 24 | 1-30 |  |  | 3 | 7710922 | 2022-06-11 | 6 |  |  | 677.58 | WO Created (Today)
488352 | C10280 | 2022-01-21 | 2022-03-24 | AC-8035-02 | 37 | 58.74 | 2173.38 | P | 79 | 61-90 | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488489 | C10455 | 2021-12-19 | 2022-04-28 | AC-8035-02 | 32 | 76.01 | 2432.32 | P | 44 | 31-60 | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488113 | C10498 | 2022-01-16 | 2022-05-28 | AC-8035-02 | 26 | 179.75 | 4673.5 | P | 14 | 1-30 | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
489479 | C10501 | 2021-09-25 | 2021-11-12 | AC-8100-02 | 40 | 77.4 | 3096 | P | 211 | 90+ |  |  | 2 | [6 empty] | Open - No Action
488869 | C10940 | 2022-02-14 | 2022-05-27 | AC-8100-02 | 25 | 25.85 | 646.25 | P | 15 | 1-30 |  |  | 2 | 7710604 | 2022-02-24 | 20 |  |  | 517 | WO In Progress
488361 | C10461 | 2021-09-23 | 2022-02-10 | AC-8194-03 | 40 | 166.93 | 6677.2 | P | 121 | 90+ | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487402 | C10589 | 2022-02-04 | 2022-03-24 | AC-8194-03 | 5 | 73.8 | 369 | P | 79 | 61-90 | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
487542 | C10281 | 2021-12-27 | 2022-03-30 | AC-8194-03 | 22 | 167.84 | 3692.48 | P | 73 | 61-90 | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
488693 | C10251 | 2022-02-21 | 2022-06-08 | AC-8194-03 | 46 | 78.07 | 3591.22 | P | 3 | 1-30 | Engineering Hold - First Article Rejected |  | 4 | [6 empty] | Do Not Make
489364 | C10264 | 2021-12-19 | 2022-04-21 | AC-8302-05 | 6 | 80.37 | 482.22 | P | 51 | 31-60 |  |  | 2 | [6 empty] | Open - No Action
489420 | C10695 | 2022-01-24 | 2022-05-14 | AC-8302-05 | 13 | 77.85 | 1012.05 | P | 28 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
488625 | C10817 | 2022-01-26 | 2022-02-28 | AC-8328-B | 44 | 82.7 | 3638.8 | P | 103 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
487466 | C10519 | 2022-02-25 | 2022-04-07 | AC-8328-B | 54 | 88.33 | 4769.82 | P | 65 | 61-90 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
489542 | C10498 | 2022-01-16 | 2022-04-13 | AC-8338-01 | 39 | 113.38 | 4421.82 | P | 59 | 31-60 |  |  | 4 | [6 empty] | Open - No Action
489757 | C10280 | 2022-02-08 | 2022-05-22 | AC-8338-01 | 31 | 123.44 | 3826.64 | P | 20 | 1-30 |  |  | 4 | [6 empty] | Open - No Action
489495 | C10746 | 2022-03-01 | 2022-06-02 | AC-8338-01 | 25 | 102.6 | 2565 | P | 9 | 1-30 |  |  | 4 | 7710208 | 2022-03-03 | 15 |  |  | 1539 | WO In Progress
488969 | C10706 | 2022-03-15 | 2022-06-06 | AC-8338-01 | 23 | 59.13 | 1359.99 | P | 5 | 1-30 |  |  | 4 | [6 empty] | Open - No Action
489061 | C10530 | 2021-05-19 | 2021-10-01 | AC-8393-03 | 18 | 103.23 | 1858.14 | P | 253 | 90+ |  |  | 1 | [6 empty] | Open - No Action
487739 | C10786 | 2021-06-17 | 2021-08-28 | AC-8440-03 | 36 | 80.41 | 2894.76 | P | 287 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
488033 | C10252 | 2021-05-22 | 2021-09-27 | AC-8440-03 | 30 | 79.06 | 2371.8 | P | 257 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
488249 | C10526 | 2021-09-22 | 2022-01-04 | AC-8440-03 | 54 | 42.12 | 2274.48 | P | 158 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
487905 | C10455 | 2021-11-07 | 2022-01-28 | AC-8440-03 | 6 | 74.71 | 448.26 | P | 134 | 90+ | Engineering Hold - Customer Spec Change |  | 4 | [6 empty] | Do Not Make
489489 | C10211 | 2021-09-13 | 2021-11-14 | AC-8463-05 | 37 | 74.83 | 2768.71 | P | 209 | 90+ |  |  | 4 | [6 empty] | Open - No Action
488988 | C10281 | 2022-01-13 | 2022-04-04 | AC-8463-05 | 7 | 58.13 | 406.91 | P | 68 | 61-90 |  |  | 4 | [6 empty] | Open - No Action
489694 | C10461 | 2022-02-16 | 2022-04-23 | AC-8463-05 | 31 | 116.54 | 3612.74 | P | 49 | 31-60 |  |  | 4 | [6 empty] | Open - No Action
489232 | C10170 | 2022-01-11 | 2022-05-19 | AC-8463-05 | 3 | 56.29 | 168.87 | P | 23 | 1-30 |  |  | 4 | [6 empty] | Open - No Action
487525 | C10350 | 2021-09-18 | 2022-01-02 | AC-8498-A | 28 | 129.23 | 3618.44 | P | 160 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488225 | C10526 | 2021-10-06 | 2022-02-13 | AC-8498-A | 30 | 158.14 | 4744.2 | P | 118 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
487774 | C10519 | 2022-02-16 | 2022-04-07 | AC-8498-A | 35 | 124.72 | 4365.2 | P | 65 | 61-90 | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488494 | C10498 | 2021-08-13 | 2021-10-09 | AC-8508-03 | 48 | 113.29 | 5437.92 | P | 245 | 90+ | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
488640 | C10273 | 2021-11-26 | 2022-03-27 | AC-8508-03 | 47 | 116.22 | 5462.34 | P | 76 | 61-90 | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
488604 | C10830 | 2021-12-26 | 2022-04-14 | AC-8508-03 | 57 | 148.69 | 8475.33 | P | 58 | 31-60 | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
487695 | C10560 | 2022-01-01 | 2022-04-19 | AC-8508-03 | 34 | 135.09 | 4593.06 | P | 53 | 31-60 | Engineering Hold - NCR Open |  | 4 | [6 empty] | Do Not Make
487372 | C10746 | 2021-06-20 | 2021-09-18 | AC-8535-05 | 51 | 105.98 | 5404.98 | P | 266 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
488015 | C10830 | 2021-08-24 | 2022-01-08 | AC-8535-05 | 48 | 59.29 | 2845.92 | P | 154 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
489656 | C10327 | 2021-11-25 | 2022-03-28 | AC-8653-01 | 7 | 126.18 | 883.26 | P | 75 | 61-90 |  |  | 5 | 7710186 | 2021-12-06 | 7 |  |  | 883.26 | WO In Progress
489401 | C10530 | 2021-12-19 | 2022-04-08 | AC-8653-01 | 24 | 79.82 | 1915.68 | P | 64 | 61-90 |  |  | 5 | [6 empty] | Open - No Action
489120 | C10752 | 2022-01-02 | 2022-04-09 | AC-8653-01 | 35 | 45.13 | 1579.55 | P | 63 | 61-90 |  |  | 5 | [6 empty] | Open - No Action
489425 | C10436 | 2022-01-31 | 2022-05-02 | AC-8653-01 | 27 | 28.3 | 764.1 | P | 40 | 31-60 |  |  | 5 | [6 empty] | Open - No Action
489016 | C10695 | 2022-03-13 | 2022-05-03 | AC-8653-01 | 16 | 29.85 | 477.6 | P | 39 | 31-60 |  |  | 5 | 7710695 | 2022-06-11 | 16 |  |  | 477.6 | WO Created (Today)
489678 | C10238 | 2021-12-23 | 2022-04-22 | AC-8656-05 | 28 | 173.36 | 4854.08 | P | 50 | 31-60 |  |  | 1 | 7711549 | 2022-01-03 | 28 | CMP-512-T | 28 | 4854.08 | Component Shortage
487374 | C10350 | 2021-07-09 | 2021-10-03 | AC-8665-02 | 15 | 74.19 | 1112.85 | P | 251 | 90+ | Engineering Hold - First Article Rejected |  | 3 | [6 empty] | Do Not Make
488365 | C10940 | 2021-11-22 | 2022-03-17 | AC-8665-02 | 39 | 94.1 | 3669.9 | P | 86 | 61-90 | Engineering Hold - First Article Rejected |  | 3 | [6 empty] | Do Not Make
488833 | C10281 | 2021-12-14 | 2022-03-24 | AC-8665-02 | 4 | 76.56 | 306.24 | P | 79 | 61-90 | Engineering Hold - First Article Rejected |  | 3 | [6 empty] | Do Not Make
489623 | C10501 | 2021-11-20 | 2022-03-23 | AC-8805-01 | 29 | 53.15 | 1541.35 | P | 80 | 61-90 |  |  | 4 | 7711109 | 2022-06-11 | 29 |  |  | 1541.35 | WO Created (Today)
488897 | C10281 | 2022-01-10 | 2022-04-14 | AC-8805-01 | 38 | 117.48 | 4464.24 | P | 58 | 31-60 |  |  | 4 | 7710852 | 2022-06-11 | 27 |  |  | 3171.96 | WO Created (Today)
489674 | C10305 | 2022-04-01 | 2022-05-06 | AC-8805-01 | 12 | 83.94 | 1007.28 | P | 36 | 31-60 |  | Over Credit Limit | 4 | [6 empty] | Credit Hold
489802 | C10973 | 2022-04-06 | 2022-05-19 | AC-8805-01 | 24 | 45.52 | 1092.48 | P | 23 | 1-30 |  |  | 4 | [6 empty] | Open - No Action
487441 | C10860 | 2021-05-10 | 2021-07-19 | AC-8814-03 | 54 | 62.93 | 3398.22 | P | 327 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
487691 | C10664 | 2021-08-21 | 2021-12-15 | AC-8814-03 | 15 | 106.79 | 1601.85 | P | 178 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488616 | C10519 | 2021-10-23 | 2022-01-15 | AC-8814-03 | 38 | 76.66 | 2913.08 | P | 147 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
487790 | C10786 | 2021-08-23 | 2021-11-28 | AC-8827-A | 49 | 42.73 | 2093.77 | P | 195 | 90+ | Engineering Hold - Drawing Rev Pending |  | 1 | [6 empty] | Do Not Make
488850 | C10281 | 2022-01-23 | 2022-04-17 | AC-8865-01 | 31 | 104.9 | 3251.9 | P | 55 | 31-60 |  |  | 2 | 7710627 | 2022-02-03 | 31 |  |  | 3251.9 | WO In Progress
489526 | C10305 | 2022-01-05 | 2022-05-08 | AC-8865-01 | 17 | 167.41 | 2845.97 | P | 34 | 31-60 |  | Over Credit Limit | 2 | [6 empty] | Credit Hold
489578 | C10332 | 2022-04-07 | 2022-05-10 | AC-8965-05 | 24 | 96.51 | 2316.24 | P | 32 | 31-60 |  |  | 1 | 7710027 | 2022-04-13 | 24 |  |  | 2316.24 | WO In Progress
487589 | C10498 | 2021-04-05 | 2021-08-21 | AC-8994-B | 52 | 112.33 | 5841.16 | P | 294 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487383 | C10706 | 2021-06-28 | 2021-09-14 | AC-8994-B | 34 | 57.63 | 1959.42 | P | 270 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487646 | C10664 | 2021-12-26 | 2022-01-24 | AC-8994-B | 33 | 169.14 | 5581.62 | P | 138 | 90+ | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
488257 | C10327 | 2021-11-16 | 2022-03-22 | AC-8994-B | 27 | 139.39 | 3763.53 | P | 81 | 61-90 | Engineering Hold - Drawing Rev Pending |  | 4 | [6 empty] | Do Not Make
487967 | C10824 | 2021-07-18 | 2021-09-17 | AC-9025-05 | 46 | 95.52 | 4393.92 | P | 267 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488730 | C10852 | 2021-09-20 | 2021-11-21 | AC-9025-05 | 51 | 106.1 | 5411.1 | P | 202 | 90+ | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
487704 | C10786 | 2021-12-13 | 2022-04-20 | AC-9025-05 | 16 | 83.45 | 1335.2 | P | 52 | 31-60 | Engineering Hold - Customer Spec Change |  | 3 | [6 empty] | Do Not Make
488744 | C10951 | 2021-03-26 | 2021-07-03 | AC-9084-10 | 26 | 161.47 | 4198.22 | P | 343 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
488067 | C10321 | 2021-10-10 | 2022-01-25 | AC-9084-10 | 50 | 129.8 | 6490 | P | 137 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
489238 | C10252 | 2021-11-13 | 2021-12-17 | AC-9101-02 | 38 | 53.62 | 2037.56 | P | 176 | 90+ |  |  | 1 | [6 empty] | Open - No Action
488499 | C10526 | 2021-03-05 | 2021-07-05 | AC-9141-03 | 32 | 70.47 | 2255.04 | P | 341 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487708 | C10264 | 2021-09-12 | 2021-12-09 | AC-9141-03 | 42 | 122.53 | 5146.26 | P | 184 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
488733 | C10519 | 2021-08-30 | 2021-12-16 | AC-9141-03 | 29 | 135.31 | 3923.99 | P | 177 | 90+ | Engineering Hold - Material Deviation |  | 3 | [6 empty] | Do Not Make
487857 | C10664 | 2021-10-12 | 2022-02-02 | AC-9206-05 | 14 | 121.62 | 1702.68 | P | 129 | 90+ | Engineering Hold - Drawing Rev Pending |  | 3 | [6 empty] | Do Not Make
487910 | C10860 | 2021-12-08 | 2022-03-22 | AC-9206-05 | 25 | 101.27 | 2531.75 | P | 81 | 61-90 | Engineering Hold - Drawing Rev Pending |  | 3 | [6 empty] | Do Not Make
487437 | C10170 | 2022-02-14 | 2022-05-26 | AC-9206-05 | 39 | 173.67 | 6773.13 | P | 16 | 1-30 | Engineering Hold - Drawing Rev Pending |  | 3 | [6 empty] | Do Not Make
488984 | C10186 | 2022-01-08 | 2022-04-18 | AC-9217-10 | 28 | 115.26 | 3227.28 | P | 54 | 31-60 |  |  | 1 | 7710769 | 2022-06-11 | 28 |  |  | 3227.28 | WO Created (Today)
489128 | C10530 | 2021-11-28 | 2022-02-08 | AC-9241-02 | 24 | 100.87 | 2420.88 | P | 123 | 90+ |  |  | 1 | [6 empty] | Open - No Action
488216 | C10256 | 2021-07-23 | 2021-09-08 | AC-9246-03 | 15 | 69.67 | 1045.05 | P | 276 | 90+ | Engineering Hold - First Article Rejected |  | 1 | [6 empty] | Do Not Make
487938 | C10560 | 2021-04-15 | 2021-07-15 | AC-9290-02 | 6 | 144.53 | 867.18 | P | 331 | 90+ | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
488061 | C10498 | 2021-12-23 | 2022-04-15 | AC-9290-02 | 44 | 171.99 | 7567.56 | P | 57 | 31-60 | Engineering Hold - Customer Spec Change |  | 2 | [6 empty] | Do Not Make
488238 | C10498 | 2021-08-30 | 2021-10-04 | AC-9332-01 | 50 | 68.4 | 3420 | P | 250 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488740 | C10377 | 2021-09-19 | 2021-12-30 | AC-9332-01 | 19 | 144.35 | 2742.65 | P | 163 | 90+ | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
488399 | C10786 | 2022-02-24 | 2022-05-08 | AC-9332-01 | 15 | 97.42 | 1461.3 | P | 34 | 31-60 | Engineering Hold - NCR Open |  | 3 | [6 empty] | Do Not Make
489775 | C10251 | 2021-11-14 | 2022-03-16 | AC-9385-03 | 34 | 167.64 | 5699.76 | P | 87 | 61-90 |  |  | 2 | 7711892 | 2021-11-23 | 34 | CMP-685-R | 68 | 5699.76 | Component Shortage
489671 | C10966 | 2022-02-07 | 2022-05-26 | AC-9385-03 | 34 | 87.34 | 2969.56 | P | 16 | 1-30 |  |  | 2 | [6 empty] | Open - No Action
488097 | C10222 | 2021-06-08 | 2021-07-24 | AC-9448-05 | 4 | 70.75 | 283 | P | 322 | 90+ | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
487999 | C10544 | 2021-08-16 | 2021-11-30 | AC-9448-05 | 24 | 158.12 | 3794.88 | P | 193 | 90+ | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
488286 | C10251 | 2021-12-20 | 2022-02-12 | AC-9448-05 | 54 | 124.7 | 6733.8 | P | 119 | 90+ | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
488222 | C10752 | 2022-01-05 | 2022-03-27 | AC-9448-05 | 42 | 105.52 | 4431.84 | P | 76 | 61-90 | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
487367 | C10211 | 2022-02-28 | 2022-04-21 | AC-9448-05 | 25 | 131.8 | 3295 | P | 51 | 31-60 | Engineering Hold - Drawing Rev Pending |  | 5 | [6 empty] | Do Not Make
488683 | C10786 | 2021-09-08 | 2021-10-27 | AC-9453-B | 49 | 132.68 | 6501.32 | P | 227 | 90+ | Engineering Hold - Customer Spec Change |  | 1 | [6 empty] | Do Not Make
489113 | C10852 | 2021-06-24 | 2021-08-23 | AC-9458-05 | 39 | 74.75 | 2915.25 | P | 292 | 90+ |  |  | 1 | [6 empty] | Open - No Action
489195 | C10249 | 2021-03-18 | 2021-06-10 | AC-9577-02 | 23 | 140.23 | 3225.29 | P | 366 | 90+ |  | Over Credit Limit | 2 | [6 empty] | Credit Hold
488871 | C10544 | 2022-02-07 | 2022-05-10 | AC-9577-02 | 39 | 97.88 | 3817.32 | P | 32 | 31-60 |  |  | 2 | [6 empty] | Open - No Action
489358 | C10377 | 2021-07-15 | 2021-08-22 | AC-9591-03 | 22 | 68.55 | 1508.1 | P | 293 | 90+ |  |  | 5 | [6 empty] | Open - No Action
488891 | C10519 | 2022-03-12 | 2022-04-17 | AC-9591-03 | 22 | 111.23 | 2447.06 | P | 55 | 31-60 |  |  | 5 | [6 empty] | Open - No Action
488985 | C10238 | 2022-03-15 | 2022-05-22 | AC-9591-03 | 33 | 122.25 | 4034.25 | P | 20 | 1-30 |  |  | 5 | [6 empty] | Open - No Action
488862 | C10560 | 2022-03-27 | 2022-06-02 | AC-9591-03 | 28 | 85.11 | 2383.08 | P | 9 | 1-30 |  |  | 5 | 7710948 | 2022-06-11 | 28 |  |  | 2383.08 | WO Created (Today)
489076 | C10900 | 2022-03-17 | 2022-06-03 | AC-9591-03 | 2 | 54.92 | 109.84 | P | 8 | 1-30 |  |  | 5 | [6 empty] | Open - No Action
489510 | C10316 | 2022-01-06 | 2022-05-16 | AC-9622-10 | 23 | 96.67 | 2223.41 | P | 26 | 1-30 |  |  | 1 | 7711879 | 2022-01-18 | 23 | CMP-535-F | 46 | 2223.41 | Component Shortage
488023 | C10350 | 2021-08-31 | 2021-12-24 | AC-9688-B | 28 | 155.42 | 4351.76 | P | 169 | 90+ | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
488521 | C10519 | 2022-01-27 | 2022-04-10 | AC-9688-B | 19 | 111.67 | 2121.73 | P | 62 | 61-90 | Engineering Hold - Material Deviation |  | 2 | [6 empty] | Do Not Make
488928 | C10852 | 2021-09-29 | 2021-12-06 | AC-9720-A | 19 | 84.65 | 1608.35 | P | 187 | 90+ |  |  | 3 | [6 empty] | Open - No Action
488939 | C10316 | 2022-01-14 | 2022-04-03 | AC-9720-A | 19 | 66.92 | 1271.48 | P | 69 | 61-90 |  |  | 3 | [6 empty] | Open - No Action
489644 | C10525 | 2022-01-08 | 2022-05-28 | AC-9720-A | 37 | 62.02 | 2294.74 | P | 14 | 1-30 |  |  | 3 | 7712352 | 2022-01-18 | 37 | CMP-625-S | 74 | 2294.74 | Component Shortage
489261 | C10786 | 2021-06-24 | 2021-09-29 | AC-9763-01 | 7 | 89.24 | 624.68 | P | 255 | 90+ |  |  | 1 | 7710318 | 2021-06-29 | 7 |  |  | 624.68 | WO In Progress
Note on L1: The formula that started it all. Looks up the Item Number on the Do Not Make List and returns the hold reason; blank = OK to make.
Note on N1: COUNTIF of the Item Number. More than 1 = multiple open orders that could share a work order.
Note on T1: Originally a copy/paste of Ext Price. Rebuilt as Work Order Qty x Unit Price so short-shipped lines count only what actually ships.

## Past Due Report
Plant | Div | Ord Type | Sales Order | Line | Rel | Cust # | Ship Via | Terms | Buyer | Rev | UOM | Cust Class | Whse | Order Date | Promise Date | Item Number | Qty | Unit Price | Ext Price | O/P
M1-02 | 20 | SO | 489226 | 6 | 3 | C10385 | BEST WAY | N45 | B11 | C | EA | DEF | 02 | 2022-03-05 | 2022-04-19 | AC-2988-A | 13 | 46.34 | 602.42 | P
M1-02 | 20 | SO | 481101 | 2 | 3 | C10305 | LTL | N30 | B22 | C | EA | MRO | 02 | 2021-12-20 | 2022-04-20 | AC-9140-01 | 38 | 108.58 | 4126.04 | O
M1-02 | 30 | SO | 488976 | 1 | 1 | C10830 | BEST WAY | 2%10N30 | B11 | E | EA | DEF | 05 | 2022-03-02 | 2022-04-23 | AC-4972-05 | 35 | 252.06 | 8822.1 | P
M1-02 | 30 | SO | 481582 | 7 | 1 | C10706 | BEST WAY | 2%10N30 | B22 | C | EA | AERO | 05 | 2022-01-28 | 2022-05-12 | AC-1515-01 | 57 | 114.3 | 6515.1 | O
M1-02 | 30 | SO | 484041 | 4 | 2 | C10756 | LTL | 2%10N30 | B07 | NC | EA | AERO | 01 | 2021-09-05 | 2021-12-23 | AC-3920-05 | 19 | 166.81 | 3169.39 | O
M1-02 | 20 | SO | 481511 | 5 | 0 | C10973 | LTL | N30 | B07 | E | EA | AERO | 05 | 2021-09-02 | 2021-10-11 | AC-3019-B | 63 | 80.08 | 5045.04 | O
M1-02 | 30 | SO | 484937 | 9 | 1 | C10249 | FDX 2D | N60 | B14 | A | EA | AERO | 01 | 2021-09-19 | 2021-12-26 | AC-6384-A | 29 | 59.6 | 1728.4 | O
M1-02 | 30 | SO | 485506 | 7 | 3 | C10350 | BEST WAY | N60 | B11 | E | EA | AERO | 02 | 2021-06-25 | 2021-08-23 | AC-2870-A | 33 | 176.03 | 5808.99 | O
M1-02 | 30 | BL | 484638 | 1 | 3 | C10331 | BEST WAY | N45 | B22 | E | EA | AERO | 02 | 2021-06-26 | 2021-08-01 | AC-2827-02 | 98 | 165.33 | 16202.34 | O
M1-02 | 30 | SO | 485864 | 9 | 2 | C10900 | BEST WAY | 2%10N30 | B14 | C | EA | MRO | 05 | 2022-02-16 | 2022-05-23 | AC-7720-10 | 5 | 158.81 | 794.05 | O
M1-02 | 20 | BL | 480024 | 7 | 2 | C10436 | FDX 2D | N45 | B11 | D | EA | OEM | 05 | 2022-01-04 | 2022-05-11 | AC-1337-02 | 17 | 147.41 | 2505.97 | O
M1-02 | 30 | BL | 485342 | 9 | 0 | C10170 | UPS GND | N45 | B14 | A | EA | DEF | 01 | 2022-01-25 | 2022-03-16 | AC-1141-02 | 39 | 90.98 | 3548.22 | O
M1-02 | 30 | BL | 489076 | 1 | 1 | C10900 | FDX 2D | N30 | B22 | NC | EA | OEM | 05 | 2022-03-17 | 2022-06-03 | AC-9591-03 | 2 | 54.92 | 109.84 | P
M1-02 | 30 | SO | 484070 | 5 | 0 | C10519 | UPS GND | N60 | B07 | E | EA | OEM | 05 | 2021-03-12 | 2021-06-27 | AC-1742-B | 97 | 90.79 | 8806.63 | O
M1-02 | 20 | SO | 489694 | 9 | 1 | C10461 | CUST PU | N60 | B11 | D | EA | OEM | 02 | 2022-02-16 | 2022-04-23 | AC-8463-05 | 31 | 116.54 | 3612.74 | P
M1-02 | 20 | SO | 487270 | 7 | 1 | C10936 | BEST WAY | N60 | B07 | E | EA | OEM | 02 | 2021-11-29 | 2022-03-29 | AC-2574-A | 66 | 137.74 | 9090.84 | O
M1-02 | 20 | SO | 483148 | 5 | 3 | C10170 | LTL | 2%10N30 | B11 | D | EA | AERO | 02 | 2022-01-22 | 2022-04-20 | AC-2467-A | 34 | 176.31 | 5994.54 | O
M1-02 | 30 | SO | 483178 | 3 | 2 | C10525 | BEST WAY | N30 | B22 | C | EA | DEF | 01 | 2022-01-15 | 2022-03-14 | AC-8552-01 | 57 | 54.96 | 3132.72 | O
M1-02 | 20 | SO | 484539 | 10 | 3 | C10806 | UPS GND | N60 | B14 | C | EA | MRO | 05 | 2021-12-14 | 2022-04-28 | AC-9541-B | 59 | 107.77 | 6358.43 | O
M1-02 | 30 | SO | 482652 | 2 | 1 | C10706 | LTL | N45 | B07 | A | EA | MRO | 02 | 2021-12-26 | 2022-04-07 | AC-9587-B | 88 | 112.9 | 9935.2 | O
M1-02 | 30 | BL | 489455 | 9 | 0 | C10525 | UPS GND | N45 | B22 | E | EA | OEM | 05 | 2022-01-13 | 2022-06-02 | AC-6632-01 | 2 | 78.75 | 157.5 | P
M1-02 | 20 | SO | 485540 | 1 | 1 | C10256 | CUST PU | N45 | B11 | NC | EA | DEF | 05 | 2022-02-13 | 2022-04-19 | AC-3872-A | 25 | 166.14 | 4153.5 | O
M1-02 | 30 | SO | 485453 | 8 | 0 | C10940 | CUST PU | N30 | B14 | D | EA | AERO | 01 | 2021-03-02 | 2021-06-08 | AC-8540-01 | 91 | 139.61 | 12704.51 | O
M1-02 | 20 | SO | 489399 | 11 | 0 | C10501 | CUST PU | N30 | B22 | NC | EA | AERO | 02 | 2022-03-14 | 2022-05-28 | AC-2356-05 | 2 | 128.28 | 256.56 | P
M1-02 | 20 | SO | 483582 | 7 | 0 | C10305 | UPS GND | 2%10N30 | B22 | B | EA | OEM | 02 | 2021-12-02 | 2022-03-06 | AC-6537-05 | 24 | 149.22 | 3581.28 | O
M1-02 | 30 | BL | 480416 | 1 | 0 | C10350 | LTL | N30 | B14 | D | EA | DEF | 02 | 2022-01-05 | 2022-04-11 | AC-6008-A | 30 | 95.05 | 2851.5 | O
M1-02 | 30 | SO | 482213 | 8 | 2 | C10752 | BEST WAY | 2%10N30 | B07 | A | EA | OEM | 01 | 2022-02-09 | 2022-03-22 | AC-6644-03 | 19 | 87.08 | 1654.52 | O
M1-02 | 30 | BL | 489326 | 6 | 0 | C10280 | BEST WAY | 2%10N30 | B14 | A | EA | OEM | 02 | 2022-02-12 | 2022-04-30 | AC-4304-A | 30 | 28.33 | 849.9 | P
M1-02 | 20 | SO | 483766 | 4 | 1 | C10756 | FDX 2D | N60 | B22 | E | EA | AERO | 05 | 2022-02-25 | 2022-04-30 | AC-9454-05 | 93 | 97.33 | 9051.69 | O
M1-02 | 20 | SO | 485326 | 7 | 2 | C10280 | UPS GND | N30 | B14 | NC | EA | MRO | 01 | 2021-07-07 | 2021-09-14 | AC-5023-B | 44 | 176.38 | 7760.72 | O
M1-02 | 30 | SO | 483333 | 9 | 1 | C10498 | FDX 2D | N30 | B11 | A | EA | OEM | 02 | 2022-01-24 | 2022-06-04 | AC-6484-05 | 98 | 172.98 | 16952.04 | O
M1-02 | 20 | SO | 487841 | 9 | 0 | C10377 | BEST WAY | N45 | B22 | A | EA | DEF | 02 | 2021-12-24 | 2022-03-24 | AC-6549-A | 21 | 173.06 | 3634.26 | P
M1-02 | 20 | SO | 482385 | 6 | 1 | C10281 | LTL | N45 | B07 | E | EA | AERO | 05 | 2021-06-15 | 2021-09-17 | AC-3649-B | 83 | 99.9 | 8291.7 | O
M1-02 | 20 | SO | 480381 | 7 | 2 | C10170 | LTL | N30 | B11 | E | EA | AERO | 05 | 2021-11-28 | 2022-02-17 | AC-1683-10 | 66 | 130.86 | 8636.76 | O
M1-02 | 20 | SO | 483857 | 7 | 1 | C10852 | CUST PU | N60 | B07 | B | EA | AERO | 05 | 2021-12-01 | 2022-01-07 | AC-3019-B | 63 | 169.31 | 10666.53 | O
M1-02 | 20 | BL | 485183 | 9 | 0 | C10525 | BEST WAY | N60 | B14 | E | EA | OEM | 05 | 2021-07-23 | 2021-10-14 | AC-5631-01 | 21 | 67.93 | 1426.53 | O
M1-02 | 20 | SO | 487279 | 11 | 1 | C10860 | FDX 2D | 2%10N30 | B11 | C | EA | DEF | 05 | 2021-12-08 | 2022-04-07 | AC-7625-B | 87 | 80.82 | 7031.34 | O
M1-02 | 20 | SO | 486434 | 2 | 2 | C10238 | LTL | N30 | B07 | C | EA | MRO | 05 | 2021-10-18 | 2022-03-05 | AC-7714-10 | 19 | 109.05 | 2071.95 | O
M1-02 | 30 | SO | 481556 | 5 | 3 | C10332 | FDX 2D | N30 | B14 | NC | EA | AERO | 05 | 2022-01-11 | 2022-04-28 | AC-4289-01 | 25 | 75.37 | 1884.25 | O
M1-02 | 30 | SO | 487866 | 8 | 0 | C10817 | CUST PU | 2%10N30 | B07 | A | EA | DEF | 01 | 2021-06-29 | 2021-11-12 | AC-1448-02 | 4 | 54.23 | 216.92 | P
M1-02 | 20 | BL | 482913 | 10 | 0 | C10331 | LTL | N60 | B14 | B | EA | AERO | 01 | 2021-12-23 | 2022-03-30 | AC-7669-B | 71 | 140.05 | 9943.55 | O
M1-02 | 30 | SO | 487855 | 4 | 2 | C10170 | CUST PU | N60 | B07 | B | EA | DEF | 01 | 2021-07-24 | 2021-12-01 | AC-1084-B | 8 | 171.38 | 1371.04 | P
M1-02 | 30 | SO | 483146 | 11 | 1 | C10664 | LTL | N30 | B11 | B | EA | MRO | 05 | 2021-02-20 | 2021-07-09 | AC-6076-02 | 25 | 102.04 | 2551 | O
M1-02 | 20 | SO | 486900 | 10 | 1 | C10852 | BEST WAY | N30 | B14 | NC | EA | MRO | 05 | 2022-04-03 | 2022-05-14 | AC-9839-10 | 53 | 104.42 | 5534.26 | O
M1-02 | 30 | SO | 484768 | 9 | 1 | C10860 | CUST PU | N45 | B22 | NC | EA | DEF | 05 | 2021-11-14 | 2022-03-08 | AC-9652-03 | 38 | 68.15 | 2589.7 | O
M1-02 | 20 | SO | 488600 | 6 | 1 | C10321 | FDX 2D | N30 | B11 | E | EA | MRO | 02 | 2021-10-05 | 2022-02-11 | AC-3675-B | 60 | 144.39 | 8663.4 | P
M1-02 | 20 | SO | 487383 | 4 | 2 | C10706 | UPS GND | 2%10N30 | B14 | C | EA | OEM | 01 | 2021-06-28 | 2021-09-14 | AC-8994-B | 34 | 57.63 | 1959.42 | P
M1-02 | 30 | SO | 483381 | 8 | 1 | C10695 | CUST PU | N60 | B22 | C | EA | DEF | 02 | 2021-12-16 | 2022-04-06 | AC-3578-10 | 17 | 46.34 | 787.78 | O
M1-02 | 20 | BL | 480637 | 7 | 1 | C10252 | FDX 2D | N30 | B07 | A | EA | OEM | 05 | 2022-02-13 | 2022-03-25 | AC-7692-03 | 45 | 165.76 | 7459.2 | O
M1-02 | 30 | SO | 482618 | 12 | 2 | C10273 | UPS GND | N45 | B11 | A | EA | DEF | 05 | 2021-08-16 | 2021-12-16 | AC-5371-10 | 50 | 83.83 | 4191.5 | O
M1-02 | 30 | SO | 484131 | 10 | 2 | C10222 | LTL | N30 | B14 | NC | EA | OEM | 02 | 2021-06-30 | 2021-11-08 | AC-8872-B | 62 | 163.26 | 10122.12 | O
M1-02 | 20 | SO | 486330 | 7 | 1 | C10456 | CUST PU | N30 | B14 | E | EA | MRO | 05 | 2022-04-16 | 2022-05-14 | AC-2569-02 | 65 | 91.24 | 5930.6 | O
M1-02 | 20 | BL | 484257 | 2 | 3 | C10951 | CUST PU | 2%10N30 | B07 | B | EA | AERO | 02 | 2022-03-17 | 2022-06-03 | AC-3047-05 | 68 | 174.34 | 11855.12 | O
M1-02 | 30 | SO | 484208 | 10 | 0 | C10385 | LTL | N30 | B07 | C | EA | MRO | 02 | 2022-04-07 | 2022-05-05 | AC-7158-02 | 30 | 54.14 | 1624.2 | O
M1-02 | 20 | SO | 486737 | 1 | 1 | C10787 | LTL | N60 | B07 | A | EA | OEM | 01 | 2022-05-03 | 2022-06-10 | AC-4693-05 | 75 | 44 | 3300 | O
M1-02 | 20 | BL | 487094 | 7 | 1 | C10951 | UPS GND | N45 | B14 | C | EA | OEM | 05 | 2022-01-15 | 2022-04-05 | AC-2354-A | 97 | 49.61 | 4812.17 | O
M1-02 | 30 | SO | 486405 | 1 | 2 | C10331 | CUST PU | N60 | B14 | B | EA | MRO | 02 | 2022-03-17 | 2022-06-08 | AC-2645-01 | 20 | 61.79 | 1235.8 | O
M1-02 | 30 | SO | 487262 | 4 | 1 | C10249 | UPS GND | N30 | B11 | E | EA | AERO | 05 | 2022-01-24 | 2022-05-07 | AC-9278-01 | 33 | 44.32 | 1462.56 | O
M1-02 | 20 | SO | 488647 | 2 | 1 | C10951 | FDX 2D | 2%10N30 | B22 | E | EA | DEF | 01 | 2022-01-25 | 2022-04-21 | AC-6827-05 | 45 | 135.57 | 6100.65 | P
M1-02 | 30 | SO | 484635 | 9 | 0 | C10806 | CUST PU | N30 | B11 | D | EA | AERO | 01 | 2022-02-03 | 2022-03-29 | AC-5027-10 | 91 | 60.87 | 5539.17 | O
M1-02 | 30 | SO | 483879 | 9 | 0 | C10530 | LTL | N60 | B14 | C | EA | OEM | 02 | 2022-01-08 | 2022-05-24 | AC-6234-02 | 19 | 71.9 | 1366.1 | O
M1-02 | 20 | SO | 486300 | 12 | 3 | C10331 | LTL | N30 | B11 | NC | EA | OEM | 01 | 2022-02-18 | 2022-05-23 | AC-1896-A | 96 | 177.57 | 17046.72 | O
M1-02 | 30 | SO | 487704 | 8 | 0 | C10786 | BEST WAY | N30 | B14 | E | EA | DEF | 01 | 2021-12-13 | 2022-04-20 | AC-9025-05 | 16 | 83.45 | 1335.2 | P
M1-02 | 30 | BL | 485058 | 7 | 1 | C10806 | LTL | 2%10N30 | B07 | C | EA | DEF | 02 | 2022-03-16 | 2022-04-15 | AC-2849-B | 67 | 83.05 | 5564.35 | O
M1-02 | 30 | SO | 485363 | 9 | 0 | C10519 | LTL | 2%10N30 | B14 | B | EA | DEF | 05 | 2022-01-24 | 2022-04-26 | AC-6281-10 | 63 | 140.35 | 8842.05 | O
M1-02 | 20 | SO | 487174 | 6 | 2 | C10787 | CUST PU | 2%10N30 | B07 | C | EA | AERO | 01 | 2021-02-26 | 2021-06-30 | AC-2790-10 | 59 | 90.96 | 5366.64 | O
M1-02 | 20 | SO | 480648 | 1 | 0 | C10746 | UPS GND | N30 | B11 | D | EA | MRO | 05 | 2021-05-16 | 2021-07-30 | AC-2967-A | 34 | 127.28 | 4327.52 | O
M1-02 | 30 | SO | 484411 | 7 | 3 | C10806 | CUST PU | 2%10N30 | B07 | C | EA | MRO | 02 | 2022-02-04 | 2022-04-15 | AC-5010-A | 10 | 83.48 | 834.8 | O
M1-02 | 30 | SO | 487890 | 1 | 3 | C10852 | UPS GND | N45 | B14 | D | EA | AERO | 05 | 2021-10-14 | 2021-12-18 | AC-3665-03 | 60 | 83.39 | 5003.4 | P
M1-02 | 30 | SO | 482146 | 7 | 3 | C10420 | LTL | N60 | B11 | D | EA | AERO | 01 | 2021-04-04 | 2021-07-03 | AC-3013-B | 4 | 156.79 | 627.16 | O
M1-02 | 30 | SO | 485236 | 5 | 1 | C10860 | CUST PU | N30 | B11 | NC | EA | DEF | 05 | 2021-12-19 | 2022-03-27 | AC-9295-03 | 99 | 121.84 | 12062.16 | O
M1-02 | 20 | SO | 486751 | 8 | 2 | C10238 | LTL | 2%10N30 | B11 | B | EA | MRO | 01 | 2021-12-31 | 2022-05-15 | AC-5825-B | 25 | 109.95 | 2748.75 | O
M1-02 | 20 | SO | 480057 | 1 | 1 | C10817 | CUST PU | 2%10N30 | B11 | D | EA | AERO | 01 | 2022-01-19 | 2022-03-22 | AC-1568-A | 63 | 74.18 | 4673.34 | O
M1-02 | 20 | BL | 482532 | 10 | 1 | C10806 | LTL | N45 | B22 | C | EA | OEM | 05 | 2022-01-19 | 2022-05-28 | AC-1515-01 | 99 | 122.86 | 12163.14 | O
M1-02 | 20 | SO | 481465 | 6 | 1 | C10316 | BEST WAY | N45 | B11 | E | EA | AERO | 05 | 2021-12-19 | 2022-04-11 | AC-5562-B | 17 | 166.2 | 2825.4 | O
M1-02 | 20 | SO | 485042 | 11 | 2 | C10186 | LTL | N30 | B07 | NC | EA | DEF | 05 | 2022-02-12 | 2022-04-17 | AC-7549-05 | 15 | 153.96 | 2309.4 | O
M1-02 | 20 | SO | 484561 | 11 | 0 | C10305 | BEST WAY | N45 | B14 | D | EA | OEM | 01 | 2022-03-02 | 2022-04-26 | AC-3896-05 | 66 | 49.66 | 3277.56 | O
M1-02 | 20 | SO | 486003 | 3 | 3 | C10332 | FDX 2D | 2%10N30 | B22 | C | EA | OEM | 02 | 2022-05-07 | 2022-06-09 | AC-2574-A | 83 | 116.96 | 9707.68 | O
M1-02 | 30 | SO | 486135 | 9 | 2 | C10501 | UPS GND | 2%10N30 | B07 | A | EA | MRO | 01 | 2022-01-02 | 2022-03-28 | AC-4499-03 | 39 | 89.43 | 3487.77 | O
M1-02 | 20 | SO | 483749 | 11 | 2 | C10817 | LTL | N60 | B07 | A | EA | AERO | 05 | 2021-11-23 | 2022-03-23 | AC-7896-01 | 52 | 173.01 | 8996.52 | O
M1-02 | 30 | SO | 482055 | 1 | 0 | C10817 | UPS GND | N45 | B22 | C | EA | MRO | 02 | 2022-03-26 | 2022-04-30 | AC-1463-02 | 5 | 167.95 | 839.75 | O
M1-02 | 30 | SO | 483953 | 3 | 0 | C10852 | BEST WAY | N45 | B14 | E | EA | MRO | 01 | 2021-08-03 | 2021-12-06 | AC-8201-A | 46 | 66.5 | 3059 | O
M1-02 | 20 | SO | 481703 | 3 | 3 | C10900 | FDX 2D | N30 | B11 | NC | EA | DEF | 01 | 2021-11-30 | 2022-04-12 | AC-7277-A | 56 | 159.65 | 8940.4 | O
M1-02 | 20 | SO | 487036 | 5 | 3 | C10706 | LTL | N45 | B14 | A | EA | AERO | 05 | 2021-10-03 | 2022-01-16 | AC-4065-10 | 88 | 87.72 | 7719.36 | O
M1-02 | 30 | SO | 484412 | 5 | 3 | C10238 | FDX 2D | 2%10N30 | B14 | NC | EA | DEF | 05 | 2022-02-18 | 2022-05-16 | AC-2870-A | 93 | 66.32 | 6167.76 | O
M1-02 | 30 | SO | 480443 | 4 | 1 | C10688 | BEST WAY | N30 | B14 | D | EA | MRO | 05 | 2022-01-24 | 2022-03-19 | AC-8581-03 | 70 | 115.43 | 8080.1 | O
M1-02 | 20 | SO | 483403 | 5 | 0 | C10501 | UPS GND | N60 | B11 | C | EA | MRO | 01 | 2022-01-31 | 2022-04-18 | AC-1084-B | 16 | 93.1 | 1489.6 | O
M1-02 | 20 | SO | 486663 | 10 | 0 | C10316 | BEST WAY | N30 | B07 | C | EA | AERO | 01 | 2022-03-16 | 2022-04-15 | AC-2085-01 | 76 | 81.81 | 6217.56 | O
M1-02 | 30 | SO | 482160 | 12 | 1 | C10787 | LTL | 2%10N30 | B22 | E | EA | OEM | 01 | 2021-12-17 | 2022-04-13 | AC-2364-01 | 7 | 106.05 | 742.35 | O
M1-02 | 20 | SO | 489500 | 5 | 2 | C10455 | FDX 2D | N60 | B07 | B | EA | OEM | 01 | 2022-04-12 | 2022-05-30 | AC-3277-05 | 12 | 94.59 | 1135.08 | P
M1-02 | 30 | SO | 483533 | 4 | 0 | C10950 | BEST WAY | N60 | B14 | D | EA | AERO | 01 | 2021-11-18 | 2022-03-16 | AC-5036-01 | 99 | 45.31 | 4485.69 | O
M1-02 | 20 | SO | 486226 | 1 | 2 | C10519 | CUST PU | 2%10N30 | B11 | NC | EA | DEF | 05 | 2022-01-17 | 2022-04-03 | AC-2427-01 | 100 | 50.19 | 5019 | O
M1-02 | 20 | SO | 485340 | 1 | 0 | C10170 | BEST WAY | N60 | B14 | D | EA | AERO | 02 | 2022-04-17 | 2022-06-10 | AC-1179-B | 25 | 99.33 | 2483.25 | O
M1-02 | 20 | SO | 484383 | 3 | 3 | C10256 | FDX 2D | 2%10N30 | B22 | B | EA | AERO | 02 | 2022-02-23 | 2022-04-10 | AC-3014-10 | 51 | 163.64 | 8345.64 | O
M1-02 | 30 | BL | 482930 | 9 | 3 | C10817 | LTL | N60 | B07 | NC | EA | MRO | 02 | 2021-12-17 | 2022-04-02 | AC-9748-05 | 65 | 132.18 | 8591.7 | O
M1-02 | 20 | SO | 481980 | 3 | 1 | C10664 | LTL | N30 | B07 | NC | EA | DEF | 01 | 2021-11-27 | 2022-03-18 | AC-6072-03 | 99 | 172.96 | 17123.04 | O
M1-02 | 30 | BL | 484163 | 12 | 3 | C10973 | UPS GND | N45 | B14 | NC | EA | MRO | 02 | 2021-08-02 | 2021-09-22 | AC-8853-B | 48 | 133.1 | 6388.8 | O
M1-02 | 20 | BL | 481146 | 9 | 0 | C10251 | CUST PU | N30 | B22 | D | EA | OEM | 01 | 2022-04-09 | 2022-05-25 | AC-6487-02 | 16 | 142.38 | 2278.08 | O
M1-02 | 30 | BL | 480612 | 12 | 3 | C10316 | CUST PU | N30 | B11 | D | EA | MRO | 05 | 2022-02-27 | 2022-05-27 | AC-9815-05 | 54 | 102.25 | 5521.5 | O
M1-02 | 20 | SO | 487318 | 7 | 2 | C10377 | FDX 2D | N30 | B11 | C | EA | OEM | 01 | 2021-11-23 | 2022-03-17 | AC-6612-B | 38 | 131 | 4978 | O
M1-02 | 20 | SO | 480622 | 3 | 3 | C10501 | LTL | N45 | B11 | C | EA | MRO | 01 | 2022-03-07 | 2022-05-27 | AC-5968-02 | 78 | 133.77 | 10434.06 | O
M1-02 | 20 | SO | 486905 | 1 | 2 | C10966 | BEST WAY | N60 | B07 | B | EA | DEF | 02 | 2022-01-10 | 2022-04-12 | AC-2938-03 | 10 | 96.77 | 967.7 | O
M1-02 | 30 | BL | 486249 | 12 | 1 | C10519 | BEST WAY | N45 | B14 | A | EA | OEM | 02 | 2021-04-24 | 2021-08-10 | AC-2827-02 | 14 | 144.71 | 2025.94 | O
M1-02 | 30 | SO | 484300 | 12 | 1 | C10568 | FDX 2D | 2%10N30 | B14 | C | EA | DEF | 01 | 2022-01-21 | 2022-05-07 | AC-1789-10 | 75 | 83.61 | 6270.75 | O
M1-02 | 20 | BL | 483816 | 1 | 3 | C10238 | FDX 2D | 2%10N30 | B11 | D | EA | DEF | 05 | 2022-04-06 | 2022-05-23 | AC-4388-B | 20 | 161.93 | 3238.6 | O
M1-02 | 30 | BL | 489718 | 8 | 2 | C10436 | LTL | 2%10N30 | B11 | A | EA | MRO | 01 | 2022-02-01 | 2022-05-31 | AC-6854-01 | 40 | 171.93 | 6877.2 | P
M1-02 | 30 | BL | 484238 | 3 | 3 | C10461 | LTL | N30 | B07 | B | EA | OEM | 02 | 2021-04-05 | 2021-06-30 | AC-5562-B | 64 | 168.1 | 10758.4 | O
M1-02 | 20 | SO | 489791 | 8 | 2 | C10940 | LTL | N30 | B22 | E | EA | OEM | 01 | 2022-04-24 | 2022-06-03 | AC-6670-10 | 25 | 69.87 | 1746.75 | P
M1-02 | 20 | SO | 484954 | 1 | 2 | C10544 | LTL | N30 | B22 | A | EA | DEF | 02 | 2022-01-16 | 2022-05-22 | AC-4556-A | 55 | 158.31 | 8707.05 | O
M1-02 | 20 | BL | 489128 | 9 | 3 | C10530 | BEST WAY | N30 | B11 | C | EA | AERO | 02 | 2021-11-28 | 2022-02-08 | AC-9241-02 | 24 | 100.87 | 2420.88 | P
M1-02 | 30 | SO | 485279 | 11 | 1 | C10186 | UPS GND | N30 | B11 | A | EA | OEM | 01 | 2022-02-16 | 2022-04-19 | AC-3297-05 | 74 | 143.1 | 10589.4 | O
M1-02 | 30 | SO | 485323 | 12 | 2 | C10498 | CUST PU | N60 | B11 | NC | EA | AERO | 05 | 2022-01-04 | 2022-04-07 | AC-3317-B | 80 | 105.48 | 8438.4 | O
M1-02 | 30 | SO | 488984 | 3 | 1 | C10186 | FDX 2D | 2%10N30 | B11 | C | EA | AERO | 01 | 2022-01-08 | 2022-04-18 | AC-9217-10 | 28 | 115.26 | 3227.28 | P
M1-02 | 20 | SO | 486803 | 11 | 2 | C10806 | CUST PU | N30 | B22 | C | EA | MRO | 01 | 2022-01-10 | 2022-03-30 | AC-8412-03 | 51 | 102.06 | 5205.06 | O
M1-02 | 20 | SO | 483609 | 10 | 2 | C10251 | LTL | N60 | B14 | B | EA | AERO | 02 | 2022-02-14 | 2022-06-10 | AC-5592-03 | 86 | 62.23 | 5351.78 | O
M1-02 | 20 | BL | 489183 | 3 | 1 | C10950 | LTL | N60 | B07 | NC | EA | DEF | 05 | 2021-11-24 | 2022-04-05 | AC-6706-05 | 26 | 127.13 | 3305.38 | P
M1-02 | 30 | SO | 487806 | 6 | 2 | C10238 | CUST PU | 2%10N30 | B11 | NC | EA | AERO | 05 | 2021-12-24 | 2022-04-30 | AC-2363-03 | 59 | 168.56 | 9945.04 | P
M1-02 | 30 | BL | 488389 | 5 | 3 | C10860 | CUST PU | N30 | B07 | NC | EA | DEF | 02 | 2021-12-06 | 2022-04-17 | AC-2363-03 | 36 | 160.32 | 5771.52 | P
M1-02 | 30 | BL | 488097 | 1 | 0 | C10222 | UPS GND | 2%10N30 | B07 | E | EA | OEM | 02 | 2021-06-08 | 2021-07-24 | AC-9448-05 | 4 | 70.75 | 283 | P
M1-02 | 30 | SO | 487074 | 6 | 1 | C10385 | FDX 2D | N30 | B07 | NC | EA | MRO | 05 | 2022-04-22 | 2022-06-02 | AC-8900-01 | 72 | 93.05 | 6699.6 | O
M1-02 | 30 | SO | 483968 | 4 | 3 | C10852 | CUST PU | N60 | B22 | E | EA | AERO | 02 | 2021-05-07 | 2021-08-11 | AC-6605-03 | 39 | 134.09 | 5229.51 | O
M1-02 | 30 | SO | 487510 | 4 | 1 | C10817 | UPS GND | 2%10N30 | B22 | D | EA | DEF | 05 | 2022-01-12 | 2022-04-18 | AC-2364-01 | 32 | 124.29 | 3977.28 | P
M1-02 | 20 | SO | 488249 | 8 | 0 | C10526 | CUST PU | N60 | B22 | B | EA | DEF | 01 | 2021-09-22 | 2022-01-04 | AC-8440-03 | 54 | 42.12 | 2274.48 | P
M1-02 | 20 | SO | 489623 | 11 | 3 | C10501 | LTL | N45 | B11 | D | EA | AERO | 01 | 2021-11-20 | 2022-03-23 | AC-8805-01 | 29 | 53.15 | 1541.35 | P
M1-02 | 20 | BL | 485559 | 1 | 0 | C10940 | CUST PU | N45 | B14 | E | EA | MRO | 01 | 2021-07-29 | 2021-10-03 | AC-8427-05 | 70 | 131.55 | 9208.5 | O
M1-02 | 20 | SO | 483415 | 11 | 2 | C10756 | UPS GND | N45 | B07 | E | EA | DEF | 01 | 2021-05-25 | 2021-07-26 | AC-9748-05 | 67 | 85.86 | 5752.62 | O
M1-02 | 30 | BL | 480753 | 12 | 1 | C10385 | FDX 2D | 2%10N30 | B22 | D | EA | OEM | 02 | 2021-12-27 | 2022-04-22 | AC-4556-A | 72 | 82 | 5904 | O
M1-02 | 30 | SO | 488456 | 6 | 2 | C10273 | FDX 2D | N60 | B14 | C | EA | DEF | 01 | 2021-04-08 | 2021-07-23 | AC-3060-02 | 33 | 179.42 | 5920.86 | P
M1-02 | 30 | SO | 488408 | 6 | 0 | C10560 | BEST WAY | N60 | B11 | B | EA | AERO | 05 | 2021-05-13 | 2021-09-12 | AC-4690-10 | 37 | 131.58 | 4868.46 | P
M1-02 | 20 | SO | 486473 | 4 | 3 | C10966 | BEST WAY | 2%10N30 | B22 | A | EA | AERO | 02 | 2021-12-27 | 2022-05-15 | AC-4936-01 | 79 | 156.49 | 12362.71 | O
M1-02 | 20 | SO | 488053 | 12 | 0 | C10589 | BEST WAY | N30 | B14 | D | EA | MRO | 05 | 2021-04-01 | 2021-05-27 | AC-3151-05 | 15 | 86.61 | 1299.15 | P
M1-02 | 20 | SO | 488920 | 10 | 0 | C10695 | UPS GND | N30 | B11 | A | EA | OEM | 01 | 2022-04-12 | 2022-05-27 | AC-2726-B | 39 | 128.65 | 5017.35 | P
M1-02 | 30 | BL | 488207 | 7 | 0 | C10746 | FDX 2D | N30 | B14 | C | EA | MRO | 05 | 2022-01-07 | 2022-04-17 | AC-7457-B | 21 | 50.05 | 1051.05 | P
M1-02 | 30 | SO | 488155 | 7 | 2 | C10456 | UPS GND | N30 | B14 | NC | EA | DEF | 05 | 2021-06-12 | 2021-08-19 | AC-3053-03 | 55 | 130.28 | 7165.4 | P
M1-02 | 30 | SO | 484277 | 12 | 1 | C10281 | UPS GND | N30 | B14 | D | EA | AERO | 05 | 2021-04-30 | 2021-08-07 | AC-6469-10 | 7 | 125.22 | 876.54 | O
M1-02 | 20 | BL | 489260 | 6 | 2 | C10688 | BEST WAY | N60 | B22 | NC | EA | AERO | 05 | 2022-01-04 | 2022-05-01 | AC-5120-A | 16 | 128.99 | 2063.84 | P
M1-02 | 30 | SO | 484403 | 5 | 2 | C10461 | CUST PU | N60 | B07 | C | EA | DEF | 02 | 2021-06-07 | 2021-08-23 | AC-7626-05 | 86 | 142.16 | 12225.76 | O
M1-02 | 30 | SO | 488871 | 4 | 1 | C10544 | LTL | N60 | B07 | A | EA | AERO | 05 | 2022-02-07 | 2022-05-10 | AC-9577-02 | 39 | 97.88 | 3817.32 | P
M1-02 | 30 | SO | 482944 | 8 | 1 | C10746 | CUST PU | N45 | B22 | NC | EA | OEM | 05 | 2021-08-11 | 2021-09-16 | AC-2084-A | 34 | 97.98 | 3331.32 | O
M1-02 | 20 | BL | 485471 | 4 | 1 | C10860 | UPS GND | N60 | B11 | E | EA | AERO | 01 | 2021-09-21 | 2022-01-24 | AC-1293-A | 15 | 168.5 | 2527.5 | O
M1-02 | 20 | SO | 480970 | 11 | 1 | C10936 | UPS GND | N60 | B11 | NC | EA | DEF | 01 | 2022-01-21 | 2022-04-08 | AC-1748-A | 75 | 115 | 8625 | O
M1-02 | 30 | SO | 485841 | 9 | 2 | C10350 | LTL | N60 | B11 | D | EA | MRO | 02 | 2022-02-09 | 2022-05-27 | AC-1144-10 | 16 | 46.28 | 740.48 | O
M1-02 | 20 | SO | 487121 | 4 | 2 | C10688 | CUST PU | N45 | B14 | A | EA | DEF | 01 | 2022-01-16 | 2022-03-22 | AC-2570-B | 55 | 76.16 | 4188.8 | O
M1-02 | 30 | BL | 483157 | 12 | 2 | C10530 | CUST PU | N45 | B22 | D | EA | OEM | 05 | 2022-04-09 | 2022-06-07 | AC-8540-01 | 65 | 155.17 | 10086.05 | O
M1-02 | 20 | BL | 482559 | 8 | 0 | C10824 | BEST WAY | 2%10N30 | B07 | D | EA | MRO | 02 | 2022-03-07 | 2022-04-26 | AC-1382-B | 77 | 71.38 | 5496.26 | O
M1-02 | 30 | SO | 481431 | 2 | 0 | C10252 | CUST PU | N30 | B22 | C | EA | OEM | 02 | 2022-02-10 | 2022-04-06 | AC-4001-10 | 54 | 105.36 | 5689.44 | O
M1-02 | 30 | SO | 483591 | 10 | 0 | C10252 | BEST WAY | N30 | B11 | B | EA | DEF | 02 | 2021-08-28 | 2021-12-22 | AC-3872-A | 5 | 54.5 | 272.5 | O
M1-02 | 20 | SO | 489033 | 4 | 0 | C10377 | UPS GND | N60 | B22 | A | EA | MRO | 01 | 2021-03-12 | 2021-07-20 | AC-4307-01 | 15 | 45.85 | 687.75 | P
M1-02 | 30 | SO | 488810 | 7 | 1 | C10852 | BEST WAY | N30 | B14 | NC | EA | DEF | 02 | 2021-12-07 | 2022-01-26 | AC-1599-03 | 18 | 120.87 | 2175.66 | P
M1-02 | 20 | SO | 480466 | 9 | 0 | C10331 | LTL | 2%10N30 | B14 | B | EA | MRO | 05 | 2021-09-09 | 2022-01-24 | AC-3815-B | 94 | 93.33 | 8773.02 | O
M1-02 | 30 | SO | 484804 | 4 | 3 | C10350 | BEST WAY | N60 | B11 | B | EA | AERO | 05 | 2022-01-15 | 2022-05-21 | AC-9003-03 | 100 | 162.8 | 16280 | O
M1-02 | 30 | SO | 485964 | 3 | 2 | C10256 | BEST WAY | N45 | B14 | A | EA | AERO | 01 | 2022-02-04 | 2022-05-19 | AC-3418-01 | 58 | 154.63 | 8968.54 | O
M1-02 | 20 | SO | 482903 | 11 | 1 | C10249 | BEST WAY | N60 | B14 | E | EA | OEM | 05 | 2021-12-06 | 2022-04-25 | AC-6982-05 | 51 | 105.99 | 5405.49 | O
M1-02 | 30 | SO | 486606 | 2 | 1 | C10688 | BEST WAY | N45 | B11 | D | EA | DEF | 01 | 2021-07-31 | 2021-12-03 | AC-8345-B | 26 | 80.77 | 2100.02 | O
M1-02 | 30 | SO | 487051 | 10 | 2 | C10420 | BEST WAY | N60 | B07 | C | EA | MRO | 05 | 2022-03-01 | 2022-05-26 | AC-2371-A | 61 | 114.81 | 7003.41 | O
M1-02 | 30 | BL | 480523 | 8 | 3 | C10170 | CUST PU | N60 | B11 | NC | EA | OEM | 02 | 2021-05-28 | 2021-09-30 | AC-2546-A | 56 | 125.03 | 7001.68 | O
M1-02 | 20 | SO | 488366 | 2 | 1 | C10186 | UPS GND | N30 | B22 | E | EA | DEF | 02 | 2021-10-03 | 2021-12-04 | AC-2334-02 | 41 | 59.19 | 2426.79 | P
M1-02 | 30 | BL | 480999 | 2 | 0 | C10966 | UPS GND | N45 | B07 | B | EA | AERO | 05 | 2021-12-14 | 2022-04-27 | AC-9569-A | 34 | 45.85 | 1558.9 | O
M1-02 | 20 | BL | 487566 | 9 | 3 | C10385 | CUST PU | 2%10N30 | B22 | D | EA | MRO | 05 | 2022-04-20 | 2022-06-07 | AC-6702-02 | 49 | 135.77 | 6652.73 | P
M1-02 | 30 | SO | 488586 | 6 | 0 | C10264 | UPS GND | 2%10N30 | B11 | NC | EA | DEF | 05 | 2021-10-31 | 2022-03-19 | AC-2415-B | 47 | 65.07 | 3058.29 | P
M1-02 | 20 | SO | 487523 | 3 | 1 | C10519 | UPS GND | 2%10N30 | B22 | E | EA | AERO | 02 | 2022-01-12 | 2022-05-08 | AC-1883-02 | 16 | 51.92 | 830.72 | P
M1-02 | 30 | SO | 486783 | 10 | 2 | C10758 | BEST WAY | N30 | B07 | E | EA | MRO | 02 | 2021-09-30 | 2022-02-15 | AC-1789-10 | 31 | 86.1 | 2669.1 | O
M1-02 | 30 | BL | 487312 | 1 | 1 | C10568 | LTL | N30 | B22 | NC | EA | AERO | 01 | 2021-11-03 | 2022-03-15 | AC-5952-B | 11 | 118.65 | 1305.15 | O
M1-02 | 20 | BL | 485406 | 10 | 1 | C10695 | CUST PU | N45 | B14 | E | EA | MRO | 02 | 2022-02-01 | 2022-05-30 | AC-6106-B | 64 | 87.12 | 5575.68 | O
M1-02 | 30 | SO | 484210 | 6 | 0 | C10756 | CUST PU | 2%10N30 | B22 | D | EA | DEF | 01 | 2022-03-15 | 2022-05-20 | AC-1301-B | 33 | 101.49 | 3349.17 | O
M1-02 | 30 | SO | 485789 | 4 | 1 | C10280 | CUST PU | 2%10N30 | B11 | B | EA | AERO | 02 | 2021-05-26 | 2021-09-25 | AC-4001-10 | 48 | 44.79 | 2149.92 | O
M1-02 | 30 | SO | 481682 | 9 | 0 | C10940 | UPS GND | N30 | B07 | E | EA | OEM | 01 | 2022-02-17 | 2022-05-03 | AC-2561-05 | 19 | 58.16 | 1105.04 | O
M1-02 | 20 | SO | 489247 | 12 | 0 | C10519 | UPS GND | N30 | B11 | NC | EA | DEF | 02 | 2021-11-27 | 2022-04-16 | AC-3870-01 | 6 | 76.2 | 457.2 | P
M1-02 | 20 | SO | 481666 | 7 | 0 | C10568 | BEST WAY | N45 | B14 | E | EA | OEM | 02 | 2021-03-28 | 2021-07-26 | AC-1382-B | 98 | 84.2 | 8251.6 | O
M1-02 | 20 | SO | 489757 | 10 | 2 | C10280 | BEST WAY | N60 | B14 | C | EA | MRO | 05 | 2022-02-08 | 2022-05-22 | AC-8338-01 | 31 | 123.44 | 3826.64 | P
M1-02 | 30 | SO | 481482 | 7 | 3 | C10966 | LTL | N30 | B14 | E | EA | DEF | 01 | 2022-01-29 | 2022-04-17 | AC-1358-01 | 47 | 60.63 | 2849.61 | O
M1-02 | 20 | SO | 483599 | 4 | 3 | C10525 | FDX 2D | N30 | B07 | B | EA | AERO | 02 | 2022-03-28 | 2022-05-08 | AC-8427-05 | 90 | 147.42 | 13267.8 | O
M1-02 | 20 | SO | 489603 | 9 | 3 | C10461 | CUST PU | 2%10N30 | B07 | D | EA | OEM | 01 | 2021-12-22 | 2022-04-04 | AC-6713-10 | 34 | 132.88 | 4517.92 | P
M1-02 | 20 | SO | 489015 | 8 | 2 | C10461 | LTL | 2%10N30 | B11 | E | EA | AERO | 05 | 2021-06-17 | 2021-09-03 | AC-4074-03 | 8 | 109.06 | 872.48 | P
M1-02 | 30 | BL | 487525 | 5 | 0 | C10350 | BEST WAY | N60 | B11 | E | EA | AERO | 02 | 2021-09-18 | 2022-01-02 | AC-8498-A | 28 | 129.23 | 3618.44 | P
M1-02 | 30 | BL | 488436 | 2 | 1 | C10501 | CUST PU | N60 | B22 | B | EA | DEF | 05 | 2021-10-16 | 2022-01-02 | AC-2081-A | 19 | 50.67 | 962.73 | P
M1-02 | 20 | SO | 487266 | 6 | 2 | C10420 | FDX 2D | N60 | B11 | A | EA | AERO | 05 | 2022-03-04 | 2022-05-26 | AC-4457-B | 88 | 85.98 | 7566.24 | O
M1-02 | 20 | SO | 484935 | 10 | 3 | C10786 | BEST WAY | N45 | B22 | B | EA | DEF | 05 | 2021-11-15 | 2022-03-17 | AC-3896-A | 4 | 48.44 | 193.76 | O
M1-02 | 30 | SO | 488318 | 12 | 1 | C10186 | UPS GND | N30 | B22 | D | EA | MRO | 01 | 2021-11-23 | 2022-01-14 | AC-7397-01 | 60 | 168.34 | 10100.4 | P
M1-02 | 20 | SO | 484148 | 10 | 0 | C10420 | UPS GND | 2%10N30 | B07 | B | EA | MRO | 01 | 2021-03-30 | 2021-07-23 | AC-9675-05 | 72 | 158.29 | 11396.88 | O
M1-02 | 30 | SO | 489661 | 5 | 1 | C10525 | FDX 2D | N45 | B14 | C | EA | AERO | 05 | 2022-02-25 | 2022-04-18 | AC-1060-10 | 27 | 197 | 5319 | P
M1-02 | 30 | BL | 484474 | 12 | 3 | C10758 | UPS GND | N60 | B07 | E | EA | AERO | 02 | 2022-04-14 | 2022-06-07 | AC-5027-10 | 18 | 169.3 | 3047.4 | O
M1-02 | 30 | SO | 480975 | 1 | 0 | C10519 | UPS GND | N30 | B07 | A | EA | OEM | 01 | 2021-11-11 | 2022-03-18 | AC-1364-B | 38 | 113.04 | 4295.52 | O
M1-02 | 20 | SO | 481795 | 2 | 1 | C10746 | UPS GND | N60 | B22 | NC | EA | OEM | 05 | 2022-03-16 | 2022-05-04 | AC-7511-03 | 94 | 123.98 | 11654.12 | O
M1-02 | 30 | SO | 489627 | 3 | 3 | C10321 | UPS GND | N60 | B07 | A | EA | OEM | 05 | 2022-02-10 | 2022-04-14 | AC-1565-05 | 27 | 64.07 | 1729.89 | P
M1-02 | 20 | SO | 486267 | 6 | 0 | C10824 | BEST WAY | 2%10N30 | B14 | NC | EA | AERO | 02 | 2022-01-04 | 2022-03-19 | AC-2334-02 | 69 | 95.72 | 6604.68 | O
M1-02 | 20 | BL | 480188 | 10 | 3 | C10940 | UPS GND | 2%10N30 | B14 | E | EA | OEM | 05 | 2022-01-17 | 2022-04-10 | AC-9526-B | 53 | 77.35 | 4099.55 | O
M1-02 | 30 | BL | 488113 | 1 | 1 | C10498 | CUST PU | N30 | B11 | C | EA | OEM | 05 | 2022-01-16 | 2022-05-28 | AC-8035-02 | 26 | 179.75 | 4673.5 | P
M1-02 | 20 | SO | 488665 | 11 | 2 | C10280 | CUST PU | N45 | B07 | B | EA | OEM | 05 | 2021-10-10 | 2022-02-22 | AC-2334-02 | 33 | 69.43 | 2291.19 | P
M1-02 | 20 | SO | 482764 | 2 | 3 | C10787 | LTL | 2%10N30 | B07 | C | EA | OEM | 01 | 2021-03-18 | 2021-06-14 | AC-2139-10 | 51 | 137 | 6987 | O
M1-02 | 30 | BL | 480577 | 9 | 1 | C10706 | FDX 2D | N60 | B14 | E | EA | DEF | 05 | 2022-04-18 | 2022-06-08 | AC-6377-05 | 47 | 60.39 | 2838.33 | O
M1-02 | 30 | SO | 480435 | 2 | 2 | C10973 | CUST PU | N30 | B07 | A | EA | MRO | 02 | 2021-10-12 | 2022-01-11 | AC-7170-B | 13 | 45.79 | 595.27 | O
M1-02 | 30 | BL | 480919 | 3 | 3 | C10186 | FDX 2D | N60 | B14 | E | EA | MRO | 01 | 2021-09-16 | 2021-10-23 | AC-3495-05 | 48 | 167.1 | 8020.8 | O
M1-02 | 30 | SO | 486224 | 6 | 2 | C10688 | LTL | N45 | B14 | C | EA | DEF | 05 | 2022-03-20 | 2022-04-29 | AC-7749-05 | 53 | 69.15 | 3664.95 | O
M1-02 | 30 | SO | 484219 | 3 | 2 | C10824 | FDX 2D | N45 | B07 | C | EA | DEF | 01 | 2021-03-14 | 2021-06-26 | AC-1568-A | 14 | 48.38 | 677.32 | O
M1-02 | 20 | BL | 483034 | 9 | 3 | C10568 | FDX 2D | N30 | B14 | D | EA | OEM | 01 | 2022-01-29 | 2022-03-31 | AC-9382-03 | 37 | 174.35 | 6450.95 | O
M1-02 | 30 | SO | 483152 | 4 | 2 | C10321 | FDX 2D | N60 | B11 | NC | EA | MRO | 02 | 2022-01-18 | 2022-05-17 | AC-5672-03 | 15 | 80.62 | 1209.3 | O
M1-02 | 20 | SO | 484582 | 1 | 2 | C10752 | BEST WAY | N30 | B07 | A | EA | OEM | 05 | 2022-04-20 | 2022-06-04 | AC-8462-A | 7 | 79.78 | 558.46 | O
M1-02 | 30 | SO | 483050 | 11 | 1 | C10830 | LTL | N45 | B11 | A | EA | AERO | 01 | 2021-09-07 | 2021-12-30 | AC-7135-05 | 75 | 114.79 | 8609.25 | O
M1-02 | 20 | BL | 489016 | 9 | 2 | C10695 | BEST WAY | N60 | B14 | D | EA | MRO | 05 | 2022-03-13 | 2022-05-03 | AC-8653-01 | 16 | 29.85 | 477.6 | P
M1-02 | 30 | SO | 487273 | 10 | 3 | C10264 | FDX 2D | N60 | B07 | D | EA | AERO | 02 | 2022-01-12 | 2022-05-28 | AC-6758-10 | 59 | 160.48 | 9468.32 | O
M1-02 | 30 | SO | 483778 | 1 | 1 | C10436 | UPS GND | N45 | B14 | E | EA | DEF | 02 | 2021-12-17 | 2022-02-15 | AC-2415-B | 52 | 152.5 | 7930 | O
M1-02 | 30 | SO | 488740 | 4 | 0 | C10377 | FDX 2D | 2%10N30 | B14 | A | EA | AERO | 01 | 2021-09-19 | 2021-12-30 | AC-9332-01 | 19 | 144.35 | 2742.65 | P
M1-02 | 30 | SO | 486015 | 1 | 0 | C10973 | FDX 2D | 2%10N30 | B07 | A | EA | MRO | 02 | 2022-02-18 | 2022-04-27 | AC-4357-05 | 86 | 120.68 | 10378.48 | O
M1-02 | 20 | SO | 488590 | 12 | 3 | C10852 | CUST PU | N60 | B22 | E | EA | OEM | 05 | 2021-03-07 | 2021-06-12 | AC-3396-01 | 50 | 165.35 | 8267.5 | P
M1-02 | 20 | SO | 482621 | 10 | 2 | C10560 | FDX 2D | N60 | B11 | B | EA | OEM | 01 | 2022-04-16 | 2022-06-04 | AC-9448-02 | 61 | 162.52 | 9913.72 | O
M1-02 | 20 | SO | 480849 | 2 | 2 | C10273 | UPS GND | N60 | B22 | B | EA | AERO | 02 | 2022-03-07 | 2022-05-23 | AC-4302-01 | 14 | 159.19 | 2228.66 | O
M1-02 | 30 | SO | 486012 | 4 | 3 | C10900 | LTL | N60 | B22 | B | EA | OEM | 05 | 2022-03-25 | 2022-05-20 | AC-4556-A | 98 | 161.45 | 15822.1 | O
M1-02 | 30 | SO | 485836 | 11 | 2 | C10746 | UPS GND | 2%10N30 | B14 | B | EA | AERO | 01 | 2021-07-06 | 2021-08-22 | AC-2943-01 | 66 | 107.6 | 7101.6 | O
M1-02 | 20 | SO | 488800 | 5 | 3 | C10498 | LTL | N30 | B14 | B | EA | DEF | 02 | 2022-03-13 | 2022-05-22 | AC-7397-01 | 27 | 87.39 | 2359.53 | P
M1-02 | 20 | BL | 480079 | 9 | 1 | C10787 | BEST WAY | N60 | B07 | NC | EA | MRO | 01 | 2021-11-30 | 2022-01-05 | AC-2571-A | 91 | 76.52 | 6963.32 | O
M1-02 | 20 | SO | 481540 | 7 | 3 | C10756 | FDX 2D | 2%10N30 | B11 | E | EA | MRO | 01 | 2022-02-25 | 2022-05-19 | AC-9767-B | 83 | 154.36 | 12811.88 | O
M1-02 | 20 | BL | 482569 | 6 | 2 | C10526 | CUST PU | N30 | B14 | C | EA | DEF | 01 | 2022-01-27 | 2022-05-04 | AC-1388-B | 50 | 113.92 | 5696 | O
M1-02 | 20 | SO | 485103 | 8 | 2 | C10273 | BEST WAY | 2%10N30 | B11 | C | EA | OEM | 01 | 2022-01-18 | 2022-03-21 | AC-5036-01 | 99 | 46.08 | 4561.92 | O
M1-02 | 30 | SO | 484017 | 4 | 0 | C10544 | LTL | N45 | B07 | D | EA | OEM | 01 | 2022-01-24 | 2022-05-21 | AC-9804-05 | 75 | 155.07 | 11630.25 | O
M1-02 | 30 | SO | 480631 | 8 | 2 | C10787 | FDX 2D | N30 | B14 | C | EA | MRO | 01 | 2022-01-07 | 2022-05-19 | AC-6550-01 | 98 | 107.27 | 10512.46 | O
M1-02 | 30 | BL | 482233 | 4 | 3 | C10560 | CUST PU | 2%10N30 | B22 | E | EA | OEM | 02 | 2022-03-20 | 2022-06-10 | AC-5371-10 | 41 | 113.33 | 4646.53 | O
M1-02 | 20 | SO | 481069 | 9 | 0 | C10589 | FDX 2D | N30 | B11 | D | EA | DEF | 05 | 2021-10-22 | 2021-12-23 | AC-6332-B | 25 | 101.54 | 2538.5 | O
M1-02 | 30 | SO | 484780 | 2 | 2 | C10385 | FDX 2D | N30 | B22 | A | EA | DEF | 01 | 2022-03-11 | 2022-05-22 | AC-8083-03 | 52 | 50.19 | 2609.88 | O
M1-02 | 30 | BL | 487402 | 2 | 0 | C10589 | CUST PU | N60 | B11 | B | EA | DEF | 05 | 2022-02-04 | 2022-03-24 | AC-8194-03 | 5 | 73.8 | 369 | P
M1-02 | 30 | SO | 487896 | 9 | 3 | C10526 | CUST PU | N30 | B07 | C | EA | OEM | 05 | 2021-05-23 | 2021-06-23 | AC-1570-02 | 13 | 41.8 | 543.4 | P
M1-02 | 20 | SO | 489653 | 2 | 1 | C10706 | UPS GND | N45 | B22 | D | EA | OEM | 02 | 2022-01-10 | 2022-04-23 | AC-4972-05 | 28 | 251.74 | 7048.72 | P
M1-02 | 20 | SO | 484118 | 5 | 3 | C10321 | LTL | N30 | B07 | C | EA | DEF | 05 | 2021-11-21 | 2022-04-03 | AC-1364-B | 45 | 162.26 | 7301.7 | O
M1-02 | 30 | SO | 487910 | 7 | 2 | C10860 | CUST PU | N60 | B11 | D | EA | DEF | 02 | 2021-12-08 | 2022-03-22 | AC-9206-05 | 25 | 101.27 | 2531.75 | P
M1-02 | 30 | BL | 483153 | 1 | 1 | C10966 | FDX 2D | N60 | B22 | D | EA | AERO | 02 | 2021-11-26 | 2022-01-25 | AC-1748-A | 91 | 118.21 | 10757.11 | O
M1-02 | 30 | BL | 483097 | 12 | 3 | C10316 | CUST PU | N45 | B11 | A | EA | MRO | 01 | 2022-01-20 | 2022-04-11 | AC-2371-A | 80 | 164.19 | 13135.2 | O
M1-02 | 30 | SO | 481039 | 9 | 1 | C10950 | CUST PU | N45 | B22 | E | EA | DEF | 02 | 2021-07-09 | 2021-10-06 | AC-2895-B | 48 | 169.6 | 8140.8 | O
M1-02 | 20 | SO | 482872 | 12 | 3 | C10281 | LTL | N45 | B07 | B | EA | OEM | 01 | 2022-01-11 | 2022-05-03 | AC-6787-03 | 69 | 164.22 | 11331.18 | O
M1-02 | 20 | SO | 489594 | 7 | 2 | C10256 | UPS GND | N30 | B11 | NC | EA | AERO | 01 | 2022-01-16 | 2022-06-01 | AC-3277-05 | 14 | 48.09 | 673.26 | P
M1-02 | 30 | SO | 481882 | 4 | 3 | C10973 | CUST PU | 2%10N30 | B14 | C | EA | MRO | 05 | 2021-12-09 | 2022-04-02 | AC-4457-B | 83 | 107.53 | 8924.99 | O
M1-02 | 20 | SO | 486157 | 3 | 1 | C10786 | BEST WAY | N45 | B11 | E | EA | OEM | 02 | 2022-01-24 | 2022-03-17 | AC-6260-10 | 26 | 53.49 | 1390.74 | O
M1-02 | 20 | BL | 484979 | 6 | 1 | C10256 | UPS GND | N30 | B07 | NC | EA | MRO | 01 | 2022-04-05 | 2022-05-20 | AC-1140-01 | 91 | 155.71 | 14169.61 | O
M1-02 | 20 | SO | 487138 | 1 | 1 | C10316 | BEST WAY | N60 | B07 | C | EA | MRO | 01 | 2021-11-24 | 2022-03-22 | AC-7669-B | 75 | 176.98 | 13273.5 | O
M1-02 | 30 | BL | 483558 | 4 | 2 | C10544 | UPS GND | N45 | B14 | D | EA | OEM | 05 | 2022-04-01 | 2022-05-06 | AC-2546-A | 16 | 159.29 | 2548.64 | O
M1-02 | 20 | BL | 481168 | 1 | 2 | C10305 | UPS GND | N45 | B07 | D | EA | OEM | 01 | 2022-03-03 | 2022-05-23 | AC-6482-03 | 54 | 162.06 | 8751.24 | O
M1-02 | 30 | SO | 484266 | 11 | 1 | C10664 | FDX 2D | N30 | B14 | A | EA | MRO | 05 | 2022-02-11 | 2022-06-09 | AC-7692-03 | 12 | 162.76 | 1953.12 | O
M1-02 | 20 | BL | 489519 | 7 | 2 | C10758 | BEST WAY | N45 | B07 | NC | EA | DEF | 02 | 2022-03-10 | 2022-04-14 | AC-7933-10 | 3 | 133.82 | 401.46 | P
M1-02 | 20 | SO | 482447 | 6 | 1 | C10860 | BEST WAY | N60 | B22 | NC | EA | MRO | 05 | 2022-02-11 | 2022-04-09 | AC-8774-01 | 35 | 131.51 | 4602.85 | O
M1-02 | 20 | BL | 484369 | 3 | 3 | C10420 | BEST WAY | N45 | B22 | D | EA | DEF | 01 | 2022-01-16 | 2022-05-23 | AC-6550-01 | 78 | 44.44 | 3466.32 | O
M1-02 | 30 | SO | 482131 | 1 | 1 | C10456 | UPS GND | N30 | B14 | C | EA | OEM | 05 | 2022-02-10 | 2022-04-19 | AC-7846-05 | 21 | 62.82 | 1319.22 | O
M1-02 | 30 | SO | 482943 | 9 | 0 | C10817 | CUST PU | N30 | B22 | A | EA | OEM | 02 | 2021-10-12 | 2022-01-06 | AC-5035-B | 85 | 90.55 | 7696.75 | O
M1-02 | 20 | SO | 481239 | 5 | 3 | C10786 | LTL | N30 | B22 | B | EA | DEF | 02 | 2022-01-08 | 2022-04-10 | AC-1584-B | 90 | 170.66 | 15359.4 | O
M1-02 | 30 | SO | 486052 | 3 | 0 | C10806 | BEST WAY | N45 | B22 | A | EA | MRO | 01 | 2022-02-19 | 2022-03-31 | AC-8381-10 | 81 | 65.39 | 5296.59 | O
M1-02 | 30 | SO | 485828 | 3 | 1 | C10186 | CUST PU | N45 | B22 | C | EA | MRO | 02 | 2022-03-16 | 2022-06-09 | AC-9718-03 | 13 | 143.51 | 1865.63 | O
M1-02 | 20 | SO | 486546 | 10 | 3 | C10746 | FDX 2D | 2%10N30 | B22 | A | EA | DEF | 02 | 2022-03-23 | 2022-06-09 | AC-2895-B | 34 | 162.24 | 5516.16 | O
M1-02 | 30 | SO | 482240 | 7 | 3 | C10560 | UPS GND | N60 | B14 | NC | EA | OEM | 05 | 2022-03-11 | 2022-05-23 | AC-5303-B | 10 | 154.47 | 1544.7 | O
M1-02 | 30 | SO | 481972 | 1 | 1 | C10350 | FDX 2D | 2%10N30 | B11 | E | EA | MRO | 05 | 2022-03-05 | 2022-04-29 | AC-2063-10 | 59 | 164.51 | 9706.09 | O
M1-02 | 20 | SO | 489642 | 11 | 1 | C10951 | FDX 2D | N60 | B11 | B | EA | DEF | 01 | 2022-01-07 | 2022-03-21 | AC-6859-A | 8 | 152.05 | 1216.4 | P
M1-02 | 20 | BL | 483484 | 9 | 2 | C10170 | CUST PU | N30 | B11 | C | EA | MRO | 01 | 2021-12-31 | 2022-02-15 | AC-9748-05 | 36 | 138.14 | 4973.04 | O
M1-02 | 20 | SO | 488823 | 6 | 3 | C10973 | FDX 2D | 2%10N30 | B07 | A | EA | AERO | 05 | 2021-07-28 | 2021-09-15 | AC-6493-05 | 37 | 56.56 | 2092.72 | P
M1-02 | 20 | BL | 487742 | 5 | 1 | C10281 | BEST WAY | 2%10N30 | B14 | D | EA | AERO | 01 | 2021-04-29 | 2021-08-08 | AC-3103-B | 10 | 129.45 | 1294.5 | P
M1-02 | 30 | SO | 487084 | 10 | 0 | C10664 | LTL | N60 | B14 | E | EA | DEF | 01 | 2022-01-24 | 2022-04-02 | AC-8608-B | 99 | 83.14 | 8230.86 | O
M1-02 | 30 | SO | 481909 | 7 | 1 | C10256 | LTL | N60 | B14 | E | EA | MRO | 02 | 2022-02-24 | 2022-06-06 | AC-7160-A | 14 | 162.85 | 2279.9 | O
M1-02 | 30 | SO | 480157 | 12 | 0 | C10170 | BEST WAY | N60 | B07 | A | EA | AERO | 02 | 2022-03-28 | 2022-06-04 | AC-2755-05 | 43 | 57.21 | 2460.03 | O
M1-02 | 20 | SO | 487437 | 4 | 0 | C10170 | UPS GND | N60 | B07 | B | EA | OEM | 05 | 2022-02-14 | 2022-05-26 | AC-9206-05 | 39 | 173.67 | 6773.13 | P
M1-02 | 20 | BL | 482276 | 1 | 1 | C10461 | FDX 2D | N60 | B11 | E | EA | MRO | 02 | 2021-12-26 | 2022-05-01 | AC-6273-05 | 41 | 62.07 | 2544.87 | O
M1-02 | 20 | SO | 487110 | 5 | 0 | C10817 | BEST WAY | N60 | B14 | D | EA | DEF | 05 | 2022-01-16 | 2022-05-30 | AC-6261-05 | 26 | 141.78 | 3686.28 | O
M1-02 | 30 | SO | 483169 | 5 | 1 | C10817 | BEST WAY | N60 | B22 | D | EA | DEF | 02 | 2022-02-04 | 2022-04-12 | AC-7789-05 | 71 | 124.79 | 8860.09 | O
M1-02 | 20 | BL | 484927 | 4 | 3 | C10256 | CUST PU | 2%10N30 | B07 | B | EA | DEF | 02 | 2022-03-23 | 2022-05-24 | AC-8955-02 | 83 | 129.55 | 10752.65 | O
M1-02 | 20 | SO | 487563 | 12 | 0 | C10824 | BEST WAY | 2%10N30 | B22 | D | EA | DEF | 01 | 2021-08-26 | 2021-12-15 | AC-7219-A | 44 | 58.25 | 2563 | P
M1-02 | 30 | SO | 488140 | 5 | 0 | C10568 | LTL | N45 | B14 | C | EA | MRO | 01 | 2021-05-30 | 2021-09-21 | AC-4980-01 | 40 | 95.01 | 3800.4 | P
M1-02 | 20 | SO | 486693 | 1 | 1 | C10498 | CUST PU | N45 | B11 | B | EA | AERO | 01 | 2022-01-09 | 2022-05-27 | AC-5291-10 | 8 | 96.39 | 771.12 | O
M1-02 | 20 | SO | 489093 | 2 | 1 | C10806 | FDX 2D | N60 | B11 | D | EA | DEF | 05 | 2022-02-17 | 2022-04-27 | AC-5148-01 | 32 | 35 | 1120 | P
M1-02 | 30 | SO | 483887 | 12 | 2 | C10455 | UPS GND | N60 | B11 | E | EA | AERO | 02 | 2022-01-03 | 2022-05-16 | AC-8880-03 | 23 | 160.27 | 3686.21 | O
M1-02 | 30 | SO | 484847 | 12 | 2 | C10264 | UPS GND | N30 | B11 | B | EA | MRO | 01 | 2022-01-24 | 2022-03-25 | AC-9400-03 | 56 | 115.17 | 6449.52 | O
M1-02 | 30 | SO | 487796 | 12 | 3 | C10264 | FDX 2D | N60 | B07 | C | EA | AERO | 01 | 2021-04-12 | 2021-08-29 | AC-7397-01 | 4 | 113.27 | 453.08 | P
M1-02 | 30 | SO | 485152 | 8 | 3 | C10256 | LTL | N30 | B11 | B | EA | MRO | 02 | 2022-01-12 | 2022-03-28 | AC-8370-A | 97 | 57.57 | 5584.29 | O
M1-02 | 30 | BL | 486019 | 9 | 3 | C10817 | BEST WAY | N30 | B07 | D | EA | MRO | 01 | 2021-06-26 | 2021-10-17 | AC-5010-A | 14 | 83.09 | 1163.26 | O
M1-02 | 20 | SO | 487002 | 1 | 0 | C10170 | BEST WAY | N60 | B22 | E | EA | OEM | 01 | 2022-03-12 | 2022-05-30 | AC-2084-A | 70 | 78.95 | 5526.5 | O
M1-02 | 20 | SO | 482637 | 12 | 1 | C10281 | LTL | N60 | B07 | B | EA | MRO | 05 | 2022-04-13 | 2022-05-24 | AC-4906-02 | 89 | 97.78 | 8702.42 | O
M1-02 | 30 | SO | 483737 | 12 | 2 | C10786 | UPS GND | 2%10N30 | B11 | A | EA | AERO | 01 | 2021-10-17 | 2022-02-11 | AC-5838-05 | 36 | 128.59 | 4629.24 | O
M1-02 | 30 | SO | 482450 | 5 | 1 | C10327 | CUST PU | 2%10N30 | B11 | B | EA | AERO | 02 | 2022-01-02 | 2022-04-20 | AC-1073-B | 45 | 116.01 | 5220.45 | O
M1-02 | 30 | SO | 481675 | 4 | 2 | C10436 | BEST WAY | N60 | B11 | NC | EA | DEF | 05 | 2022-01-13 | 2022-05-16 | AC-7303-05 | 68 | 88.45 | 6014.6 | O
M1-02 | 20 | SO | 484487 | 5 | 1 | C10900 | UPS GND | N60 | B07 | NC | EA | DEF | 01 | 2022-01-17 | 2022-03-23 | AC-5097-02 | 14 | 144.42 | 2021.88 | O
M1-02 | 20 | SO | 481792 | 8 | 3 | C10900 | BEST WAY | 2%10N30 | B11 | A | EA | MRO | 02 | 2021-12-07 | 2022-01-19 | AC-9725-A | 78 | 114.42 | 8924.76 | O
M1-02 | 20 | SO | 488916 | 9 | 0 | C10746 | FDX 2D | N30 | B22 | E | EA | DEF | 02 | 2021-05-29 | 2021-09-03 | AC-2322-03 | 32 | 114.35 | 3659.2 | P
M1-02 | 30 | SO | 482713 | 4 | 0 | C10280 | FDX 2D | 2%10N30 | B22 | E | EA | OEM | 02 | 2022-02-22 | 2022-06-07 | AC-5284-02 | 32 | 130.42 | 4173.44 | O
M1-02 | 30 | SO | 488404 | 5 | 3 | C10544 | FDX 2D | N30 | B11 | C | EA | AERO | 02 | 2021-09-04 | 2021-10-11 | AC-5085-05 | 5 | 54.96 | 274.8 | P
M1-02 | 30 | BL | 482864 | 8 | 3 | C10525 | UPS GND | 2%10N30 | B14 | D | EA | DEF | 01 | 2022-03-17 | 2022-04-30 | AC-7877-03 | 55 | 159.87 | 8792.85 | O
M1-02 | 30 | SO | 489736 | 12 | 3 | C10327 | BEST WAY | 2%10N30 | B14 | E | EA | DEF | 01 | 2022-04-23 | 2022-05-25 | AC-7933-10 | 21 | 189.85 | 3986.85 | P
M1-02 | 30 | SO | 486036 | 2 | 1 | C10688 | CUST PU | 2%10N30 | B14 | B | EA | AERO | 05 | 2022-01-27 | 2022-05-20 | AC-3275-03 | 94 | 177.43 | 16678.42 | O
M1-02 | 30 | SO | 487824 | 1 | 3 | C10526 | LTL | N30 | B22 | NC | EA | DEF | 01 | 2021-11-09 | 2022-03-01 | AC-7794-A | 54 | 140.35 | 7578.9 | P
M1-02 | 30 | SO | 483186 | 7 | 2 | C10456 | UPS GND | N30 | B14 | A | EA | DEF | 01 | 2021-06-25 | 2021-10-17 | AC-4736-B | 98 | 95.58 | 9366.84 | O
M1-02 | 30 | BL | 480516 | 1 | 3 | C10519 | LTL | N30 | B07 | C | EA | DEF | 01 | 2021-08-31 | 2021-12-08 | AC-8073-10 | 17 | 79.32 | 1348.44 | O
M1-02 | 30 | BL | 486656 | 8 | 3 | C10455 | FDX 2D | 2%10N30 | B11 | B | EA | DEF | 01 | 2021-12-15 | 2022-03-21 | AC-5249-10 | 11 | 50.68 | 557.48 | O
M1-02 | 30 | BL | 488405 | 2 | 3 | C10787 | CUST PU | 2%10N30 | B07 | B | EA | OEM | 01 | 2021-12-08 | 2022-03-20 | AC-3696-02 | 28 | 99.33 | 2781.24 | P
M1-02 | 30 | SO | 480841 | 9 | 1 | C10936 | CUST PU | N60 | B14 | E | EA | DEF | 01 | 2021-11-01 | 2022-03-03 | AC-7648-01 | 95 | 99.05 | 9409.75 | O
M1-02 | 20 | SO | 488849 | 5 | 3 | C10706 | FDX 2D | N30 | B07 | E | EA | AERO | 01 | 2022-01-14 | 2022-04-22 | AC-6632-01 | 6 | 114.35 | 686.1 | P
M1-02 | 30 | SO | 487632 | 11 | 2 | C10273 | UPS GND | N30 | B14 | D | EA | OEM | 01 | 2021-05-19 | 2021-07-09 | AC-3287-02 | 14 | 179.23 | 2509.22 | P
M1-02 | 30 | SO | 488030 | 8 | 3 | C10526 | CUST PU | N60 | B11 | C | EA | AERO | 02 | 2021-11-27 | 2022-04-13 | AC-3047-05 | 45 | 173.07 | 7788.15 | P
M1-02 | 30 | SO | 480776 | 5 | 3 | C10568 | FDX 2D | N45 | B07 | E | EA | OEM | 05 | 2021-11-22 | 2022-04-07 | AC-3282-10 | 97 | 175.52 | 17025.44 | O
M1-02 | 20 | SO | 480820 | 7 | 2 | C10806 | BEST WAY | N45 | B14 | E | EA | MRO | 05 | 2021-05-09 | 2021-08-26 | AC-6027-B | 64 | 134.42 | 8602.88 | O
M1-02 | 30 | SO | 484503 | 1 | 0 | C10787 | FDX 2D | N45 | B11 | D | EA | MRO | 05 | 2022-01-03 | 2022-04-08 | AC-2308-A | 60 | 134.69 | 8081.4 | O
M1-02 | 20 | SO | 487872 | 12 | 0 | C10900 | FDX 2D | N60 | B22 | NC | EA | MRO | 05 | 2021-05-13 | 2021-06-16 | AC-3231-10 | 49 | 50.03 | 2451.47 | P
M1-02 | 30 | SO | 481839 | 7 | 2 | C10501 | FDX 2D | N60 | B14 | E | EA | OEM | 05 | 2022-01-22 | 2022-05-29 | AC-3420-02 | 22 | 56.25 | 1237.5 | O
M1-02 | 30 | SO | 480489 | 9 | 1 | C10568 | FDX 2D | N60 | B11 | NC | EA | OEM | 05 | 2022-03-19 | 2022-04-27 | AC-6482-03 | 14 | 128.24 | 1795.36 | O
M1-02 | 20 | SO | 487491 | 6 | 3 | C10273 | BEST WAY | N45 | B14 | D | EA | MRO | 05 | 2021-11-16 | 2021-12-15 | AC-3359-A | 9 | 157.79 | 1420.11 | P
M1-02 | 20 | SO | 487367 | 6 | 1 | C10211 | UPS GND | N30 | B07 | D | EA | OEM | 02 | 2022-02-28 | 2022-04-21 | AC-9448-05 | 25 | 131.8 | 3295 | P
M1-02 | 20 | SO | 486531 | 3 | 2 | C10752 | CUST PU | N30 | B07 | NC | EA | DEF | 02 | 2021-04-01 | 2021-07-07 | AC-9655-B | 72 | 107.05 | 7707.6 | O
M1-02 | 20 | SO | 488274 | 11 | 3 | C10455 | FDX 2D | N60 | B07 | NC | EA | OEM | 05 | 2021-11-29 | 2022-01-04 | AC-4607-A | 5 | 159.17 | 795.85 | P
M1-02 | 30 | SO | 487584 | 2 | 2 | C10544 | FDX 2D | N60 | B14 | NC | EA | OEM | 05 | 2021-12-16 | 2022-03-30 | AC-7338-02 | 50 | 84.56 | 4228 | P
M1-02 | 30 | SO | 487042 | 1 | 2 | C10966 | BEST WAY | N45 | B14 | A | EA | AERO | 02 | 2022-01-07 | 2022-04-19 | AC-9183-05 | 14 | 95.92 | 1342.88 | O
M1-02 | 30 | BL | 486398 | 1 | 1 | C10249 | LTL | N30 | B22 | NC | EA | MRO | 01 | 2022-01-26 | 2022-06-09 | AC-3053-03 | 45 | 77 | 3465 | O
M1-02 | 30 | BL | 486817 | 11 | 1 | C10900 | UPS GND | N30 | B14 | A | EA | AERO | 02 | 2022-01-24 | 2022-03-29 | AC-3067-10 | 8 | 175.64 | 1405.12 | O
M1-02 | 30 | BL | 483276 | 6 | 3 | C10252 | CUST PU | N30 | B22 | NC | EA | MRO | 05 | 2021-10-02 | 2021-12-12 | AC-8974-05 | 19 | 117.87 | 2239.53 | O
M1-02 | 30 | SO | 489612 | 3 | 2 | C10544 | FDX 2D | 2%10N30 | B14 | E | EA | OEM | 02 | 2022-01-11 | 2022-05-14 | AC-1891-03 | 6 | 73.12 | 438.72 | P
M1-02 | 30 | SO | 489578 | 3 | 3 | C10332 | CUST PU | 2%10N30 | B14 | E | EA | AERO | 01 | 2022-04-07 | 2022-05-10 | AC-8965-05 | 24 | 96.51 | 2316.24 | P
M1-02 | 30 | BL | 480487 | 6 | 3 | C10377 | CUST PU | N30 | B07 | D | EA | DEF | 01 | 2022-01-15 | 2022-04-19 | AC-8358-03 | 6 | 85.32 | 511.92 | O
M1-02 | 20 | SO | 483652 | 7 | 2 | C10973 | LTL | N30 | B22 | C | EA | AERO | 02 | 2022-04-05 | 2022-06-03 | AC-2924-03 | 54 | 98.98 | 5344.92 | O
M1-02 | 30 | SO | 482333 | 8 | 3 | C10281 | CUST PU | N45 | B07 | C | EA | AERO | 02 | 2022-05-02 | 2022-06-09 | AC-1179-B | 70 | 175.07 | 12254.9 | O
M1-02 | 20 | SO | 481056 | 11 | 3 | C10501 | UPS GND | N60 | B07 | C | EA | OEM | 01 | 2022-01-12 | 2022-04-28 | AC-1463-02 | 22 | 149.34 | 3285.48 | O
M1-02 | 30 | SO | 485914 | 6 | 0 | C10936 | CUST PU | 2%10N30 | B11 | B | EA | MRO | 02 | 2021-03-23 | 2021-07-25 | AC-4104-10 | 99 | 94.77 | 9382.23 | O
M1-02 | 30 | SO | 486172 | 6 | 2 | C10786 | FDX 2D | N30 | B11 | D | EA | OEM | 02 | 2022-03-11 | 2022-04-25 | AC-6040-10 | 63 | 87 | 5481 | O
M1-02 | 20 | SO | 488257 | 6 | 0 | C10327 | FDX 2D | N30 | B14 | C | EA | AERO | 01 | 2021-11-16 | 2022-03-22 | AC-8994-B | 27 | 139.39 | 3763.53 | P
M1-02 | 30 | SO | 488489 | 6 | 3 | C10455 | LTL | N60 | B14 | D | EA | OEM | 02 | 2021-12-19 | 2022-04-28 | AC-8035-02 | 32 | 76.01 | 2432.32 | P
M1-02 | 20 | SO | 480118 | 9 | 1 | C10966 | LTL | 2%10N30 | B14 | NC | EA | DEF | 01 | 2022-01-11 | 2022-04-14 | AC-2755-05 | 76 | 173.18 | 13161.68 | O
M1-02 | 20 | SO | 484672 | 11 | 3 | C10589 | CUST PU | N30 | B22 | D | EA | MRO | 01 | 2022-04-21 | 2022-05-25 | AC-1559-05 | 8 | 150.27 | 1202.16 | O
M1-02 | 20 | BL | 483866 | 7 | 0 | C10544 | UPS GND | 2%10N30 | B22 | C | EA | OEM | 05 | 2022-02-18 | 2022-05-30 | AC-4104-10 | 23 | 54.78 | 1259.94 | O
M1-02 | 20 | SO | 485194 | 7 | 2 | C10787 | FDX 2D | N45 | B14 | D | EA | AERO | 02 | 2022-02-20 | 2022-06-07 | AC-6612-B | 39 | 86.28 | 3364.92 | O
M1-02 | 20 | SO | 489134 | 3 | 1 | C10332 | FDX 2D | N45 | B07 | B | EA | DEF | 02 | 2021-11-05 | 2022-03-22 | AC-1347-B | 19 | 182.45 | 3466.55 | P
M1-02 | 30 | SO | 481221 | 7 | 3 | C10186 | LTL | N60 | B07 | C | EA | MRO | 02 | 2022-03-05 | 2022-04-15 | AC-3060-02 | 73 | 80.21 | 5855.33 | O
M1-02 | 30 | BL | 483107 | 8 | 1 | C10252 | CUST PU | N45 | B11 | NC | EA | AERO | 01 | 2022-03-07 | 2022-05-01 | AC-1568-A | 69 | 151.24 | 10435.56 | O
M1-02 | 30 | SO | 482340 | 2 | 2 | C10589 | LTL | N60 | B11 | D | EA | MRO | 01 | 2022-01-03 | 2022-05-20 | AC-4693-05 | 95 | 172.19 | 16358.05 | O
M1-02 | 30 | SO | 482549 | 8 | 2 | C10950 | CUST PU | N30 | B11 | A | EA | AERO | 01 | 2022-03-08 | 2022-05-20 | AC-7603-02 | 88 | 162.17 | 14270.96 | O
M1-02 | 30 | SO | 485012 | 2 | 2 | C10951 | CUST PU | N30 | B07 | B | EA | DEF | 02 | 2021-12-06 | 2022-04-13 | AC-7511-03 | 75 | 163.87 | 12290.25 | O
M1-02 | 30 | SO | 489364 | 6 | 0 | C10264 | CUST PU | 2%10N30 | B11 | D | EA | OEM | 02 | 2021-12-19 | 2022-04-21 | AC-8302-05 | 6 | 80.37 | 482.22 | P
M1-02 | 30 | BL | 480152 | 12 | 0 | C10420 | BEST WAY | N60 | B11 | C | EA | MRO | 05 | 2021-08-04 | 2021-09-04 | AC-9159-A | 95 | 94.25 | 8953.75 | O
M1-02 | 30 | SO | 484535 | 7 | 2 | C10560 | FDX 2D | 2%10N30 | B22 | A | EA | DEF | 05 | 2021-12-05 | 2022-03-24 | AC-6261-05 | 12 | 98.65 | 1183.8 | O
M1-02 | 20 | SO | 488616 | 8 | 1 | C10519 | LTL | 2%10N30 | B07 | C | EA | AERO | 05 | 2021-10-23 | 2022-01-15 | AC-8814-03 | 38 | 76.66 | 2913.08 | P
M1-02 | 30 | SO | 487721 | 5 | 1 | C10966 | CUST PU | N60 | B11 | NC | EA | AERO | 01 | 2021-03-22 | 2021-06-10 | AC-7375-B | 20 | 109.54 | 2190.8 | P
M1-02 | 20 | BL | 486587 | 2 | 2 | C10973 | FDX 2D | N30 | B22 | NC | EA | DEF | 01 | 2021-12-26 | 2022-04-01 | AC-1170-05 | 23 | 165.47 | 3805.81 | O
M1-02 | 20 | BL | 486536 | 12 | 1 | C10316 | UPS GND | N45 | B07 | C | EA | AERO | 05 | 2022-01-15 | 2022-04-03 | AC-2938-03 | 50 | 86.21 | 4310.5 | O
M1-02 | 20 | BL | 485487 | 10 | 0 | C10186 | FDX 2D | N30 | B07 | A | EA | MRO | 02 | 2022-02-18 | 2022-04-04 | AC-4101-02 | 96 | 72.62 | 6971.52 | O
M1-02 | 20 | BL | 487544 | 2 | 1 | C10568 | FDX 2D | 2%10N30 | B22 | A | EA | DEF | 01 | 2021-05-15 | 2021-07-27 | AC-7375-B | 19 | 125.91 | 2392.29 | P
M1-02 | 20 | BL | 488508 | 4 | 0 | C10211 | BEST WAY | N60 | B07 | E | EA | DEF | 05 | 2021-08-30 | 2021-10-01 | AC-6792-B | 4 | 53.29 | 213.16 | P
M1-02 | 20 | SO | 485226 | 8 | 0 | C10170 | BEST WAY | N60 | B11 | NC | EA | DEF | 02 | 2022-02-01 | 2022-05-03 | AC-8361-02 | 4 | 144.57 | 578.28 | O
M1-02 | 20 | SO | 483220 | 2 | 2 | C10273 | LTL | 2%10N30 | B14 | B | EA | OEM | 02 | 2022-02-20 | 2022-05-24 | AC-6205-A | 41 | 83.44 | 3421.04 | O
M1-02 | 20 | SO | 486534 | 5 | 3 | C10560 | FDX 2D | N45 | B11 | C | EA | MRO | 02 | 2021-12-10 | 2022-02-21 | AC-9427-05 | 68 | 150.39 | 10226.52 | O
M1-02 | 30 | SO | 480100 | 7 | 2 | C10501 | CUST PU | N60 | B07 | D | EA | OEM | 05 | 2022-01-08 | 2022-05-01 | AC-4023-03 | 96 | 115.71 | 11108.16 | O
M1-02 | 30 | BL | 489775 | 1 | 0 | C10251 | UPS GND | 2%10N30 | B07 | A | EA | OEM | 01 | 2021-11-14 | 2022-03-16 | AC-9385-03 | 34 | 167.64 | 5699.76 | P
M1-02 | 30 | SO | 485298 | 4 | 0 | C10936 | LTL | N45 | B22 | A | EA | DEF | 01 | 2022-01-28 | 2022-03-23 | AC-7688-10 | 51 | 95.29 | 4859.79 | O
M1-02 | 20 | BL | 482066 | 12 | 1 | C10170 | BEST WAY | N30 | B22 | C | EA | OEM | 02 | 2022-02-07 | 2022-03-27 | AC-2677-01 | 84 | 51.19 | 4299.96 | O
M1-02 | 30 | BL | 486591 | 3 | 1 | C10519 | BEST WAY | 2%10N30 | B11 | D | EA | MRO | 02 | 2021-12-29 | 2022-05-15 | AC-9491-03 | 56 | 56.91 | 3186.96 | O
M1-02 | 30 | SO | 485489 | 2 | 3 | C10332 | FDX 2D | N60 | B22 | C | EA | OEM | 02 | 2022-03-27 | 2022-04-25 | AC-1637-A | 37 | 104.59 | 3869.83 | O
M1-02 | 20 | SO | 481886 | 2 | 0 | C10305 | BEST WAY | N30 | B22 | B | EA | DEF | 05 | 2022-02-12 | 2022-06-09 | AC-2167-03 | 36 | 137.16 | 4937.76 | O
M1-02 | 20 | SO | 485322 | 3 | 1 | C10951 | BEST WAY | N30 | B07 | NC | EA | AERO | 01 | 2022-02-21 | 2022-05-04 | AC-3829-05 | 48 | 46.26 | 2220.48 | O
M1-02 | 30 | SO | 486638 | 8 | 2 | C10264 | UPS GND | N30 | B11 | A | EA | OEM | 02 | 2021-12-29 | 2022-04-29 | AC-2723-03 | 73 | 156.67 | 11436.91 | O
M1-02 | 30 | BL | 482339 | 2 | 1 | C10455 | FDX 2D | N30 | B07 | D | EA | OEM | 02 | 2021-12-13 | 2022-03-15 | AC-9652-03 | 41 | 60.24 | 2469.84 | O
M1-02 | 20 | SO | 484799 | 4 | 0 | C10280 | UPS GND | N60 | B07 | E | EA | DEF | 01 | 2022-02-13 | 2022-06-10 | AC-4134-03 | 12 | 83.98 | 1007.76 | O
M1-02 | 30 | BL | 482617 | 9 | 3 | C10331 | UPS GND | N45 | B11 | C | EA | OEM | 02 | 2021-08-20 | 2021-10-31 | AC-9725-A | 34 | 155.85 | 5298.9 | O
M1-02 | 30 | BL | 485409 | 7 | 1 | C10321 | UPS GND | N45 | B22 | NC | EA | DEF | 05 | 2021-12-29 | 2022-04-14 | AC-4208-A | 13 | 148.26 | 1927.38 | O
M1-02 | 30 | SO | 481017 | 11 | 2 | C10706 | CUST PU | N30 | B22 | NC | EA | MRO | 02 | 2021-08-15 | 2021-11-10 | AC-1565-10 | 7 | 76.35 | 534.45 | O
M1-02 | 30 | SO | 481566 | 12 | 3 | C10695 | LTL | 2%10N30 | B22 | NC | EA | DEF | 05 | 2022-04-02 | 2022-05-10 | AC-3833-03 | 65 | 67.09 | 4360.85 | O
M1-02 | 20 | BL | 482476 | 3 | 3 | C10455 | LTL | N60 | B14 | B | EA | DEF | 02 | 2022-01-21 | 2022-05-30 | AC-7511-03 | 45 | 160.02 | 7200.9 | O
M1-02 | 30 | SO | 487605 | 7 | 1 | C10327 | UPS GND | 2%10N30 | B14 | B | EA | DEF | 02 | 2021-08-14 | 2021-09-11 | AC-2274-A | 30 | 136.26 | 4087.8 | P
M1-02 | 30 | BL | 481076 | 1 | 2 | C10817 | LTL | N30 | B07 | D | EA | DEF | 02 | 2022-02-04 | 2022-04-20 | AC-3780-A | 52 | 145.41 | 7561.32 | O
M1-02 | 30 | SO | 486826 | 8 | 3 | C10436 | UPS GND | 2%10N30 | B07 | B | EA | DEF | 02 | 2021-04-19 | 2021-08-06 | AC-2484-A | 81 | 162.13 | 13132.53 | O
M1-02 | 20 | SO | 489264 | 8 | 0 | C10688 | BEST WAY | N60 | B11 | A | EA | DEF | 05 | 2022-01-08 | 2022-03-24 | AC-6197-02 | 22 | 63.98 | 1407.56 | P
M1-02 | 20 | SO | 489581 | 6 | 1 | C10752 | UPS GND | N30 | B07 | B | EA | DEF | 02 | 2022-01-20 | 2022-03-09 | AC-7348-02 | 29 | 133.25 | 3864.25 | P
M1-02 | 30 | SO | 480360 | 5 | 1 | C10186 | LTL | N60 | B07 | E | EA | DEF | 01 | 2021-12-14 | 2022-01-17 | AC-9003-03 | 19 | 145.89 | 2771.91 | O
M1-02 | 30 | SO | 487366 | 6 | 0 | C10281 | UPS GND | N30 | B14 | D | EA | OEM | 02 | 2022-02-19 | 2022-06-01 | AC-2960-10 | 39 | 138.1 | 5385.9 | P
M1-02 | 30 | SO | 487970 | 12 | 0 | C10973 | CUST PU | 2%10N30 | B14 | A | EA | DEF | 05 | 2021-06-27 | 2021-11-06 | AC-3696-02 | 24 | 162.15 | 3891.6 | P
M1-02 | 20 | SO | 481165 | 2 | 3 | C10281 | CUST PU | N45 | B22 | C | EA | DEF | 05 | 2022-04-14 | 2022-05-18 | AC-7626-05 | 23 | 152.97 | 3518.31 | O
M1-02 | 30 | BL | 484098 | 5 | 3 | C10211 | LTL | N45 | B22 | C | EA | MRO | 02 | 2022-04-08 | 2022-05-30 | AC-8608-B | 7 | 132.86 | 930.02 | O
M1-02 | 30 | SO | 488387 | 12 | 1 | C10688 | CUST PU | N45 | B14 | B | EA | MRO | 01 | 2021-12-05 | 2022-01-07 | AC-3231-10 | 13 | 86.29 | 1121.77 | P
M1-02 | 20 | SO | 482231 | 3 | 3 | C10385 | CUST PU | 2%10N30 | B22 | NC | EA | OEM | 01 | 2022-01-12 | 2022-05-18 | AC-7355-A | 29 | 155.37 | 4505.73 | O
M1-02 | 20 | SO | 481134 | 10 | 1 | C10936 | LTL | 2%10N30 | B14 | E | EA | MRO | 05 | 2022-04-20 | 2022-05-24 | AC-3597-01 | 19 | 43.56 | 827.64 | O
M1-02 | 30 | SO | 487857 | 8 | 0 | C10664 | FDX 2D | 2%10N30 | B22 | B | EA | MRO | 01 | 2021-10-12 | 2022-02-02 | AC-9206-05 | 14 | 121.62 | 1702.68 | P
M1-02 | 30 | SO | 486344 | 9 | 0 | C10940 | UPS GND | N30 | B14 | A | EA | MRO | 05 | 2022-01-26 | 2022-05-22 | AC-7714-10 | 22 | 61.55 | 1354.1 | O
M1-02 | 20 | BL | 482186 | 7 | 2 | C10498 | CUST PU | N45 | B11 | E | EA | DEF | 02 | 2022-01-16 | 2022-04-07 | AC-6234-02 | 13 | 163.01 | 2119.13 | O
M1-02 | 20 | BL | 483801 | 6 | 0 | C10758 | LTL | N60 | B11 | A | EA | MRO | 01 | 2021-05-29 | 2021-07-23 | AC-5341-10 | 96 | 49.94 | 4794.24 | O
M1-02 | 30 | SO | 486339 | 2 | 0 | C10787 | UPS GND | N60 | B07 | A | EA | OEM | 05 | 2022-04-02 | 2022-06-10 | AC-8540-01 | 7 | 69.09 | 483.63 | O
M1-02 | 30 | SO | 482095 | 11 | 3 | C10350 | FDX 2D | N30 | B11 | NC | EA | DEF | 02 | 2022-05-09 | 2022-06-10 | AC-9543-B | 44 | 118.97 | 5234.68 | O
M1-02 | 20 | SO | 485157 | 11 | 3 | C10436 | UPS GND | N45 | B14 | NC | EA | AERO | 05 | 2021-10-28 | 2021-12-05 | AC-1574-05 | 75 | 166.62 | 12496.5 | O
M1-02 | 20 | SO | 483124 | 5 | 1 | C10273 | CUST PU | N45 | B14 | B | EA | DEF | 02 | 2022-01-14 | 2022-05-13 | AC-2677-01 | 43 | 73.49 | 3160.07 | O
M1-02 | 20 | SO | 481934 | 5 | 3 | C10664 | CUST PU | 2%10N30 | B11 | A | EA | DEF | 05 | 2022-01-11 | 2022-05-29 | AC-7406-05 | 92 | 43.45 | 3997.4 | O
M1-02 | 20 | BL | 483742 | 1 | 0 | C10350 | CUST PU | N45 | B11 | B | EA | AERO | 05 | 2022-02-17 | 2022-05-09 | AC-8872-B | 18 | 155.6 | 2800.8 | O
M1-02 | 20 | SO | 484221 | 4 | 3 | C10186 | CUST PU | N45 | B07 | C | EA | DEF | 05 | 2021-11-20 | 2022-02-01 | AC-2619-01 | 71 | 120.04 | 8522.84 | O
M1-02 | 30 | SO | 480692 | 8 | 3 | C10544 | LTL | N45 | B07 | D | EA | MRO | 02 | 2021-09-12 | 2021-12-02 | AC-8774-01 | 51 | 173.21 | 8833.71 | O
M1-02 | 30 | SO | 488747 | 6 | 0 | C10806 | BEST WAY | 2%10N30 | B14 | C | EA | DEF | 02 | 2021-11-22 | 2022-03-10 | AC-3257-03 | 43 | 68.63 | 2951.09 | P
M1-02 | 30 | SO | 488343 | 4 | 0 | C10498 | FDX 2D | 2%10N30 | B22 | NC | EA | OEM | 05 | 2021-07-06 | 2021-08-21 | AC-3471-10 | 18 | 146.96 | 2645.28 | P
M1-02 | 30 | SO | 484860 | 9 | 2 | C10706 | CUST PU | N60 | B14 | E | EA | MRO | 02 | 2021-12-29 | 2022-03-04 | AC-3896-A | 29 | 64.43 | 1868.47 | O
M1-02 | 20 | SO | 488683 | 10 | 1 | C10786 | UPS GND | 2%10N30 | B11 | E | EA | AERO | 02 | 2021-09-08 | 2021-10-27 | AC-9453-B | 49 | 132.68 | 6501.32 | P
M1-02 | 20 | SO | 483267 | 9 | 0 | C10436 | LTL | N60 | B22 | E | EA | OEM | 02 | 2022-01-14 | 2022-04-21 | AC-1023-B | 47 | 169.04 | 7944.88 | O
M1-02 | 30 | BL | 485609 | 10 | 0 | C10461 | UPS GND | N60 | B14 | C | EA | MRO | 01 | 2021-11-20 | 2022-03-13 | AC-4936-01 | 57 | 131.09 | 7472.13 | O
M1-02 | 30 | SO | 482527 | 12 | 0 | C10456 | FDX 2D | 2%10N30 | B22 | B | EA | MRO | 02 | 2022-02-02 | 2022-04-26 | AC-3829-05 | 7 | 59.22 | 414.54 | O
M1-02 | 30 | SO | 486129 | 11 | 1 | C10951 | CUST PU | 2%10N30 | B22 | NC | EA | DEF | 02 | 2022-01-15 | 2022-05-23 | AC-3060-02 | 100 | 157.69 | 15769 | O
M1-02 | 20 | SO | 481716 | 6 | 3 | C10498 | LTL | N30 | B22 | B | EA | AERO | 01 | 2022-01-03 | 2022-05-18 | AC-1680-02 | 85 | 58.23 | 4949.55 | O
M1-02 | 30 | SO | 485551 | 12 | 2 | C10256 | CUST PU | N60 | B07 | A | EA | DEF | 01 | 2022-04-10 | 2022-05-21 | AC-9875-03 | 14 | 136.07 | 1904.98 | O
M1-02 | 20 | SO | 484309 | 3 | 0 | C10966 | CUST PU | N60 | B07 | A | EA | OEM | 02 | 2022-01-25 | 2022-05-24 | AC-7596-10 | 46 | 71.74 | 3300.04 | O
M1-02 | 20 | BL | 488137 | 1 | 1 | C10316 | BEST WAY | N45 | B22 | C | EA | DEF | 05 | 2021-09-23 | 2021-12-16 | AC-7572-B | 60 | 53.32 | 3199.2 | P
M1-02 | 20 | BL | 485510 | 3 | 2 | C10900 | LTL | N30 | B22 | D | EA | DEF | 02 | 2022-01-23 | 2022-04-11 | AC-6029-01 | 87 | 121.28 | 10551.36 | O
M1-02 | 30 | SO | 483665 | 6 | 0 | C10752 | CUST PU | N45 | B11 | C | EA | MRO | 02 | 2021-11-16 | 2022-03-20 | AC-1557-B | 34 | 74.62 | 2537.08 | O
M1-02 | 20 | SO | 485351 | 5 | 3 | C10501 | UPS GND | N45 | B14 | B | EA | DEF | 02 | 2021-03-20 | 2021-06-08 | AC-4953-10 | 18 | 168.84 | 3039.12 | O
M1-02 | 20 | SO | 484821 | 1 | 1 | C10350 | UPS GND | N45 | B07 | B | EA | OEM | 05 | 2021-09-08 | 2021-11-15 | AC-8712-03 | 58 | 101.63 | 5894.54 | O
M1-02 | 20 | BL | 486313 | 6 | 0 | C10385 | BEST WAY | N60 | B07 | D | EA | DEF | 05 | 2022-03-01 | 2022-04-12 | AC-1978-10 | 69 | 116.77 | 8057.13 | O
M1-02 | 20 | SO | 486027 | 9 | 0 | C10252 | BEST WAY | N60 | B22 | C | EA | OEM | 01 | 2021-12-12 | 2022-03-10 | AC-5278-A | 57 | 71.5 | 4075.5 | O
M1-02 | 20 | SO | 486611 | 3 | 2 | C10461 | BEST WAY | N45 | B07 | B | EA | OEM | 05 | 2021-06-17 | 2021-09-25 | AC-7596-10 | 85 | 107.76 | 9159.6 | O
M1-02 | 20 | SO | 488909 | 9 | 3 | C10756 | CUST PU | 2%10N30 | B07 | B | EA | OEM | 02 | 2022-04-09 | 2022-05-26 | AC-4011-03 | 25 | 103.06 | 2576.5 | P
M1-02 | 30 | SO | 480273 | 7 | 2 | C10436 | BEST WAY | 2%10N30 | B14 | E | EA | DEF | 02 | 2021-12-06 | 2022-04-16 | AC-4953-10 | 8 | 172.45 | 1379.6 | O
M1-02 | 20 | SO | 486471 | 4 | 0 | C10525 | LTL | 2%10N30 | B11 | A | EA | MRO | 02 | 2021-04-16 | 2021-08-30 | AC-3022-A | 41 | 150.18 | 6157.38 | O
M1-02 | 30 | SO | 486258 | 2 | 1 | C10456 | CUST PU | N45 | B07 | B | EA | OEM | 01 | 2021-11-09 | 2022-03-22 | AC-6605-03 | 67 | 157.9 | 10579.3 | O
M1-02 | 30 | BL | 487691 | 6 | 3 | C10664 | LTL | 2%10N30 | B07 | D | EA | DEF | 02 | 2021-08-21 | 2021-12-15 | AC-8814-03 | 15 | 106.79 | 1601.85 | P
M1-02 | 30 | SO | 487466 | 2 | 0 | C10519 | CUST PU | N45 | B14 | C | EA | MRO | 01 | 2022-02-25 | 2022-04-07 | AC-8328-B | 54 | 88.33 | 4769.82 | P
M1-02 | 20 | BL | 483076 | 9 | 2 | C10936 | CUST PU | N60 | B22 | A | EA | AERO | 02 | 2021-03-19 | 2021-05-28 | AC-7258-B | 76 | 72.41 | 5503.16 | O
M1-02 | 30 | SO | 482633 | 5 | 2 | C10787 | BEST WAY | N30 | B11 | D | EA | OEM | 05 | 2022-03-25 | 2022-06-10 | AC-4792-03 | 42 | 71.8 | 3015.6 | O
M1-02 | 20 | SO | 482169 | 4 | 3 | C10461 | UPS GND | N30 | B22 | NC | EA | MRO | 01 | 2022-01-14 | 2022-04-29 | AC-6053-01 | 59 | 78.1 | 4607.9 | O
M1-02 | 30 | SO | 481025 | 5 | 2 | C10966 | CUST PU | N60 | B07 | B | EA | AERO | 01 | 2022-04-12 | 2022-05-28 | AC-1254-10 | 19 | 166.93 | 3171.67 | O
M1-02 | 30 | SO | 483849 | 6 | 3 | C10321 | BEST WAY | N30 | B22 | C | EA | DEF | 05 | 2021-12-13 | 2022-01-29 | AC-6072-03 | 48 | 75.93 | 3644.64 | O
M1-02 | 30 | SO | 487839 | 7 | 1 | C10385 | BEST WAY | N60 | B14 | C | EA | MRO | 02 | 2022-02-09 | 2022-05-04 | AC-2371-A | 4 | 131.7 | 526.8 | P
M1-02 | 20 | SO | 488368 | 5 | 1 | C10817 | LTL | 2%10N30 | B07 | B | EA | OEM | 01 | 2021-08-29 | 2021-11-05 | AC-7572-B | 47 | 40.83 | 1919.01 | P
M1-02 | 20 | SO | 484189 | 12 | 2 | C10688 | BEST WAY | N30 | B07 | A | EA | MRO | 05 | 2021-09-15 | 2021-11-18 | AC-6565-B | 5 | 86.22 | 431.1 | O
M1-02 | 30 | SO | 489153 | 10 | 3 | C10936 | LTL | N45 | B11 | C | EA | DEF | 02 | 2022-04-02 | 2022-05-04 | AC-2322-03 | 27 | 110.22 | 2975.94 | P
M1-02 | 30 | SO | 483553 | 11 | 3 | C10860 | LTL | N30 | B11 | A | EA | MRO | 01 | 2021-09-19 | 2022-01-12 | AC-3649-B | 15 | 94.33 | 1414.95 | O
M1-02 | 30 | SO | 480093 | 4 | 2 | C10966 | BEST WAY | N30 | B22 | NC | EA | MRO | 05 | 2021-06-05 | 2021-09-12 | AC-1381-05 | 89 | 139.77 | 12439.53 | O
M1-02 | 30 | SO | 489436 | 8 | 0 | C10900 | BEST WAY | N45 | B07 | E | EA | MRO | 01 | 2022-02-05 | 2022-04-01 | AC-6854-01 | 34 | 116.83 | 3972.22 | P
M1-02 | 30 | BL | 487979 | 12 | 3 | C10256 | LTL | N30 | B11 | NC | EA | MRO | 02 | 2021-03-01 | 2021-07-15 | AC-3929-10 | 13 | 44.29 | 575.77 | P
M1-02 | 30 | SO | 482225 | 7 | 0 | C10238 | CUST PU | N60 | B07 | B | EA | AERO | 02 | 2022-02-23 | 2022-05-09 | AC-2092-01 | 82 | 139.13 | 11408.66 | O
M1-02 | 30 | SO | 481290 | 5 | 2 | C10530 | CUST PU | N60 | B22 | E | EA | MRO | 02 | 2021-08-04 | 2021-10-01 | AC-6487-02 | 32 | 46.77 | 1496.64 | O
M1-02 | 20 | SO | 482702 | 2 | 0 | C10568 | LTL | N60 | B22 | B | EA | OEM | 05 | 2022-01-21 | 2022-04-18 | AC-9458-02 | 48 | 132.72 | 6370.56 | O
M1-02 | 20 | SO | 482405 | 1 | 0 | C10249 | LTL | N30 | B11 | C | EA | AERO | 05 | 2021-04-26 | 2021-08-06 | AC-9183-05 | 65 | 144.83 | 9413.95 | O
M1-02 | 30 | SO | 481711 | 8 | 1 | C10252 | UPS GND | N60 | B11 | D | EA | AERO | 05 | 2022-01-17 | 2022-02-24 | AC-1310-B | 58 | 66.75 | 3871.5 | O
M1-02 | 30 | SO | 484117 | 3 | 1 | C10525 | UPS GND | N45 | B07 | NC | EA | OEM | 01 | 2022-01-22 | 2022-04-29 | AC-5837-01 | 89 | 173.32 | 15425.48 | O
M1-02 | 30 | SO | 480050 | 4 | 3 | C10251 | UPS GND | N60 | B14 | A | EA | OEM | 01 | 2021-07-24 | 2021-11-28 | AC-1293-A | 63 | 123.99 | 7811.37 | O
M1-02 | 30 | SO | 485706 | 6 | 3 | C10786 | FDX 2D | N60 | B11 | C | EA | MRO | 02 | 2022-03-11 | 2022-06-04 | AC-6546-10 | 13 | 71.49 | 929.37 | O
M1-02 | 20 | SO | 488886 | 5 | 2 | C10316 | UPS GND | N60 | B11 | A | EA | MRO | 01 | 2022-03-24 | 2022-05-30 | AC-1166-B | 17 | 203.64 | 3461.88 | P
M1-02 | 20 | SO | 485816 | 9 | 1 | C10316 | LTL | N30 | B14 | B | EA | MRO | 01 | 2022-01-09 | 2022-04-05 | AC-6053-01 | 31 | 124.43 | 3857.33 | O
M1-02 | 20 | SO | 487337 | 12 | 2 | C10321 | CUST PU | N60 | B14 | D | EA | DEF | 05 | 2022-01-03 | 2022-04-27 | AC-5562-B | 32 | 87.53 | 2800.96 | O
M1-02 | 20 | SO | 481851 | 12 | 1 | C10436 | LTL | 2%10N30 | B14 | A | EA | OEM | 02 | 2022-02-14 | 2022-04-24 | AC-4302-01 | 28 | 90.83 | 2543.24 | O
M1-02 | 20 | SO | 487178 | 2 | 1 | C10455 | UPS GND | N30 | B11 | NC | EA | DEF | 05 | 2022-01-04 | 2022-03-14 | AC-3418-01 | 80 | 167.75 | 13420 | O
M1-02 | 20 | BL | 487204 | 8 | 1 | C10786 | CUST PU | N45 | B14 | B | EA | DEF | 05 | 2021-11-15 | 2022-03-18 | AC-4400-10 | 97 | 109.39 | 10610.83 | O
M1-02 | 20 | SO | 489155 | 5 | 1 | C10305 | CUST PU | 2%10N30 | B07 | C | EA | DEF | 05 | 2022-01-05 | 2022-04-29 | AC-1231-10 | 29 | 170.26 | 4937.54 | P
M1-02 | 20 | SO | 481272 | 8 | 1 | C10526 | LTL | N60 | B14 | NC | EA | OEM | 02 | 2021-04-15 | 2021-07-21 | AC-4101-02 | 94 | 134.77 | 12668.38 | O
M1-02 | 20 | SO | 485064 | 5 | 2 | C10456 | LTL | N60 | B11 | E | EA | OEM | 02 | 2022-01-23 | 2022-06-05 | AC-6205-A | 80 | 92.01 | 7360.8 | O
M1-02 | 30 | BL | 484315 | 10 | 0 | C10264 | FDX 2D | N30 | B11 | E | EA | MRO | 02 | 2021-02-16 | 2021-05-30 | AC-6864-05 | 62 | 53.32 | 3305.84 | O
M1-02 | 20 | SO | 488793 | 2 | 3 | C10316 | UPS GND | 2%10N30 | B07 | C | EA | DEF | 05 | 2021-06-26 | 2021-08-15 | AC-3359-A | 37 | 107.1 | 3962.7 | P
M1-02 | 30 | SO | 486507 | 1 | 0 | C10350 | LTL | 2%10N30 | B07 | A | EA | AERO | 05 | 2021-12-25 | 2022-03-15 | AC-6537-05 | 91 | 107.12 | 9747.92 | O
M1-02 | 30 | SO | 486646 | 4 | 0 | C10756 | FDX 2D | N45 | B11 | B | EA | DEF | 02 | 2022-04-12 | 2022-06-07 | AC-3944-B | 35 | 135.91 | 4756.85 | O
M1-02 | 20 | BL | 481368 | 5 | 0 | C10211 | CUST PU | N45 | B11 | B | EA | OEM | 01 | 2022-03-02 | 2022-05-22 | AC-4924-03 | 22 | 46.84 | 1030.48 | O
M1-02 | 30 | BL | 486612 | 6 | 3 | C10568 | LTL | N30 | B11 | C | EA | OEM | 05 | 2022-02-02 | 2022-05-19 | AC-9427-05 | 38 | 146.28 | 5558.64 | O
M1-02 | 30 | SO | 484297 | 11 | 2 | C10256 | FDX 2D | N60 | B14 | B | EA | DEF | 05 | 2022-04-06 | 2022-05-14 | AC-3231-10 | 79 | 137.98 | 10900.42 | O
M1-02 | 20 | SO | 488469 | 3 | 3 | C10170 | FDX 2D | N45 | B11 | NC | EA | AERO | 01 | 2021-12-30 | 2022-05-09 | AC-6549-A | 20 | 105.1 | 2102 | P
M1-02 | 30 | SO | 485008 | 9 | 1 | C10966 | FDX 2D | N60 | B14 | C | EA | AERO | 02 | 2022-01-04 | 2022-03-18 | AC-8675-10 | 33 | 164.31 | 5422.23 | O
M1-02 | 30 | SO | 484542 | 3 | 0 | C10900 | LTL | N45 | B07 | C | EA | AERO | 01 | 2022-04-04 | 2022-06-06 | AC-1579-10 | 84 | 93.14 | 7823.76 | O
M1-02 | 30 | SO | 487925 | 2 | 1 | C10936 | BEST WAY | N30 | B22 | B | EA | MRO | 05 | 2021-07-26 | 2021-10-11 | AC-4873-10 | 50 | 46.63 | 2331.5 | P
M1-02 | 20 | SO | 485036 | 7 | 1 | C10940 | FDX 2D | N60 | B11 | C | EA | OEM | 01 | 2022-03-18 | 2022-05-05 | AC-3896-05 | 93 | 152.88 | 14217.84 | O
M1-02 | 30 | SO | 482190 | 6 | 0 | C10222 | BEST WAY | N60 | B22 | A | EA | AERO | 01 | 2021-09-14 | 2021-11-23 | AC-4132-01 | 64 | 102.47 | 6558.08 | O
M1-02 | 30 | SO | 483049 | 4 | 3 | C10281 | FDX 2D | 2%10N30 | B22 | D | EA | MRO | 01 | 2022-03-10 | 2022-06-10 | AC-6384-A | 52 | 125.09 | 6504.68 | O
M1-02 | 30 | SO | 486544 | 1 | 1 | C10936 | FDX 2D | N60 | B22 | E | EA | AERO | 01 | 2021-12-17 | 2022-04-18 | AC-3356-03 | 79 | 162.32 | 12823.28 | O
M1-02 | 30 | SO | 482927 | 11 | 0 | C10186 | CUST PU | 2%10N30 | B22 | E | EA | AERO | 02 | 2021-12-12 | 2022-03-26 | AC-1843-10 | 39 | 45.98 | 1793.22 | O
M1-02 | 30 | SO | 481235 | 1 | 1 | C10695 | BEST WAY | N30 | B14 | D | EA | MRO | 05 | 2021-05-31 | 2021-08-08 | AC-8540-01 | 64 | 124.27 | 7953.28 | O
M1-02 | 20 | BL | 488273 | 7 | 0 | C10519 | LTL | N60 | B22 | NC | EA | OEM | 02 | 2021-05-30 | 2021-08-19 | AC-3929-10 | 17 | 81.81 | 1390.77 | P
M1-02 | 30 | SO | 487007 | 6 | 1 | C10951 | CUST PU | N60 | B22 | NC | EA | OEM | 02 | 2022-02-06 | 2022-05-16 | AC-6982-05 | 86 | 145.86 | 12543.96 | O
M1-02 | 30 | SO | 484398 | 12 | 2 | C10525 | FDX 2D | 2%10N30 | B14 | NC | EA | MRO | 02 | 2022-02-19 | 2022-05-11 | AC-7626-05 | 65 | 115.72 | 7521.8 | O
M1-02 | 20 | BL | 487501 | 8 | 3 | C10950 | UPS GND | N45 | B14 | NC | EA | DEF | 01 | 2022-03-01 | 2022-04-16 | AC-4645-05 | 42 | 42.58 | 1788.36 | P
M1-02 | 20 | SO | 488091 | 4 | 1 | C10695 | CUST PU | N60 | B07 | A | EA | OEM | 05 | 2021-06-14 | 2021-07-29 | AC-7176-02 | 31 | 120.18 | 3725.58 | P
M1-02 | 20 | BL | 488322 | 6 | 3 | C10331 | BEST WAY | N45 | B22 | B | EA | OEM | 02 | 2021-06-13 | 2021-09-12 | AC-4386-01 | 49 | 50.72 | 2485.28 | P
M1-02 | 20 | BL | 487751 | 10 | 2 | C10281 | BEST WAY | 2%10N30 | B11 | A | EA | OEM | 05 | 2021-12-14 | 2022-04-16 | AC-4250-A | 41 | 81.45 | 3339.45 | P
M1-02 | 30 | SO | 484230 | 5 | 1 | C10589 | BEST WAY | N45 | B22 | NC | EA | OEM | 02 | 2022-03-05 | 2022-04-09 | AC-4314-03 | 72 | 82.64 | 5950.08 | O
M1-02 | 20 | BL | 481846 | 6 | 1 | C10385 | BEST WAY | N45 | B11 | B | EA | OEM | 01 | 2022-01-10 | 2022-05-29 | AC-4045-B | 45 | 47.17 | 2122.65 | O
M1-02 | 20 | SO | 485729 | 11 | 0 | C10280 | BEST WAY | N45 | B07 | C | EA | DEF | 02 | 2022-02-03 | 2022-05-17 | AC-6691-B | 29 | 173.91 | 5043.39 | O
M1-02 | 20 | SO | 484175 | 5 | 3 | C10461 | LTL | 2%10N30 | B07 | A | EA | MRO | 01 | 2022-01-21 | 2022-05-06 | AC-9481-02 | 23 | 101.12 | 2325.76 | O
M1-02 | 20 | SO | 482237 | 5 | 2 | C10327 | CUST PU | N60 | B14 | A | EA | MRO | 01 | 2021-12-23 | 2022-03-11 | AC-3356-03 | 9 | 134.86 | 1213.74 | O
M1-02 | 30 | SO | 484869 | 8 | 1 | C10688 | BEST WAY | N60 | B14 | E | EA | AERO | 02 | 2022-03-14 | 2022-04-12 | AC-3053-03 | 25 | 142.31 | 3557.75 | O
M1-02 | 20 | BL | 480457 | 11 | 0 | C10568 | FDX 2D | 2%10N30 | B22 | A | EA | MRO | 05 | 2021-10-31 | 2022-03-13 | AC-9207-02 | 10 | 109.48 | 1094.8 | O
M1-02 | 30 | SO | 485963 | 11 | 2 | C10787 | BEST WAY | N45 | B07 | E | EA | OEM | 05 | 2021-12-01 | 2022-04-17 | AC-8370-A | 19 | 173.71 | 3300.49 | O
M1-02 | 20 | BL | 489569 | 11 | 0 | C10830 | CUST PU | N45 | B14 | A | EA | OEM | 02 | 2021-12-16 | 2022-04-28 | AC-4109-05 | 11 | 304.44 | 3348.84 | P
M1-02 | 20 | SO | 482423 | 5 | 1 | C10385 | FDX 2D | N45 | B22 | NC | EA | OEM | 02 | 2021-12-30 | 2022-04-12 | AC-2520-A | 82 | 80.76 | 6622.32 | O
M1-02 | 30 | SO | 485804 | 7 | 1 | C10752 | CUST PU | N60 | B11 | D | EA | DEF | 05 | 2022-04-13 | 2022-06-04 | AC-6537-05 | 70 | 126.68 | 8867.6 | O
M1-02 | 20 | BL | 483462 | 7 | 1 | C10501 | CUST PU | N60 | B14 | C | EA | OEM | 01 | 2022-02-05 | 2022-04-26 | AC-1368-05 | 16 | 97.9 | 1566.4 | O
M1-02 | 20 | SO | 487161 | 10 | 1 | C10589 | UPS GND | N45 | B11 | NC | EA | OEM | 02 | 2022-02-08 | 2022-04-28 | AC-7160-A | 18 | 127.34 | 2292.12 | O
M1-02 | 20 | SO | 482398 | 11 | 2 | C10222 | FDX 2D | N45 | B14 | E | EA | AERO | 01 | 2021-12-11 | 2022-04-03 | AC-7179-A | 26 | 127.41 | 3312.66 | O
M1-02 | 20 | SO | 480524 | 6 | 3 | C10170 | BEST WAY | N60 | B22 | C | EA | MRO | 02 | 2022-01-09 | 2022-04-21 | AC-2546-A | 36 | 138.01 | 4968.36 | O
M1-02 | 30 | BL | 485125 | 11 | 2 | C10806 | UPS GND | N60 | B22 | D | EA | AERO | 02 | 2022-02-16 | 2022-03-21 | AC-7258-B | 86 | 83.48 | 7179.28 | O
M1-02 | 20 | SO | 481751 | 2 | 1 | C10186 | FDX 2D | N30 | B11 | D | EA | OEM | 01 | 2021-12-17 | 2022-04-01 | AC-3297-05 | 65 | 57.58 | 3742.7 | O
M1-02 | 20 | SO | 483290 | 2 | 2 | C10170 | UPS GND | 2%10N30 | B11 | A | EA | AERO | 02 | 2022-01-01 | 2022-03-18 | AC-7692-03 | 28 | 127.1 | 3558.8 | O
M1-02 | 20 | BL | 487571 | 7 | 3 | C10256 | UPS GND | N45 | B14 | B | EA | AERO | 05 | 2022-03-14 | 2022-05-24 | AC-2827-02 | 37 | 166.65 | 6166.05 | P
M1-02 | 30 | SO | 488721 | 11 | 0 | C10688 | BEST WAY | N60 | B07 | D | EA | MRO | 01 | 2021-08-28 | 2021-10-20 | AC-5085-05 | 33 | 177.06 | 5842.98 | P
M1-02 | 20 | SO | 488308 | 3 | 2 | C10806 | LTL | N60 | B11 | B | EA | OEM | 02 | 2021-06-19 | 2021-07-25 | AC-3151-05 | 14 | 144.43 | 2022.02 | P
M1-02 | 30 | SO | 489495 | 8 | 1 | C10746 | BEST WAY | N30 | B22 | E | EA | AERO | 02 | 2022-03-01 | 2022-06-02 | AC-8338-01 | 25 | 102.6 | 2565 | P
M1-02 | 30 | BL | 486098 | 9 | 1 | C10436 | CUST PU | 2%10N30 | B07 | D | EA | AERO | 02 | 2022-03-25 | 2022-04-30 | AC-3631-03 | 12 | 49.73 | 596.76 | O
M1-02 | 30 | SO | 482521 | 5 | 3 | C10530 | UPS GND | N45 | B11 | E | EA | AERO | 02 | 2021-07-31 | 2021-08-30 | AC-7083-B | 10 | 145.49 | 1454.9 | O
M1-02 | 30 | BL | 488862 | 10 | 3 | C10560 | CUST PU | 2%10N30 | B22 | C | EA | OEM | 02 | 2022-03-27 | 2022-06-02 | AC-9591-03 | 28 | 85.11 | 2383.08 | P
M1-02 | 20 | SO | 483370 | 8 | 2 | C10752 | UPS GND | N30 | B22 | NC | EA | OEM | 01 | 2022-02-25 | 2022-04-06 | AC-6682-01 | 93 | 72.95 | 6784.35 | O
M1-02 | 20 | SO | 484395 | 1 | 0 | C10526 | FDX 2D | N30 | B07 | B | EA | OEM | 05 | 2022-02-19 | 2022-06-08 | AC-1793-03 | 53 | 127.28 | 6745.84 | O
M1-02 | 20 | SO | 484181 | 11 | 3 | C10211 | LTL | N60 | B14 | B | EA | OEM | 01 | 2022-03-07 | 2022-06-05 | AC-1973-B | 76 | 64.57 | 4907.32 | O
M1-02 | 30 | SO | 486840 | 12 | 3 | C10316 | CUST PU | 2%10N30 | B14 | C | EA | AERO | 05 | 2022-01-01 | 2022-05-03 | AC-3758-02 | 70 | 53.23 | 3726.1 | O
M1-02 | 30 | BL | 487289 | 8 | 3 | C10170 | UPS GND | N60 | B22 | E | EA | OEM | 05 | 2022-01-02 | 2022-04-26 | AC-6167-B | 12 | 79.67 | 956.04 | O
M1-02 | 30 | BL | 488611 | 1 | 2 | C10568 | BEST WAY | N30 | B07 | D | EA | DEF | 01 | 2021-12-31 | 2022-04-04 | AC-3151-05 | 51 | 146.87 | 7490.37 | P
M1-02 | 30 | SO | 485168 | 9 | 0 | C10526 | UPS GND | N60 | B11 | D | EA | OEM | 05 | 2022-02-13 | 2022-06-02 | AC-6537-05 | 93 | 81.84 | 7611.12 | O
M1-02 | 20 | SO | 485499 | 1 | 0 | C10950 | BEST WAY | N30 | B14 | E | EA | AERO | 05 | 2021-05-11 | 2021-06-17 | AC-9526-B | 58 | 112.57 | 6529.06 | O
M1-02 | 20 | SO | 481529 | 3 | 2 | C10252 | CUST PU | 2%10N30 | B07 | E | EA | AERO | 02 | 2021-11-12 | 2022-03-31 | AC-2928-B | 38 | 86.64 | 3292.32 | O
M1-02 | 30 | SO | 480913 | 2 | 1 | C10589 | FDX 2D | N60 | B11 | NC | EA | AERO | 05 | 2021-11-13 | 2022-03-03 | AC-4033-01 | 63 | 120.52 | 7592.76 | O
M1-02 | 30 | BL | 482512 | 7 | 3 | C10530 | CUST PU | N45 | B11 | A | EA | OEM | 01 | 2021-11-23 | 2022-01-08 | AC-5246-01 | 23 | 108.57 | 2497.11 | O
M1-02 | 20 | SO | 488829 | 8 | 2 | C10568 | LTL | N45 | B14 | C | EA | OEM | 02 | 2022-01-10 | 2022-04-30 | AC-4980-01 | 32 | 68.68 | 2197.76 | P
M1-02 | 30 | SO | 484556 | 5 | 3 | C10501 | UPS GND | N45 | B07 | B | EA | MRO | 02 | 2022-04-03 | 2022-06-02 | AC-8183-02 | 76 | 108.68 | 8259.68 | O
M1-02 | 20 | BL | 486086 | 9 | 2 | C10900 | LTL | N30 | B22 | A | EA | OEM | 01 | 2022-03-21 | 2022-04-20 | AC-8195-10 | 49 | 80.45 | 3942.05 | O
M1-02 | 30 | BL | 485592 | 12 | 0 | C10456 | CUST PU | N45 | B22 | C | EA | OEM | 05 | 2021-12-28 | 2022-03-14 | AC-6644-03 | 71 | 140.8 | 9996.8 | O
M1-02 | 30 | SO | 480656 | 2 | 0 | C10695 | LTL | N45 | B14 | NC | EA | DEF | 02 | 2022-02-21 | 2022-04-27 | AC-8412-03 | 7 | 131.26 | 918.82 | O
M1-02 | 30 | SO | 486561 | 3 | 3 | C10455 | CUST PU | N45 | B14 | E | EA | AERO | 05 | 2021-04-24 | 2021-05-30 | AC-5698-01 | 18 | 172.71 | 3108.78 | O
M1-02 | 20 | BL | 482795 | 1 | 1 | C10900 | CUST PU | N30 | B22 | D | EA | MRO | 05 | 2021-08-21 | 2021-11-22 | AC-5856-02 | 96 | 119.04 | 11427.84 | O
M1-02 | 20 | SO | 486104 | 1 | 3 | C10222 | LTL | N60 | B07 | C | EA | MRO | 01 | 2022-01-05 | 2022-05-24 | AC-3599-02 | 94 | 158.66 | 14914.04 | O
M1-02 | 20 | BL | 487441 | 10 | 2 | C10860 | LTL | 2%10N30 | B14 | E | EA | MRO | 05 | 2021-05-10 | 2021-07-19 | AC-8814-03 | 54 | 62.93 | 3398.22 | P
M1-02 | 30 | BL | 481033 | 1 | 1 | C10706 | UPS GND | 2%10N30 | B11 | A | EA | MRO | 05 | 2021-11-16 | 2022-03-23 | AC-7186-02 | 94 | 130.91 | 12305.54 | O
M1-02 | 30 | BL | 487986 | 1 | 2 | C10455 | BEST WAY | N45 | B22 | C | EA | MRO | 01 | 2021-09-06 | 2021-10-12 | AC-6549-A | 54 | 157.98 | 8530.92 | P
M1-02 | 20 | SO | 486423 | 12 | 1 | C10501 | FDX 2D | N60 | B14 | A | EA | MRO | 02 | 2022-03-19 | 2022-04-16 | AC-2648-05 | 32 | 74.94 | 2398.08 | O
M1-02 | 30 | SO | 486990 | 11 | 1 | C10786 | UPS GND | N30 | B14 | B | EA | MRO | 01 | 2021-12-26 | 2022-05-14 | AC-9877-05 | 55 | 42.8 | 2354 | O
M1-02 | 30 | SO | 481206 | 7 | 3 | C10211 | FDX 2D | N60 | B07 | A | EA | MRO | 01 | 2022-02-10 | 2022-04-29 | AC-3631-03 | 68 | 86.03 | 5850.04 | O
M1-02 | 30 | SO | 482772 | 10 | 2 | C10940 | CUST PU | N60 | B11 | C | EA | DEF | 05 | 2022-01-25 | 2022-04-25 | AC-5791-B | 55 | 82.34 | 4528.7 | O
M1-02 | 30 | SO | 484746 | 4 | 3 | C10973 | UPS GND | N30 | B07 | A | EA | OEM | 05 | 2021-12-23 | 2022-03-23 | AC-4026-03 | 37 | 172.81 | 6393.97 | O
M1-02 | 20 | BL | 482138 | 7 | 0 | C10951 | UPS GND | N60 | B14 | B | EA | AERO | 01 | 2021-11-28 | 2022-03-25 | AC-2571-A | 93 | 52.3 | 4863.9 | O
M1-02 | 30 | SO | 488842 | 11 | 0 | C10950 | CUST PU | 2%10N30 | B11 | E | EA | DEF | 05 | 2022-02-25 | 2022-04-14 | AC-2356-05 | 5 | 115.52 | 577.6 | P
M1-02 | 30 | SO | 487786 | 12 | 0 | C10940 | FDX 2D | N30 | B11 | NC | EA | AERO | 01 | 2021-11-13 | 2022-02-09 | AC-2133-01 | 7 | 112.36 | 786.52 | P
M1-02 | 30 | SO | 484926 | 5 | 3 | C10806 | CUST PU | N30 | B22 | D | EA | DEF | 05 | 2021-12-18 | 2022-04-09 | AC-2570-B | 62 | 106.63 | 6611.06 | O
M1-02 | 20 | SO | 482828 | 2 | 0 | C10280 | BEST WAY | N45 | B07 | D | EA | MRO | 01 | 2021-12-23 | 2022-04-09 | AC-8552-01 | 65 | 175.49 | 11406.85 | O
M1-02 | 20 | SO | 483443 | 3 | 2 | C10568 | LTL | N45 | B11 | NC | EA | OEM | 01 | 2021-12-01 | 2022-01-29 | AC-9481-02 | 91 | 80.03 | 7282.73 | O
M1-02 | 30 | SO | 488856 | 3 | 2 | C10501 | LTL | N30 | B22 | A | EA | DEF | 02 | 2021-11-30 | 2022-01-21 | AC-6078-10 | 17 | 129.33 | 2198.61 | P
M1-02 | 20 | BL | 485056 | 3 | 1 | C10249 | BEST WAY | N45 | B07 | B | EA | OEM | 05 | 2021-10-21 | 2022-01-02 | AC-8996-10 | 39 | 69.86 | 2724.54 | O
M1-02 | 20 | SO | 483976 | 7 | 2 | C10264 | FDX 2D | N30 | B14 | E | EA | AERO | 02 | 2021-08-11 | 2021-11-16 | AC-7626-05 | 83 | 82.6 | 6855.8 | O
M1-02 | 20 | BL | 485495 | 4 | 3 | C10746 | UPS GND | 2%10N30 | B11 | B | EA | AERO | 05 | 2021-04-18 | 2021-07-21 | AC-9767-B | 89 | 47.97 | 4269.33 | O
M1-02 | 20 | SO | 485281 | 6 | 1 | C10461 | CUST PU | N30 | B11 | C | EA | DEF | 01 | 2022-02-15 | 2022-05-10 | AC-9459-10 | 20 | 174.46 | 3489.2 | O
M1-02 | 20 | SO | 481648 | 12 | 3 | C10806 | CUST PU | 2%10N30 | B07 | C | EA | DEF | 02 | 2022-04-13 | 2022-06-07 | AC-8435-01 | 34 | 55.64 | 1891.76 | O
M1-02 | 20 | SO | 483083 | 3 | 3 | C10900 | CUST PU | N45 | B22 | NC | EA | AERO | 01 | 2022-01-07 | 2022-03-13 | AC-4736-B | 62 | 92.86 | 5757.32 | O
M1-02 | 20 | SO | 487390 | 2 | 0 | C10936 | BEST WAY | N45 | B22 | B | EA | MRO | 02 | 2021-10-12 | 2021-11-24 | AC-7219-A | 58 | 88.07 | 5108.06 | P
M1-02 | 30 | SO | 480684 | 4 | 3 | C10249 | CUST PU | N45 | B22 | E | EA | DEF | 02 | 2021-11-23 | 2022-04-01 | AC-5275-10 | 77 | 42.09 | 3240.93 | O
M1-02 | 30 | SO | 485954 | 11 | 0 | C10787 | LTL | N30 | B22 | E | EA | DEF | 05 | 2022-01-14 | 2022-03-18 | AC-1705-01 | 9 | 76.59 | 689.31 | O
M1-02 | 20 | SO | 480969 | 5 | 3 | C10940 | BEST WAY | N60 | B07 | B | EA | OEM | 02 | 2022-02-17 | 2022-03-23 | AC-6167-B | 70 | 112.9 | 7903 | O
M1-02 | 30 | SO | 487550 | 8 | 3 | C10568 | FDX 2D | 2%10N30 | B11 | D | EA | AERO | 01 | 2021-05-07 | 2021-08-24 | AC-7555-03 | 26 | 173.42 | 4508.92 | P
M1-02 | 20 | BL | 482883 | 4 | 1 | C10526 | UPS GND | N60 | B11 | D | EA | OEM | 02 | 2022-02-10 | 2022-05-16 | AC-8378-01 | 87 | 45.79 | 3983.73 | O
M1-02 | 30 | SO | 488040 | 10 | 1 | C10316 | BEST WAY | N45 | B07 | E | EA | MRO | 01 | 2021-09-29 | 2022-01-28 | AC-1894-02 | 31 | 70.81 | 2195.11 | P
M1-02 | 20 | BL | 489485 | 1 | 1 | C10501 | FDX 2D | N30 | B22 | B | EA | MRO | 01 | 2022-01-07 | 2022-04-16 | AC-5424-05 | 25 | 195.09 | 4877.25 | P
M1-02 | 20 | SO | 489561 | 9 | 0 | C10530 | LTL | N30 | B14 | C | EA | AERO | 02 | 2021-10-10 | 2022-02-15 | AC-1787-01 | 7 | 179.34 | 1255.38 | P
M1-02 | 20 | BL | 480425 | 4 | 3 | C10251 | UPS GND | 2%10N30 | B14 | B | EA | AERO | 05 | 2021-10-01 | 2022-02-17 | AC-1409-05 | 73 | 138.35 | 10099.55 | O
M1-02 | 30 | SO | 481786 | 1 | 2 | C10327 | UPS GND | 2%10N30 | B11 | D | EA | MRO | 01 | 2022-03-14 | 2022-05-15 | AC-7160-02 | 29 | 134.49 | 3900.21 | O
M1-02 | 20 | BL | 486023 | 7 | 2 | C10758 | CUST PU | N60 | B11 | C | EA | MRO | 05 | 2022-01-09 | 2022-03-19 | AC-3257-03 | 63 | 50.36 | 3172.68 | O
M1-02 | 30 | SO | 485065 | 3 | 1 | C10350 | CUST PU | N60 | B07 | C | EA | DEF | 05 | 2022-03-12 | 2022-05-13 | AC-2049-05 | 86 | 85.97 | 7393.42 | O
M1-02 | 30 | SO | 481707 | 4 | 0 | C10186 | BEST WAY | N60 | B14 | E | EA | MRO | 01 | 2022-01-04 | 2022-04-19 | AC-6896-10 | 35 | 147.58 | 5165.3 | O
M1-02 | 20 | BL | 482315 | 12 | 3 | C10706 | FDX 2D | N30 | B14 | E | EA | DEF | 02 | 2022-03-10 | 2022-05-12 | AC-4405-01 | 35 | 88.65 | 3102.75 | O
M1-02 | 20 | SO | 480860 | 7 | 2 | C10350 | UPS GND | N45 | B11 | C | EA | MRO | 05 | 2022-01-18 | 2022-05-15 | AC-1742-B | 37 | 107.62 | 3981.94 | O
M1-02 | 20 | BL | 482022 | 3 | 2 | C10501 | LTL | 2%10N30 | B14 | C | EA | AERO | 05 | 2022-03-30 | 2022-05-27 | AC-2254-02 | 48 | 160.08 | 7683.84 | O
M1-02 | 30 | SO | 484053 | 9 | 3 | C10852 | BEST WAY | N60 | B11 | C | EA | MRO | 02 | 2022-01-24 | 2022-03-30 | AC-4090-02 | 57 | 43.64 | 2487.48 | O
M1-02 | 20 | SO | 485547 | 11 | 3 | C10752 | BEST WAY | 2%10N30 | B22 | NC | EA | MRO | 02 | 2022-01-18 | 2022-04-08 | AC-3559-A | 18 | 123.08 | 2215.44 | O
M1-02 | 20 | SO | 483674 | 5 | 2 | C10830 | LTL | N60 | B07 | C | EA | OEM | 02 | 2021-11-02 | 2022-03-22 | AC-3357-05 | 93 | 127.93 | 11897.49 | O
M1-02 | 30 | SO | 485856 | 3 | 2 | C10758 | UPS GND | N60 | B22 | E | EA | AERO | 01 | 2021-12-25 | 2022-01-24 | AC-7179-A | 16 | 162.34 | 2597.44 | O
M1-02 | 20 | SO | 485738 | 8 | 1 | C10758 | LTL | N60 | B14 | D | EA | DEF | 05 | 2022-03-21 | 2022-06-07 | AC-7055-B | 95 | 148.73 | 14129.35 | O
M1-02 | 20 | BL | 481720 | 5 | 3 | C10706 | LTL | N30 | B07 | NC | EA | AERO | 05 | 2021-12-28 | 2022-05-15 | AC-9578-B | 17 | 140.27 | 2384.59 | O
M1-02 | 30 | BL | 480124 | 6 | 0 | C10316 | UPS GND | N45 | B11 | NC | EA | MRO | 02 | 2022-02-06 | 2022-03-21 | AC-7784-01 | 8 | 172.54 | 1380.32 | O
M1-02 | 20 | SO | 483201 | 3 | 2 | C10186 | UPS GND | 2%10N30 | B11 | C | EA | DEF | 02 | 2022-02-09 | 2022-05-28 | AC-4663-10 | 88 | 141.71 | 12470.48 | O
M1-02 | 20 | BL | 480449 | 8 | 3 | C10273 | LTL | N60 | B07 | NC | EA | MRO | 05 | 2021-09-30 | 2021-12-30 | AC-8357-01 | 90 | 113.19 | 10187.1 | O
M1-02 | 30 | SO | 483739 | 9 | 3 | C10331 | UPS GND | N60 | B07 | NC | EA | DEF | 05 | 2022-03-09 | 2022-05-20 | AC-9389-03 | 47 | 86.61 | 4070.67 | O
M1-02 | 30 | BL | 481030 | 10 | 1 | C10238 | UPS GND | 2%10N30 | B14 | A | EA | OEM | 02 | 2022-03-13 | 2022-05-25 | AC-1841-A | 79 | 110.35 | 8717.65 | O
M1-02 | 20 | SO | 480141 | 4 | 2 | C10281 | BEST WAY | N30 | B07 | NC | EA | DEF | 02 | 2021-06-01 | 2021-09-01 | AC-8916-03 | 30 | 53.21 | 1596.3 | O
M1-02 | 30 | SO | 486392 | 9 | 3 | C10560 | UPS GND | N30 | B07 | E | EA | DEF | 05 | 2022-01-17 | 2022-04-15 | AC-3945-A | 25 | 113.13 | 2828.25 | O
M1-02 | 20 | BL | 481370 | 1 | 0 | C10305 | LTL | N30 | B11 | D | EA | OEM | 01 | 2022-01-03 | 2022-03-18 | AC-6988-03 | 29 | 75.98 | 2203.42 | O
M1-02 | 30 | SO | 486466 | 9 | 3 | C10385 | UPS GND | N60 | B14 | C | EA | DEF | 01 | 2021-12-28 | 2022-03-01 | AC-8083-03 | 64 | 45.45 | 2908.8 | O
M1-02 | 20 | SO | 481341 | 10 | 3 | C10966 | FDX 2D | N45 | B11 | B | EA | MRO | 05 | 2021-12-25 | 2022-02-14 | AC-5672-03 | 66 | 133.38 | 8803.08 | O
M1-02 | 20 | BL | 484350 | 3 | 1 | C10170 | BEST WAY | N45 | B11 | A | EA | AERO | 01 | 2022-03-07 | 2022-05-13 | AC-5968-02 | 56 | 137.49 | 7699.44 | O
M1-02 | 20 | SO | 489670 | 3 | 3 | C10170 | BEST WAY | N45 | B11 | B | EA | DEF | 02 | 2022-03-24 | 2022-05-17 | AC-5686-01 | 23 | 106.2 | 2442.6 | P
M1-02 | 30 | BL | 484680 | 1 | 0 | C10817 | UPS GND | N60 | B11 | A | EA | MRO | 01 | 2021-12-15 | 2022-04-05 | AC-9492-01 | 69 | 67.3 | 4643.7 | O
M1-02 | 20 | SO | 482463 | 2 | 0 | C10589 | BEST WAY | N60 | B07 | D | EA | DEF | 01 | 2021-12-10 | 2022-03-21 | AC-2561-05 | 9 | 128.86 | 1159.74 | O
M1-02 | 30 | SO | 488465 | 5 | 0 | C10806 | BEST WAY | N30 | B14 | B | EA | MRO | 01 | 2021-12-30 | 2022-02-26 | AC-2349-05 | 29 | 113.04 | 3278.16 | P
M1-02 | 20 | SO | 485472 | 8 | 0 | C10786 | FDX 2D | N60 | B07 | C | EA | DEF | 02 | 2021-10-29 | 2022-03-13 | AC-1651-01 | 62 | 72.61 | 4501.82 | O
M1-02 | 30 | SO | 482491 | 9 | 1 | C10170 | FDX 2D | N45 | B11 | C | EA | DEF | 01 | 2022-04-14 | 2022-05-14 | AC-4095-02 | 49 | 158.56 | 7769.44 | O
M1-02 | 30 | BL | 488238 | 6 | 1 | C10498 | FDX 2D | N60 | B07 | B | EA | OEM | 01 | 2021-08-30 | 2021-10-04 | AC-9332-01 | 50 | 68.4 | 3420 | P
M1-02 | 30 | SO | 483642 | 3 | 0 | C10746 | FDX 2D | N30 | B14 | NC | EA | OEM | 02 | 2021-06-03 | 2021-09-24 | AC-3257-03 | 89 | 89.76 | 7988.64 | O
M1-02 | 30 | BL | 482194 | 11 | 0 | C10238 | LTL | 2%10N30 | B11 | A | EA | MRO | 01 | 2021-07-27 | 2021-11-29 | AC-7122-03 | 36 | 61.47 | 2212.92 | O
M1-02 | 30 | SO | 484683 | 2 | 1 | C10461 | BEST WAY | N45 | B11 | E | EA | OEM | 05 | 2022-01-13 | 2022-03-02 | AC-1382-B | 77 | 110.39 | 8500.03 | O
M1-02 | 30 | SO | 482161 | 6 | 0 | C10501 | FDX 2D | N60 | B11 | E | EA | AERO | 01 | 2021-07-20 | 2021-11-16 | AC-3764-01 | 54 | 109.5 | 5913 | O
M1-02 | 30 | SO | 489671 | 2 | 0 | C10966 | BEST WAY | N45 | B11 | E | EA | DEF | 02 | 2022-02-07 | 2022-05-26 | AC-9385-03 | 34 | 87.34 | 2969.56 | P
M1-02 | 30 | SO | 485866 | 4 | 2 | C10249 | LTL | N30 | B11 | NC | EA | OEM | 05 | 2022-03-08 | 2022-04-19 | AC-5061-A | 94 | 88.55 | 8323.7 | O
M1-02 | 20 | BL | 488623 | 4 | 3 | C10456 | FDX 2D | N30 | B14 | B | EA | MRO | 01 | 2021-08-24 | 2021-11-07 | AC-7338-02 | 11 | 120.01 | 1320.11 | P
M1-02 | 30 | SO | 482857 | 8 | 3 | C10281 | UPS GND | N45 | B11 | C | EA | OEM | 05 | 2022-03-12 | 2022-05-17 | AC-7258-B | 30 | 63.84 | 1915.2 | O
M1-02 | 30 | SO | 482754 | 3 | 2 | C10519 | UPS GND | 2%10N30 | B14 | NC | EA | OEM | 05 | 2022-02-08 | 2022-04-23 | AC-8676-03 | 23 | 72.6 | 1669.8 | O
M1-02 | 20 | SO | 481349 | 6 | 1 | C10170 | CUST PU | 2%10N30 | B07 | C | EA | AERO | 05 | 2022-03-22 | 2022-05-08 | AC-3456-B | 92 | 89.1 | 8197.2 | O
M1-02 | 30 | SO | 489409 | 1 | 1 | C10238 | BEST WAY | N60 | B07 | E | EA | DEF | 02 | 2021-12-27 | 2022-04-04 | AC-6614-05 | 19 | 108.3 | 2057.7 | P
M1-02 | 20 | SO | 488313 | 12 | 0 | C10331 | FDX 2D | N30 | B14 | C | EA | MRO | 01 | 2021-07-26 | 2021-09-18 | AC-5069-03 | 16 | 155.86 | 2493.76 | P
M1-02 | 30 | BL | 489471 | 12 | 3 | C10256 | LTL | N30 | B14 | E | EA | DEF | 02 | 2022-01-10 | 2022-03-05 | AC-3878-05 | 9 | 83.83 | 754.47 | P
M1-02 | 30 | SO | 486008 | 9 | 3 | C10860 | BEST WAY | N30 | B22 | NC | EA | DEF | 02 | 2021-10-17 | 2022-01-22 | AC-7743-10 | 20 | 99.64 | 1992.8 | O
M1-02 | 30 | SO | 488964 | 7 | 3 | C10273 | UPS GND | 2%10N30 | B11 | E | EA | OEM | 02 | 2022-02-03 | 2022-05-03 | AC-2887-A | 16 | 111.46 | 1783.36 | P
M1-02 | 20 | BL | 486579 | 10 | 3 | C10695 | UPS GND | N45 | B22 | D | EA | OEM | 01 | 2022-03-05 | 2022-05-20 | AC-3813-03 | 51 | 61.95 | 3159.45 | O
M1-02 | 20 | SO | 487640 | 8 | 0 | C10170 | UPS GND | N45 | B14 | NC | EA | OEM | 01 | 2021-05-04 | 2021-07-12 | AC-3141-10 | 20 | 119.08 | 2381.6 | P
M1-02 | 20 | SO | 485245 | 8 | 0 | C10256 | BEST WAY | N45 | B14 | E | EA | AERO | 02 | 2021-11-26 | 2022-04-11 | AC-5838-05 | 5 | 78.34 | 391.7 | O
M1-02 | 20 | BL | 483987 | 9 | 0 | C10860 | BEST WAY | N45 | B14 | NC | EA | OEM | 02 | 2021-09-12 | 2022-01-23 | AC-1448-02 | 5 | 118.53 | 592.65 | O
M1-02 | 20 | SO | 488758 | 1 | 2 | C10530 | UPS GND | 2%10N30 | B11 | A | EA | AERO | 05 | 2022-04-15 | 2022-05-14 | AC-3231-10 | 39 | 168.08 | 6555.12 | P
M1-02 | 20 | SO | 480398 | 12 | 1 | C10252 | LTL | N45 | B11 | D | EA | MRO | 05 | 2022-01-05 | 2022-05-05 | AC-6482-03 | 41 | 80.7 | 3308.7 | O
M1-02 | 20 | SO | 486787 | 10 | 1 | C10249 | BEST WAY | N45 | B22 | NC | EA | MRO | 02 | 2022-03-10 | 2022-04-21 | AC-2561-05 | 42 | 103.44 | 4344.48 | O
M1-02 | 30 | BL | 480880 | 2 | 2 | C10525 | LTL | 2%10N30 | B11 | NC | EA | MRO | 01 | 2021-10-07 | 2022-01-07 | AC-1388-B | 50 | 160.92 | 8046 | O
M1-02 | 20 | SO | 489685 | 6 | 0 | C10377 | FDX 2D | N30 | B14 | A | EA | OEM | 02 | 2022-04-01 | 2022-06-05 | AC-4307-01 | 26 | 184.95 | 4808.7 | P
M1-02 | 30 | BL | 486807 | 10 | 2 | C10706 | BEST WAY | N30 | B22 | B | EA | MRO | 01 | 2022-01-03 | 2022-04-03 | AC-4457-B | 58 | 113.11 | 6560.38 | O
M1-02 | 30 | SO | 481227 | 2 | 1 | C10756 | BEST WAY | N30 | B22 | D | EA | OEM | 05 | 2022-04-17 | 2022-05-27 | AC-7549-05 | 88 | 116.72 | 10271.36 | O
M1-02 | 30 | SO | 489760 | 7 | 0 | C10305 | UPS GND | N45 | B07 | E | EA | MRO | 05 | 2022-03-21 | 2022-04-26 | AC-2322-03 | 32 | 158.89 | 5084.48 | P
M1-02 | 30 | SO | 484651 | 4 | 0 | C10688 | BEST WAY | 2%10N30 | B07 | C | EA | OEM | 05 | 2022-02-02 | 2022-03-28 | AC-2141-03 | 58 | 158.16 | 9173.28 | O
M1-02 | 20 | BL | 483786 | 11 | 1 | C10806 | CUST PU | 2%10N30 | B14 | D | EA | OEM | 02 | 2021-11-27 | 2022-02-16 | AC-8329-02 | 70 | 45.44 | 3180.8 | O
M1-02 | 20 | SO | 487734 | 3 | 0 | C10695 | CUST PU | N60 | B07 | D | EA | DEF | 02 | 2021-08-20 | 2021-12-13 | AC-6827-05 | 39 | 161.74 | 6307.86 | P
M1-02 | 30 | BL | 485016 | 1 | 1 | C10455 | UPS GND | 2%10N30 | B14 | E | EA | OEM | 05 | 2022-02-25 | 2022-06-07 | AC-6550-01 | 11 | 45.04 | 495.44 | O
M1-02 | 30 | BL | 484764 | 11 | 1 | C10211 | BEST WAY | N30 | B11 | E | EA | OEM | 01 | 2022-01-24 | 2022-04-15 | AC-2098-10 | 5 | 95.8 | 479 | O
M1-02 | 30 | BL | 486759 | 3 | 1 | C10385 | FDX 2D | N45 | B14 | B | EA | MRO | 02 | 2021-03-28 | 2021-06-25 | AC-7489-01 | 81 | 151.67 | 12285.27 | O
M1-02 | 30 | SO | 481748 | 4 | 0 | C10664 | FDX 2D | N45 | B11 | D | EA | OEM | 02 | 2021-12-07 | 2022-04-01 | AC-9569-A | 76 | 176.99 | 13451.24 | O
M1-02 | 20 | SO | 485710 | 11 | 0 | C10316 | UPS GND | 2%10N30 | B07 | D | EA | DEF | 01 | 2022-02-26 | 2022-04-17 | AC-5876-02 | 83 | 163.37 | 13559.71 | O
M1-02 | 20 | SO | 485757 | 9 | 2 | C10817 | LTL | 2%10N30 | B11 | B | EA | AERO | 05 | 2021-12-10 | 2022-03-24 | AC-1337-02 | 37 | 86.66 | 3206.42 | O
M1-02 | 30 | SO | 480614 | 12 | 0 | C10249 | UPS GND | N45 | B14 | E | EA | DEF | 05 | 2022-01-08 | 2022-04-08 | AC-6988-03 | 98 | 116.22 | 11389.56 | O
M1-02 | 20 | BL | 485826 | 4 | 2 | C10695 | UPS GND | N60 | B07 | A | EA | OEM | 05 | 2022-04-07 | 2022-06-04 | AC-6293-05 | 37 | 129.5 | 4791.5 | O
M1-02 | 20 | SO | 489669 | 6 | 2 | C10519 | CUST PU | N60 | B07 | C | EA | AERO | 01 | 2022-03-24 | 2022-05-16 | AC-1773-02 | 8 | 29.44 | 235.52 | P
M1-02 | 20 | SO | 489368 | 4 | 3 | C10273 | FDX 2D | N45 | B14 | C | EA | DEF | 05 | 2022-04-29 | 2022-06-10 | AC-3196-A | 6 | 56.75 | 340.5 | P
M1-02 | 30 | SO | 485259 | 5 | 2 | C10589 | FDX 2D | N30 | B07 | A | EA | MRO | 05 | 2021-12-30 | 2022-04-03 | AC-6433-A | 81 | 128.59 | 10415.79 | O
M1-02 | 20 | SO | 484626 | 9 | 2 | C10852 | CUST PU | 2%10N30 | B07 | E | EA | MRO | 01 | 2022-02-16 | 2022-05-30 | AC-5838-05 | 35 | 83.88 | 2935.8 | O
M1-02 | 20 | SO | 489607 | 3 | 0 | C10251 | UPS GND | N45 | B14 | E | EA | OEM | 01 | 2022-04-22 | 2022-06-09 | AC-7953-A | 14 | 125.44 | 1756.16 | P
M1-02 | 30 | SO | 483368 | 3 | 0 | C10280 | CUST PU | N60 | B22 | B | EA | MRO | 02 | 2022-01-16 | 2022-05-12 | AC-7896-01 | 39 | 112.41 | 4383.99 | O
M1-02 | 20 | SO | 486557 | 3 | 2 | C10758 | LTL | N45 | B14 | A | EA | AERO | 05 | 2022-02-03 | 2022-05-03 | AC-2049-05 | 16 | 69.64 | 1114.24 | O
M1-02 | 30 | BL | 484824 | 3 | 1 | C10252 | FDX 2D | N30 | B07 | D | EA | DEF | 02 | 2022-01-04 | 2022-03-13 | AC-4693-05 | 13 | 108.11 | 1405.43 | O
M1-02 | 30 | SO | 486308 | 7 | 0 | C10530 | FDX 2D | N30 | B11 | NC | EA | AERO | 01 | 2021-05-24 | 2021-06-27 | AC-8703-B | 30 | 147.47 | 4424.1 | O
M1-02 | 20 | SO | 483556 | 4 | 1 | C10385 | UPS GND | N45 | B11 | D | EA | DEF | 01 | 2022-02-04 | 2022-05-13 | AC-7378-B | 35 | 133.73 | 4680.55 | O
M1-02 | 20 | SO | 487276 | 3 | 2 | C10385 | UPS GND | N60 | B07 | B | EA | AERO | 05 | 2022-03-03 | 2022-04-22 | AC-1651-01 | 87 | 96.65 | 8408.55 | O
M1-02 | 20 | SO | 484705 | 6 | 2 | C10860 | LTL | N30 | B14 | B | EA | AERO | 01 | 2021-12-29 | 2022-04-22 | AC-6234-02 | 60 | 111.18 | 6670.8 | O
M1-02 | 30 | SO | 486581 | 10 | 3 | C10238 | BEST WAY | N45 | B11 | E | EA | DEF | 02 | 2021-12-12 | 2022-04-02 | AC-3649-B | 9 | 152.23 | 1370.07 | O
M1-02 | 30 | SO | 484578 | 4 | 1 | C10746 | UPS GND | N30 | B14 | B | EA | OEM | 02 | 2021-11-09 | 2022-03-26 | AC-6625-10 | 7 | 105.75 | 740.25 | O
M1-02 | 30 | SO | 488733 | 11 | 2 | C10519 | LTL | N60 | B07 | B | EA | OEM | 02 | 2021-08-30 | 2021-12-16 | AC-9141-03 | 29 | 135.31 | 3923.99 | P
M1-02 | 20 | SO | 483977 | 9 | 3 | C10951 | BEST WAY | N30 | B11 | E | EA | OEM | 02 | 2021-04-06 | 2021-07-08 | AC-1973-B | 13 | 101.89 | 1324.57 | O
M1-02 | 30 | SO | 487906 | 11 | 3 | C10752 | FDX 2D | N45 | B11 | B | EA | OEM | 02 | 2022-02-09 | 2022-05-08 | AC-7019-10 | 16 | 129.52 | 2072.32 | P
M1-02 | 20 | SO | 483992 | 1 | 3 | C10256 | LTL | 2%10N30 | B07 | E | EA | OEM | 01 | 2022-03-02 | 2022-05-01 | AC-1409-05 | 84 | 72.55 | 6094.2 | O
M1-02 | 30 | SO | 489256 | 4 | 3 | C10170 | CUST PU | 2%10N30 | B07 | B | EA | OEM | 02 | 2022-02-11 | 2022-05-28 | AC-4972-05 | 39 | 136.81 | 5335.59 | P
M1-02 | 20 | SO | 481120 | 1 | 0 | C10936 | CUST PU | N60 | B07 | E | EA | DEF | 02 | 2022-02-03 | 2022-03-24 | AC-7648-01 | 99 | 171.82 | 17010.18 | O
M1-02 | 20 | SO | 483242 | 7 | 2 | C10752 | FDX 2D | N60 | B14 | B | EA | MRO | 05 | 2022-02-22 | 2022-05-31 | AC-2650-03 | 92 | 52.89 | 4865.88 | O
M1-02 | 30 | SO | 484732 | 12 | 0 | C10824 | UPS GND | 2%10N30 | B14 | A | EA | MRO | 01 | 2022-04-13 | 2022-06-03 | AC-2254-02 | 13 | 60.6 | 787.8 | O
M1-02 | 20 | BL | 488269 | 11 | 3 | C10688 | FDX 2D | N45 | B14 | C | EA | OEM | 02 | 2021-12-27 | 2022-04-24 | AC-4645-05 | 25 | 157.61 | 3940.25 | P
M1-02 | 30 | SO | 482128 | 12 | 2 | C10940 | BEST WAY | N30 | B22 | D | EA | AERO | 05 | 2021-12-27 | 2022-03-24 | AC-9821-03 | 25 | 81.06 | 2026.5 | O
M1-02 | 30 | BL | 489137 | 9 | 1 | C10332 | CUST PU | N30 | B22 | A | EA | OEM | 01 | 2022-03-14 | 2022-04-18 | AC-6632-01 | 24 | 48.97 | 1175.28 | P
M1-02 | 30 | SO | 484197 | 4 | 1 | C10950 | LTL | 2%10N30 | B14 | C | EA | OEM | 05 | 2021-12-16 | 2022-04-19 | AC-1599-03 | 30 | 87.19 | 2615.7 | O
M1-02 | 30 | SO | 483139 | 9 | 3 | C10186 | UPS GND | N60 | B11 | C | EA | OEM | 02 | 2022-01-27 | 2022-04-23 | AC-3815-B | 17 | 169.91 | 2888.47 | O
M1-02 | 20 | BL | 487425 | 3 | 2 | C10806 | LTL | 2%10N30 | B11 | B | EA | MRO | 02 | 2021-05-04 | 2021-07-01 | AC-4082-10 | 40 | 92.06 | 3682.4 | P
M1-02 | 20 | SO | 487837 | 10 | 3 | C10560 | UPS GND | 2%10N30 | B07 | A | EA | MRO | 01 | 2021-07-23 | 2021-10-06 | AC-5066-03 | 25 | 84.33 | 2108.25 | P
M1-02 | 20 | BL | 483026 | 7 | 3 | C10525 | FDX 2D | N60 | B11 | D | EA | OEM | 02 | 2021-09-02 | 2021-12-29 | AC-3107-B | 54 | 127.13 | 6865.02 | O
M1-02 | 20 | SO | 487730 | 10 | 1 | C10461 | FDX 2D | N30 | B11 | E | EA | MRO | 01 | 2021-12-20 | 2022-02-02 | AC-2967-A | 49 | 100.94 | 4946.06 | P
M1-02 | 30 | SO | 488172 | 11 | 3 | C10973 | CUST PU | N60 | B11 | B | EA | OEM | 02 | 2022-01-23 | 2022-04-17 | AC-7375-B | 34 | 114.74 | 3901.16 | P
M1-02 | 20 | SO | 488294 | 10 | 0 | C10281 | CUST PU | 2%10N30 | B14 | D | EA | OEM | 02 | 2021-11-24 | 2022-03-20 | AC-3755-02 | 40 | 149.17 | 5966.8 | P
M1-02 | 20 | SO | 488222 | 7 | 0 | C10752 | LTL | N60 | B14 | NC | EA | OEM | 02 | 2022-01-05 | 2022-03-27 | AC-9448-05 | 42 | 105.52 | 4431.84 | P
M1-02 | 20 | SO | 481773 | 12 | 0 | C10331 | BEST WAY | 2%10N30 | B11 | B | EA | DEF | 02 | 2022-02-10 | 2022-05-24 | AC-7817-A | 66 | 151.67 | 10010.22 | O
M1-02 | 30 | SO | 489546 | 10 | 3 | C10456 | UPS GND | N45 | B14 | D | EA | MRO | 05 | 2022-04-04 | 2022-06-09 | AC-6682-10 | 36 | 71.54 | 2575.44 | P
M1-02 | 20 | SO | 483253 | 9 | 0 | C10752 | UPS GND | N45 | B22 | C | EA | AERO | 02 | 2022-03-10 | 2022-04-12 | AC-1140-01 | 14 | 107.39 | 1503.46 | O
M1-02 | 30 | SO | 484440 | 3 | 3 | C10966 | FDX 2D | N60 | B22 | C | EA | AERO | 02 | 2021-05-05 | 2021-07-09 | AC-6261-05 | 23 | 130.52 | 3001.96 | O
M1-02 | 30 | BL | 480813 | 3 | 2 | C10377 | UPS GND | N30 | B11 | C | EA | AERO | 01 | 2022-01-07 | 2022-05-08 | AC-4400-10 | 46 | 97.98 | 4507.08 | O
M1-02 | 20 | SO | 484387 | 8 | 0 | C10321 | BEST WAY | N30 | B07 | NC | EA | AERO | 02 | 2021-12-13 | 2022-04-20 | AC-5876-02 | 64 | 163.44 | 10460.16 | O
M1-02 | 30 | SO | 482503 | 7 | 3 | C10951 | LTL | N60 | B22 | A | EA | AERO | 02 | 2021-12-14 | 2022-04-07 | AC-9815-05 | 97 | 66.58 | 6458.26 | O
M1-02 | 20 | BL | 485980 | 6 | 2 | C10589 | LTL | N30 | B22 | A | EA | DEF | 05 | 2022-02-14 | 2022-05-09 | AC-9292-01 | 99 | 110.87 | 10976.13 | O
M1-02 | 30 | SO | 483549 | 5 | 3 | C10817 | LTL | 2%10N30 | B07 | C | EA | AERO | 02 | 2021-08-10 | 2021-10-03 | AC-7823-03 | 93 | 162.21 | 15085.53 | O
M1-02 | 20 | BL | 489427 | 3 | 2 | C10746 | CUST PU | N30 | B22 | D | EA | AERO | 02 | 2021-12-21 | 2022-03-27 | AC-6130-05 | 3 | 113.55 | 340.65 | P
M1-02 | 20 | SO | 488276 | 4 | 2 | C10695 | UPS GND | N60 | B11 | A | EA | DEF | 01 | 2021-12-25 | 2022-03-20 | AC-7219-A | 44 | 111.77 | 4917.88 | P
M1-02 | 20 | SO | 481111 | 10 | 1 | C10327 | UPS GND | 2%10N30 | B11 | B | EA | DEF | 01 | 2022-01-24 | 2022-05-16 | AC-1557-B | 16 | 55.38 | 886.08 | O
M1-02 | 20 | SO | 489706 | 7 | 3 | C10695 | UPS GND | 2%10N30 | B07 | D | EA | MRO | 05 | 2021-05-20 | 2021-08-08 | AC-4212-B | 38 | 82.33 | 3128.54 | P
M1-02 | 30 | SO | 481194 | 1 | 0 | C10273 | LTL | N60 | B22 | NC | EA | DEF | 02 | 2022-01-15 | 2022-05-30 | AC-1985-05 | 36 | 111.43 | 4011.48 | O
M1-02 | 30 | SO | 483807 | 12 | 3 | C10787 | CUST PU | 2%10N30 | B14 | E | EA | OEM | 02 | 2021-07-10 | 2021-11-05 | AC-1793-03 | 76 | 51.3 | 3898.8 | O
M1-02 | 20 | SO | 481568 | 8 | 1 | C10900 | BEST WAY | N60 | B14 | NC | EA | MRO | 02 | 2022-03-26 | 2022-04-23 | AC-5452-05 | 80 | 52.82 | 4225.6 | O
M1-02 | 20 | SO | 481770 | 4 | 0 | C10951 | BEST WAY | N30 | B22 | C | EA | DEF | 01 | 2021-05-28 | 2021-07-29 | AC-3239-01 | 33 | 102.47 | 3381.51 | O
M1-02 | 20 | SO | 484771 | 12 | 2 | C10420 | UPS GND | 2%10N30 | B11 | B | EA | OEM | 05 | 2021-12-29 | 2022-04-22 | AC-6689-03 | 66 | 55.03 | 3631.98 | O
M1-02 | 30 | SO | 485944 | 7 | 0 | C10327 | LTL | N45 | B07 | D | EA | DEF | 05 | 2022-04-30 | 2022-06-07 | AC-6612-B | 86 | 153.01 | 13158.86 | O
M1-02 | 20 | SO | 482757 | 10 | 2 | C10706 | FDX 2D | N45 | B07 | B | EA | DEF | 05 | 2022-01-12 | 2022-04-24 | AC-5963-02 | 20 | 52.41 | 1048.2 | O
M1-02 | 30 | SO | 488892 | 9 | 3 | C10860 | BEST WAY | N30 | B07 | E | EA | DEF | 01 | 2021-11-30 | 2022-04-09 | AC-1231-10 | 39 | 118.95 | 4639.05 | P
M1-02 | 20 | SO | 480779 | 8 | 3 | C10940 | FDX 2D | N45 | B22 | A | EA | DEF | 01 | 2022-01-10 | 2022-02-13 | AC-9389-03 | 58 | 92.3 | 5353.4 | O
M1-02 | 30 | SO | 483529 | 12 | 2 | C10530 | UPS GND | 2%10N30 | B07 | NC | EA | MRO | 01 | 2022-04-11 | 2022-06-06 | AC-3896-05 | 87 | 107.42 | 9345.54 | O
M1-02 | 20 | SO | 488415 | 10 | 3 | C10786 | UPS GND | 2%10N30 | B11 | B | EA | OEM | 02 | 2021-07-02 | 2021-11-17 | AC-2870-A | 24 | 161.15 | 3867.6 | P
M1-02 | 30 | SO | 481437 | 4 | 0 | C10305 | BEST WAY | 2%10N30 | B22 | E | EA | AERO | 05 | 2022-02-10 | 2022-05-25 | AC-4023-03 | 52 | 143.56 | 7465.12 | O
M1-02 | 30 | SO | 481576 | 8 | 1 | C10280 | BEST WAY | 2%10N30 | B07 | A | EA | OEM | 01 | 2021-03-16 | 2021-06-04 | AC-2870-A | 88 | 156.94 | 13810.72 | O
M1-02 | 20 | BL | 480367 | 4 | 3 | C10664 | CUST PU | N45 | B11 | A | EA | OEM | 05 | 2021-10-04 | 2021-11-07 | AC-9454-05 | 28 | 59.48 | 1665.44 | O
M1-02 | 20 | SO | 488225 | 2 | 2 | C10526 | FDX 2D | 2%10N30 | B22 | D | EA | DEF | 02 | 2021-10-06 | 2022-02-13 | AC-8498-A | 30 | 158.14 | 4744.2 | P
M1-02 | 20 | SO | 488640 | 12 | 0 | C10273 | LTL | N30 | B07 | D | EA | MRO | 05 | 2021-11-26 | 2022-03-27 | AC-8508-03 | 47 | 116.22 | 5462.34 | P
M1-02 | 20 | SO | 485989 | 5 | 3 | C10695 | FDX 2D | N45 | B11 | E | EA | AERO | 05 | 2022-02-10 | 2022-03-30 | AC-1765-02 | 94 | 60.21 | 5659.74 | O
M1-02 | 20 | SO | 482111 | 2 | 2 | C10688 | FDX 2D | N45 | B11 | D | EA | MRO | 01 | 2022-02-17 | 2022-05-22 | AC-9587-B | 76 | 99.93 | 7594.68 | O
M1-02 | 20 | SO | 487431 | 1 | 0 | C10456 | UPS GND | 2%10N30 | B11 | B | EA | OEM | 01 | 2021-02-01 | 2021-06-12 | AC-4607-A | 45 | 146.36 | 6586.2 | P
M1-02 | 30 | SO | 485301 | 5 | 0 | C10385 | FDX 2D | N30 | B11 | E | EA | DEF | 01 | 2021-12-10 | 2022-03-18 | AC-4065-10 | 16 | 164.92 | 2638.72 | O
M1-02 | 30 | BL | 481352 | 1 | 1 | C10385 | BEST WAY | N30 | B14 | B | EA | DEF | 05 | 2022-02-08 | 2022-05-31 | AC-2484-A | 94 | 94.74 | 8905.56 | O
M1-02 | 30 | SO | 485849 | 5 | 2 | C10327 | BEST WAY | 2%10N30 | B11 | A | EA | AERO | 01 | 2022-02-13 | 2022-04-25 | AC-9292-01 | 91 | 89.06 | 8104.46 | O
M1-02 | 30 | SO | 482038 | 9 | 1 | C10498 | BEST WAY | N30 | B11 | B | EA | AERO | 05 | 2022-01-15 | 2022-05-16 | AC-1017-05 | 40 | 94.26 | 3770.4 | O
M1-02 | 20 | SO | 484361 | 6 | 2 | C10321 | UPS GND | N30 | B11 | B | EA | MRO | 05 | 2021-12-07 | 2022-01-13 | AC-3920-05 | 83 | 51.67 | 4288.61 | O
M1-02 | 30 | SO | 484878 | 9 | 2 | C10756 | BEST WAY | 2%10N30 | B11 | D | EA | AERO | 01 | 2022-03-13 | 2022-06-07 | AC-3937-10 | 89 | 175.57 | 15625.73 | O
M1-02 | 30 | SO | 482830 | 10 | 2 | C10222 | LTL | N45 | B22 | B | EA | MRO | 01 | 2021-12-10 | 2022-04-28 | AC-5859-A | 11 | 121.16 | 1332.76 | O
M1-02 | 30 | SO | 484590 | 9 | 2 | C10281 | BEST WAY | N60 | B14 | D | EA | AERO | 02 | 2021-03-21 | 2021-05-31 | AC-1515-01 | 39 | 160.86 | 6273.54 | O
M1-02 | 30 | SO | 482391 | 8 | 2 | C10860 | FDX 2D | 2%10N30 | B07 | E | EA | MRO | 01 | 2022-04-23 | 2022-05-27 | AC-6008-A | 91 | 103.72 | 9438.52 | O
M1-02 | 30 | SO | 484161 | 3 | 3 | C10852 | FDX 2D | 2%10N30 | B11 | A | EA | AERO | 02 | 2022-01-19 | 2022-05-08 | AC-5526-A | 93 | 91.75 | 8532.75 | O
M1-02 | 30 | BL | 482969 | 3 | 3 | C10321 | UPS GND | N60 | B14 | A | EA | DEF | 01 | 2021-10-15 | 2022-02-09 | AC-3055-A | 92 | 138.46 | 12738.32 | O
M1-02 | 30 | BL | 480897 | 7 | 2 | C10824 | UPS GND | 2%10N30 | B11 | E | EA | AERO | 02 | 2022-03-24 | 2022-05-07 | AC-2571-A | 66 | 155.8 | 10282.8 | O
M1-02 | 30 | SO | 480603 | 5 | 2 | C10787 | BEST WAY | N60 | B07 | NC | EA | DEF | 02 | 2022-01-27 | 2022-05-21 | AC-9168-B | 72 | 48.72 | 3507.84 | O
M1-02 | 20 | SO | 483039 | 6 | 1 | C10256 | LTL | N60 | B22 | NC | EA | OEM | 05 | 2022-02-11 | 2022-03-22 | AC-3682-B | 61 | 133.47 | 8141.67 | O
M1-02 | 30 | SO | 486909 | 5 | 1 | C10498 | LTL | N60 | B22 | C | EA | OEM | 01 | 2022-03-14 | 2022-05-06 | AC-7581-01 | 85 | 78.26 | 6652.1 | O
M1-02 | 20 | BL | 485515 | 10 | 3 | C10560 | FDX 2D | N45 | B14 | NC | EA | MRO | 02 | 2021-11-29 | 2022-03-18 | AC-3002-03 | 4 | 176.6 | 706.4 | O
M1-02 | 30 | SO | 483761 | 3 | 3 | C10264 | BEST WAY | N30 | B14 | E | EA | MRO | 02 | 2021-11-12 | 2022-03-31 | AC-6295-A | 16 | 158.78 | 2540.48 | O
M1-02 | 30 | SO | 481420 | 11 | 2 | C10695 | UPS GND | N45 | B11 | D | EA | DEF | 01 | 2022-02-16 | 2022-05-15 | AC-3282-10 | 40 | 45.16 | 1806.4 | O
M1-02 | 20 | SO | 486194 | 11 | 3 | C10966 | FDX 2D | N60 | B11 | A | EA | OEM | 01 | 2021-12-17 | 2022-04-29 | AC-8486-03 | 28 | 70.47 | 1973.16 | O
M1-02 | 30 | SO | 484241 | 8 | 3 | C10530 | FDX 2D | N60 | B07 | D | EA | DEF | 02 | 2021-11-29 | 2022-04-02 | AC-1388-B | 36 | 62.01 | 2232.36 | O
M1-02 | 30 | SO | 486410 | 4 | 1 | C10501 | BEST WAY | N45 | B14 | C | EA | MRO | 05 | 2022-01-01 | 2022-04-20 | AC-8427-05 | 14 | 150.49 | 2106.86 | O
M1-02 | 30 | SO | 485959 | 5 | 0 | C10222 | LTL | N60 | B11 | D | EA | OEM | 01 | 2022-04-09 | 2022-05-09 | AC-4181-B | 41 | 47.05 | 1929.05 | O
M1-02 | 20 | SO | 484864 | 11 | 2 | C10256 | FDX 2D | 2%10N30 | B22 | NC | EA | AERO | 02 | 2021-12-17 | 2022-04-21 | AC-1767-01 | 75 | 63.92 | 4794 | O
M1-02 | 30 | SO | 489750 | 11 | 0 | C10377 | FDX 2D | N60 | B07 | NC | EA | MRO | 01 | 2022-01-30 | 2022-03-22 | AC-4600-10 | 23 | 97.21 | 2235.83 | P
M1-02 | 30 | BL | 480452 | 12 | 1 | C10252 | LTL | N30 | B07 | D | EA | MRO | 05 | 2022-01-25 | 2022-04-19 | AC-6196-10 | 28 | 99.24 | 2778.72 | O
M1-02 | 20 | SO | 486890 | 1 | 3 | C10560 | UPS GND | N45 | B11 | A | EA | AERO | 05 | 2022-04-24 | 2022-05-30 | AC-1683-10 | 82 | 131.23 | 10760.86 | O
M1-02 | 30 | SO | 480131 | 11 | 1 | C10264 | BEST WAY | N30 | B22 | B | EA | MRO | 02 | 2021-12-22 | 2022-05-06 | AC-3060-02 | 55 | 128.82 | 7085.1 | O
M1-02 | 30 | SO | 481211 | 5 | 0 | C10936 | FDX 2D | 2%10N30 | B14 | A | EA | OEM | 01 | 2021-05-25 | 2021-08-28 | AC-3815-B | 23 | 67.16 | 1544.68 | O
M1-02 | 30 | SO | 480086 | 7 | 0 | C10951 | LTL | 2%10N30 | B22 | C | EA | AERO | 02 | 2022-03-06 | 2022-04-10 | AC-4357-05 | 55 | 121.78 | 6697.9 | O
M1-02 | 30 | BL | 483971 | 9 | 0 | C10256 | CUST PU | N30 | B07 | D | EA | MRO | 05 | 2022-02-19 | 2022-05-21 | AC-1566-10 | 27 | 56.34 | 1521.18 | O
M1-02 | 30 | SO | 481683 | 9 | 1 | C10385 | FDX 2D | N45 | B07 | A | EA | DEF | 05 | 2022-02-19 | 2022-04-23 | AC-4775-03 | 13 | 125 | 1625 | O
M1-02 | 30 | SO | 488505 | 6 | 0 | C10377 | FDX 2D | N60 | B14 | A | EA | AERO | 05 | 2022-01-02 | 2022-05-14 | AC-6271-03 | 14 | 113.09 | 1583.26 | P
M1-02 | 30 | SO | 485330 | 7 | 3 | C10806 | BEST WAY | 2%10N30 | B22 | B | EA | OEM | 01 | 2021-02-24 | 2021-06-22 | AC-6565-B | 98 | 172.4 | 16895.2 | O
M1-02 | 20 | SO | 487683 | 10 | 1 | C10498 | BEST WAY | N45 | B22 | E | EA | OEM | 02 | 2021-11-02 | 2022-02-10 | AC-7457-B | 19 | 133.23 | 2531.37 | P
M1-02 | 20 | SO | 482441 | 12 | 0 | C10936 | FDX 2D | N45 | B14 | D | EA | DEF | 01 | 2021-05-11 | 2021-08-14 | AC-7213-10 | 46 | 135.84 | 6248.64 | O
M1-02 | 20 | SO | 485842 | 11 | 1 | C10746 | BEST WAY | 2%10N30 | B11 | D | EA | DEF | 01 | 2021-12-23 | 2022-02-13 | AC-3682-B | 15 | 73.36 | 1100.4 | O
M1-02 | 20 | BL | 487222 | 4 | 1 | C10973 | LTL | N60 | B07 | C | EA | OEM | 05 | 2022-02-06 | 2022-05-11 | AC-3920-05 | 73 | 125.98 | 9196.54 | O
M1-02 | 30 | BL | 483221 | 4 | 0 | C10746 | UPS GND | 2%10N30 | B22 | B | EA | AERO | 05 | 2022-04-17 | 2022-06-10 | AC-8698-10 | 73 | 44.23 | 3228.79 | O
M1-02 | 30 | BL | 486891 | 7 | 2 | C10252 | UPS GND | N60 | B07 | A | EA | MRO | 05 | 2022-02-14 | 2022-05-03 | AC-3420-02 | 24 | 150.69 | 3616.56 | O
M1-02 | 30 | BL | 489597 | 5 | 2 | C10830 | BEST WAY | N60 | B07 | B | EA | AERO | 02 | 2021-08-11 | 2021-10-17 | AC-4162-03 | 2 | 72.21 | 144.42 | P
M1-02 | 20 | SO | 481871 | 12 | 2 | C10530 | UPS GND | 2%10N30 | B22 | D | EA | AERO | 01 | 2021-04-15 | 2021-06-23 | AC-2563-10 | 68 | 172.34 | 11719.12 | O
M1-02 | 30 | SO | 488216 | 6 | 2 | C10256 | LTL | 2%10N30 | B07 | A | EA | MRO | 02 | 2021-07-23 | 2021-09-08 | AC-9246-03 | 15 | 69.67 | 1045.05 | P
M1-02 | 30 | SO | 485214 | 10 | 3 | C10746 | BEST WAY | N60 | B14 | C | EA | OEM | 02 | 2022-04-07 | 2022-06-03 | AC-1424-03 | 57 | 87.37 | 4980.09 | O
M1-02 | 30 | SO | 480815 | 11 | 0 | C10560 | BEST WAY | 2%10N30 | B14 | C | EA | DEF | 01 | 2022-02-02 | 2022-05-06 | AC-7277-A | 44 | 49.53 | 2179.32 | O
M1-02 | 30 | BL | 488134 | 12 | 3 | C10526 | UPS GND | N45 | B11 | D | EA | AERO | 01 | 2021-10-09 | 2022-01-31 | AC-2723-03 | 26 | 77 | 2002 | P
M1-02 | 30 | SO | 488380 | 5 | 1 | C10170 | FDX 2D | N30 | B22 | C | EA | AERO | 05 | 2022-01-11 | 2022-05-07 | AC-6861-01 | 10 | 101.1 | 1011 | P
M1-02 | 30 | BL | 485035 | 12 | 3 | C10251 | FDX 2D | N60 | B11 | B | EA | DEF | 02 | 2022-03-24 | 2022-05-15 | AC-1448-02 | 63 | 85.14 | 5363.82 | O
M1-02 | 20 | SO | 483691 | 8 | 1 | C10786 | UPS GND | N30 | B22 | D | EA | MRO | 02 | 2022-04-04 | 2022-05-15 | AC-3237-B | 49 | 150.66 | 7382.34 | O
M1-02 | 20 | SO | 482603 | 2 | 2 | C10568 | UPS GND | N45 | B14 | NC | EA | OEM | 01 | 2022-02-11 | 2022-04-18 | AC-6295-05 | 94 | 98.79 | 9286.26 | O
M1-02 | 20 | SO | 485892 | 5 | 3 | C10211 | UPS GND | N60 | B22 | A | EA | OEM | 01 | 2021-11-02 | 2021-12-14 | AC-6891-02 | 50 | 73.02 | 3651 | O
M1-02 | 20 | SO | 482253 | 1 | 3 | C10752 | UPS GND | 2%10N30 | B11 | D | EA | DEF | 01 | 2022-03-10 | 2022-04-30 | AC-5070-03 | 31 | 68.26 | 2116.06 | O
M1-02 | 30 | BL | 488506 | 3 | 3 | C10222 | FDX 2D | 2%10N30 | B11 | B | EA | MRO | 01 | 2021-06-01 | 2021-09-23 | AC-1448-02 | 59 | 112.2 | 6619.8 | P
M1-02 | 20 | SO | 484421 | 9 | 2 | C10385 | CUST PU | N60 | B07 | E | EA | DEF | 02 | 2021-03-12 | 2021-06-18 | AC-5088-05 | 25 | 96.14 | 2403.5 | O
M1-02 | 30 | SO | 482664 | 3 | 1 | C10950 | FDX 2D | N30 | B07 | E | EA | MRO | 02 | 2022-02-12 | 2022-04-11 | AC-8566-B | 37 | 173.18 | 6407.66 | O
M1-02 | 30 | SO | 480677 | 5 | 1 | C10756 | LTL | N60 | B07 | C | EA | AERO | 01 | 2021-04-15 | 2021-08-28 | AC-1382-B | 95 | 155.95 | 14815.25 | O
M1-02 | 20 | SO | 484033 | 5 | 1 | C10950 | UPS GND | N60 | B07 | B | EA | DEF | 05 | 2021-06-22 | 2021-09-06 | AC-9382-03 | 46 | 127.31 | 5856.26 | O
M1-02 | 30 | BL | 483920 | 5 | 0 | C10530 | FDX 2D | 2%10N30 | B07 | D | EA | OEM | 05 | 2021-06-20 | 2021-08-30 | AC-6295-05 | 90 | 113.86 | 10247.4 | O
M1-02 | 30 | BL | 483883 | 4 | 1 | C10525 | FDX 2D | N45 | B22 | D | EA | AERO | 05 | 2022-02-04 | 2022-06-06 | AC-9800-A | 32 | 142.31 | 4553.92 | O
M1-02 | 30 | BL | 481408 | 1 | 3 | C10211 | UPS GND | 2%10N30 | B22 | C | EA | MRO | 05 | 2022-03-05 | 2022-06-01 | AC-1559-05 | 29 | 96.06 | 2785.74 | O
M1-02 | 30 | SO | 480414 | 6 | 0 | C10560 | CUST PU | N30 | B22 | C | EA | OEM | 01 | 2022-01-27 | 2022-06-08 | AC-3631-03 | 98 | 43.65 | 4277.7 | O
M1-02 | 30 | BL | 488055 | 11 | 2 | C10264 | CUST PU | N60 | B11 | A | EA | AERO | 02 | 2021-10-02 | 2021-12-11 | AC-7062-10 | 22 | 131.57 | 2894.54 | P
M1-02 | 30 | SO | 489387 | 9 | 1 | C10544 | BEST WAY | 2%10N30 | B07 | E | EA | DEF | 05 | 2021-11-14 | 2022-03-26 | AC-1891-03 | 28 | 135.11 | 3783.08 | P
M1-02 | 30 | SO | 486550 | 4 | 2 | C10758 | UPS GND | 2%10N30 | B14 | E | EA | AERO | 05 | 2021-12-26 | 2022-03-27 | AC-4289-01 | 45 | 62.22 | 2799.9 | O
M1-02 | 30 | SO | 484897 | 5 | 1 | C10787 | CUST PU | N45 | B07 | C | EA | DEF | 05 | 2021-03-07 | 2021-06-27 | AC-1409-05 | 81 | 92.61 | 7501.41 | O
M1-02 | 20 | SO | 487188 | 10 | 3 | C10455 | FDX 2D | N30 | B22 | C | EA | OEM | 02 | 2022-04-30 | 2022-06-10 | AC-6537-05 | 43 | 67.73 | 2912.39 | O
M1-02 | 20 | SO | 488648 | 4 | 1 | C10706 | UPS GND | N30 | B22 | C | EA | OEM | 02 | 2022-02-24 | 2022-04-20 | AC-4980-01 | 43 | 44.57 | 1916.51 | P
M1-02 | 30 | SO | 488645 | 2 | 3 | C10695 | BEST WAY | N30 | B07 | B | EA | MRO | 02 | 2021-06-21 | 2021-07-21 | AC-1883-02 | 42 | 93.67 | 3934.14 | P
M1-02 | 20 | SO | 485952 | 10 | 3 | C10264 | CUST PU | N60 | B14 | C | EA | MRO | 05 | 2021-12-03 | 2022-04-22 | AC-9491-03 | 93 | 50.74 | 4718.82 | O
M1-02 | 30 | BL | 484467 | 1 | 1 | C10695 | UPS GND | N30 | B11 | NC | EA | MRO | 05 | 2022-02-09 | 2022-05-15 | AC-1773-B | 65 | 124.87 | 8116.55 | O
M1-02 | 30 | SO | 488766 | 12 | 1 | C10456 | UPS GND | 2%10N30 | B11 | B | EA | OEM | 05 | 2021-04-23 | 2021-07-01 | AC-5901-A | 20 | 160.38 | 3207.6 | P
M1-02 | 20 | SO | 489167 | 3 | 2 | C10385 | BEST WAY | 2%10N30 | B11 | E | EA | OEM | 05 | 2022-01-09 | 2022-03-21 | AC-3147-10 | 6 | 33.11 | 198.66 | P
M1-02 | 30 | SO | 485308 | 3 | 2 | C10316 | CUST PU | 2%10N30 | B14 | A | EA | MRO | 05 | 2022-01-06 | 2022-05-14 | AC-7648-01 | 69 | 146.82 | 10130.58 | O
M1-02 | 20 | BL | 486868 | 4 | 2 | C10706 | UPS GND | N60 | B22 | NC | EA | AERO | 02 | 2022-02-17 | 2022-04-06 | AC-6169-A | 17 | 121.88 | 2071.96 | O
M1-02 | 20 | BL | 485644 | 6 | 0 | C10501 | FDX 2D | N60 | B22 | NC | EA | AERO | 01 | 2022-02-27 | 2022-05-21 | AC-4541-05 | 17 | 104.05 | 1768.85 | O
M1-02 | 20 | SO | 483902 | 3 | 2 | C10377 | CUST PU | 2%10N30 | B22 | C | EA | OEM | 05 | 2021-11-28 | 2022-03-18 | AC-7511-03 | 31 | 153.84 | 4769.04 | O
M1-02 | 20 | BL | 481265 | 5 | 2 | C10456 | CUST PU | N30 | B11 | A | EA | MRO | 05 | 2022-02-08 | 2022-06-01 | AC-8595-05 | 38 | 49.52 | 1881.76 | O
M1-02 | 30 | SO | 489553 | 5 | 0 | C10377 | UPS GND | N60 | B22 | B | EA | MRO | 01 | 2021-12-23 | 2022-03-15 | AC-4307-01 | 6 | 168.1 | 1008.6 | P
M1-02 | 20 | BL | 487549 | 1 | 1 | C10526 | UPS GND | N45 | B07 | E | EA | OEM | 02 | 2021-12-18 | 2022-03-09 | AC-2415-B | 9 | 110.19 | 991.71 | P
M1-02 | 20 | SO | 482279 | 12 | 2 | C10249 | CUST PU | N45 | B07 | NC | EA | OEM | 05 | 2022-01-17 | 2022-05-18 | AC-3141-10 | 77 | 99.73 | 7679.21 | O
M1-02 | 30 | BL | 485114 | 11 | 1 | C10824 | LTL | N30 | B07 | D | EA | DEF | 02 | 2022-02-14 | 2022-06-04 | AC-1978-10 | 19 | 72 | 1368 | O
M1-02 | 20 | SO | 482178 | 1 | 0 | C10211 | BEST WAY | N60 | B22 | C | EA | DEF | 01 | 2021-05-24 | 2021-08-07 | AC-5594-10 | 36 | 161.1 | 5799.6 | O
M1-02 | 30 | SO | 485890 | 3 | 1 | C10238 | CUST PU | 2%10N30 | B14 | NC | EA | OEM | 01 | 2022-02-01 | 2022-03-19 | AC-7103-B | 84 | 104.42 | 8771.28 | O
M1-02 | 30 | SO | 482803 | 8 | 3 | C10211 | BEST WAY | 2%10N30 | B14 | C | EA | OEM | 05 | 2021-11-07 | 2021-12-26 | AC-3758-02 | 32 | 72.74 | 2327.68 | O
M1-02 | 30 | BL | 488874 | 6 | 0 | C10316 | BEST WAY | N30 | B14 | D | EA | MRO | 01 | 2022-03-14 | 2022-04-23 | AC-6197-02 | 10 | 182.91 | 1829.1 | P
M1-02 | 20 | SO | 489515 | 5 | 1 | C10455 | FDX 2D | N30 | B07 | A | EA | AERO | 05 | 2021-12-24 | 2022-03-28 | AC-7348-02 | 16 | 116 | 1856 | P
M1-02 | 20 | SO | 485294 | 9 | 2 | C10249 | BEST WAY | N30 | B07 | NC | EA | AERO | 02 | 2022-01-16 | 2022-03-28 | AC-1424-03 | 90 | 46.08 | 4147.2 | O
M1-02 | 20 | SO | 486815 | 1 | 3 | C10385 | LTL | N60 | B11 | C | EA | AERO | 01 | 2021-09-19 | 2021-11-17 | AC-4357-05 | 80 | 148.61 | 11888.8 | O
M1-02 | 20 | SO | 487220 | 7 | 2 | C10420 | FDX 2D | N30 | B22 | B | EA | DEF | 05 | 2022-02-26 | 2022-04-02 | AC-3896-A | 55 | 176.54 | 9709.7 | O
M1-02 | 30 | BL | 484739 | 7 | 0 | C10950 | UPS GND | N30 | B22 | B | EA | DEF | 05 | 2022-01-31 | 2022-04-03 | AC-1467-01 | 14 | 118 | 1652 | O
M1-02 | 20 | SO | 481809 | 9 | 0 | C10830 | BEST WAY | N30 | B07 | D | EA | DEF | 05 | 2021-12-26 | 2022-04-27 | AC-2610-A | 10 | 140.4 | 1404 | O
M1-02 | 30 | SO | 489799 | 3 | 2 | C10170 | BEST WAY | N60 | B11 | C | EA | MRO | 01 | 2021-12-04 | 2022-04-15 | AC-4307-01 | 29 | 108.26 | 3139.54 | P
M1-02 | 20 | BL | 485208 | 10 | 0 | C10251 | FDX 2D | 2%10N30 | B11 | B | EA | MRO | 05 | 2021-06-21 | 2021-07-24 | AC-7102-A | 45 | 146.99 | 6614.55 | O
M1-02 | 20 | BL | 487860 | 12 | 1 | C10806 | FDX 2D | N30 | B22 | A | EA | MRO | 01 | 2021-05-08 | 2021-09-13 | AC-5713-01 | 38 | 166.71 | 6334.98 | P
M1-02 | 30 | SO | 482978 | 12 | 1 | C10331 | UPS GND | N30 | B14 | B | EA | OEM | 02 | 2022-02-25 | 2022-05-14 | AC-9838-B | 94 | 109.07 | 10252.58 | O
M1-02 | 20 | SO | 483247 | 2 | 1 | C10973 | CUST PU | 2%10N30 | B11 | D | EA | MRO | 01 | 2022-02-01 | 2022-04-03 | AC-5859-A | 100 | 93.76 | 9376 | O
M1-02 | 30 | BL | 484970 | 8 | 0 | C10461 | FDX 2D | 2%10N30 | B07 | B | EA | OEM | 02 | 2022-02-14 | 2022-05-24 | AC-2427-01 | 44 | 66.54 | 2927.76 | O
M1-02 | 20 | BL | 485135 | 3 | 2 | C10589 | UPS GND | N45 | B22 | E | EA | MRO | 01 | 2021-07-28 | 2021-11-28 | AC-7743-10 | 20 | 159.19 | 3183.8 | O
M1-02 | 20 | BL | 482729 | 12 | 1 | C10316 | FDX 2D | N30 | B22 | B | EA | AERO | 01 | 2022-02-07 | 2022-05-10 | AC-4561-10 | 45 | 92.93 | 4181.85 | O
M1-02 | 30 | SO | 483312 | 4 | 0 | C10950 | UPS GND | N30 | B14 | A | EA | AERO | 01 | 2021-12-25 | 2022-03-27 | AC-2924-03 | 72 | 171.51 | 12348.72 | O
M1-02 | 30 | SO | 485664 | 11 | 2 | C10530 | CUST PU | 2%10N30 | B14 | E | EA | AERO | 02 | 2021-07-27 | 2021-11-17 | AC-7648-01 | 87 | 158.43 | 13783.41 | O
M1-02 | 30 | SO | 485623 | 9 | 0 | C10900 | LTL | N30 | B22 | B | EA | OEM | 01 | 2022-02-10 | 2022-03-31 | AC-1141-02 | 21 | 66.94 | 1405.74 | O
M1-02 | 20 | SO | 488064 | 11 | 0 | C10461 | UPS GND | N60 | B22 | B | EA | DEF | 05 | 2021-12-16 | 2022-04-21 | AC-4825-B | 17 | 75.39 | 1281.63 | P
M1-02 | 20 | BL | 489407 | 7 | 2 | C10900 | CUST PU | N60 | B07 | A | EA | AERO | 02 | 2021-12-09 | 2022-04-20 | AC-5092-02 | 9 | 119.3 | 1073.7 | P
M1-02 | 20 | BL | 483576 | 11 | 3 | C10420 | UPS GND | 2%10N30 | B11 | C | EA | MRO | 01 | 2021-05-25 | 2021-09-21 | AC-4590-A | 54 | 72.21 | 3899.34 | O
M1-02 | 20 | BL | 489158 | 1 | 0 | C10251 | UPS GND | N30 | B07 | B | EA | OEM | 05 | 2021-12-21 | 2022-04-07 | AC-5148-01 | 11 | 77.98 | 857.78 | P
M1-02 | 30 | SO | 483963 | 6 | 2 | C10461 | CUST PU | N45 | B07 | C | EA | OEM | 02 | 2022-02-19 | 2022-04-08 | AC-8341-03 | 59 | 69.57 | 4104.63 | O
M1-02 | 30 | SO | 489332 | 2 | 1 | C10273 | FDX 2D | N45 | B14 | C | EA | MRO | 02 | 2021-04-25 | 2021-07-27 | AC-1787-01 | 24 | 60.71 | 1457.04 | P
M1-02 | 20 | BL | 487131 | 8 | 0 | C10525 | UPS GND | 2%10N30 | B07 | E | EA | MRO | 05 | 2022-03-21 | 2022-06-03 | AC-5562-B | 75 | 174.97 | 13122.75 | O
M1-02 | 20 | BL | 483282 | 3 | 0 | C10385 | UPS GND | N30 | B14 | E | EA | AERO | 02 | 2021-10-20 | 2022-02-08 | AC-5088-05 | 55 | 104.7 | 5758.5 | O
M1-02 | 20 | SO | 481441 | 8 | 2 | C10900 | FDX 2D | N45 | B07 | C | EA | AERO | 05 | 2022-02-18 | 2022-03-24 | AC-8706-02 | 80 | 61.38 | 4910.4 | O
M1-02 | 20 | BL | 488928 | 8 | 0 | C10852 | CUST PU | N30 | B14 | A | EA | MRO | 01 | 2021-09-29 | 2021-12-06 | AC-9720-A | 19 | 84.65 | 1608.35 | P
M1-02 | 20 | BL | 488160 | 3 | 1 | C10950 | FDX 2D | N45 | B11 | NC | EA | MRO | 02 | 2021-11-12 | 2021-12-20 | AC-3047-05 | 29 | 139.14 | 4035.06 | P
M1-02 | 20 | SO | 482845 | 3 | 2 | C10251 | CUST PU | N45 | B07 | NC | EA | OEM | 01 | 2021-05-28 | 2021-09-29 | AC-3792-05 | 64 | 123.14 | 7880.96 | O
M1-02 | 30 | SO | 488970 | 11 | 3 | C10530 | BEST WAY | N30 | B11 | D | EA | DEF | 02 | 2022-01-21 | 2022-05-06 | AC-7567-01 | 39 | 93.03 | 3628.17 | P
M1-02 | 20 | SO | 484832 | 11 | 1 | C10966 | BEST WAY | N60 | B07 | E | EA | DEF | 02 | 2022-02-18 | 2022-05-15 | AC-7743-10 | 59 | 107.33 | 6332.47 | O
M1-02 | 20 | SO | 480719 | 9 | 2 | C10327 | BEST WAY | N45 | B11 | C | EA | DEF | 05 | 2022-03-26 | 2022-05-01 | AC-2063-10 | 96 | 168.69 | 16194.24 | O
M1-02 | 20 | SO | 484693 | 11 | 0 | C10211 | CUST PU | 2%10N30 | B07 | B | EA | DEF | 02 | 2022-01-16 | 2022-03-19 | AC-2943-01 | 29 | 161.71 | 4689.59 | O
M1-02 | 20 | SO | 483942 | 1 | 3 | C10186 | CUST PU | N60 | B11 | B | EA | MRO | 01 | 2022-01-31 | 2022-05-26 | AC-6385-10 | 41 | 117.73 | 4826.93 | O
M1-02 | 20 | BL | 486699 | 8 | 3 | C10824 | FDX 2D | 2%10N30 | B14 | C | EA | OEM | 01 | 2021-10-02 | 2022-02-11 | AC-9773-02 | 66 | 98.96 | 6531.36 | O
M1-02 | 20 | SO | 487919 | 3 | 2 | C10350 | BEST WAY | N45 | B11 | C | EA | DEF | 02 | 2021-10-31 | 2022-01-01 | AC-3471-10 | 45 | 51.58 | 2321.1 | P
M1-02 | 30 | SO | 485271 | 5 | 2 | C10544 | CUST PU | N30 | B07 | NC | EA | DEF | 02 | 2022-02-19 | 2022-04-02 | AC-8538-03 | 69 | 154.33 | 10648.77 | O
M1-02 | 30 | BL | 482151 | 12 | 1 | C10238 | BEST WAY | 2%10N30 | B11 | NC | EA | DEF | 01 | 2021-12-04 | 2022-04-20 | AC-2613-10 | 42 | 43.12 | 1811.04 | O
M1-02 | 30 | SO | 486558 | 1 | 0 | C10281 | FDX 2D | N45 | B07 | A | EA | MRO | 01 | 2021-03-05 | 2021-06-11 | AC-5581-01 | 79 | 145.19 | 11470.01 | O
M1-02 | 20 | SO | 482469 | 7 | 1 | C10385 | LTL | N60 | B07 | NC | EA | DEF | 02 | 2022-01-17 | 2022-04-30 | AC-8915-05 | 85 | 136.95 | 11640.75 | O
M1-02 | 20 | SO | 483524 | 9 | 2 | C10273 | LTL | N30 | B22 | D | EA | OEM | 02 | 2022-01-12 | 2022-04-08 | AC-4268-A | 92 | 113.78 | 10467.76 | O
M1-02 | 20 | SO | 480946 | 8 | 3 | C10280 | LTL | N60 | B07 | B | EA | DEF | 05 | 2022-01-04 | 2022-04-15 | AC-2132-B | 94 | 93.72 | 8809.68 | O
M1-02 | 20 | SO | 482485 | 2 | 3 | C10501 | FDX 2D | N45 | B22 | E | EA | MRO | 05 | 2022-01-15 | 2022-03-20 | AC-7196-A | 7 | 124.29 | 870.03 | O
M1-02 | 20 | SO | 480390 | 2 | 1 | C10170 | BEST WAY | 2%10N30 | B22 | B | EA | MRO | 05 | 2022-03-30 | 2022-04-28 | AC-3896-A | 83 | 44.37 | 3682.71 | O
M1-02 | 30 | SO | 484526 | 6 | 2 | C10950 | FDX 2D | 2%10N30 | B14 | E | EA | OEM | 01 | 2022-04-23 | 2022-05-30 | AC-1310-B | 6 | 155.89 | 935.34 | O
M1-02 | 30 | SO | 489097 | 11 | 3 | C10758 | LTL | N45 | B22 | A | EA | AERO | 05 | 2022-02-11 | 2022-03-26 | AC-3542-03 | 37 | 69.85 | 2584.45 | P
M1-02 | 20 | BL | 487339 | 5 | 0 | C10824 | LTL | N60 | B07 | D | EA | OEM | 01 | 2022-02-25 | 2022-03-30 | AC-7182-03 | 79 | 167.08 | 13199.32 | O
M1-02 | 20 | SO | 487596 | 2 | 2 | C10170 | UPS GND | N45 | B22 | C | EA | MRO | 05 | 2021-04-21 | 2021-08-22 | AC-4215-05 | 52 | 44.15 | 2295.8 | P
M1-02 | 20 | BL | 481061 | 12 | 2 | C10251 | BEST WAY | N60 | B11 | C | EA | OEM | 01 | 2022-01-16 | 2022-03-15 | AC-6182-03 | 85 | 163.32 | 13882.2 | O
M1-02 | 30 | SO | 487255 | 7 | 1 | C10664 | CUST PU | N60 | B14 | B | EA | MRO | 05 | 2022-01-25 | 2022-04-25 | AC-3282-10 | 41 | 74.35 | 3048.35 | O
M1-02 | 20 | SO | 480404 | 12 | 3 | C10525 | CUST PU | 2%10N30 | B22 | E | EA | OEM | 02 | 2022-03-25 | 2022-05-01 | AC-5010-A | 25 | 123.33 | 3083.25 | O
M1-02 | 20 | BL | 486571 | 1 | 1 | C10264 | UPS GND | N30 | B11 | NC | EA | DEF | 02 | 2021-11-27 | 2022-04-02 | AC-8201-A | 63 | 123.95 | 7808.85 | O
M1-02 | 20 | SO | 486563 | 10 | 0 | C10385 | CUST PU | N45 | B07 | A | EA | MRO | 01 | 2021-11-29 | 2022-03-18 | AC-3631-03 | 75 | 47.05 | 3528.75 | O
M1-02 | 30 | SO | 483697 | 7 | 2 | C10525 | FDX 2D | N30 | B14 | C | EA | MRO | 02 | 2022-04-01 | 2022-06-07 | AC-7699-03 | 96 | 64.59 | 6200.64 | O
M1-02 | 20 | SO | 486832 | 6 | 2 | C10222 | CUST PU | N45 | B22 | E | EA | OEM | 05 | 2022-04-11 | 2022-05-22 | AC-2960-10 | 34 | 139.74 | 4751.16 | O
M1-02 | 30 | SO | 482686 | 7 | 3 | C10281 | UPS GND | N45 | B14 | C | EA | DEF | 05 | 2022-01-03 | 2022-02-23 | AC-3682-B | 32 | 176.26 | 5640.32 | O
M1-02 | 20 | SO | 489195 | 5 | 2 | C10249 | BEST WAY | N30 | B14 | D | EA | DEF | 05 | 2021-03-18 | 2021-06-10 | AC-9577-02 | 23 | 140.23 | 3225.29 | P
M1-02 | 20 | BL | 485984 | 5 | 3 | C10332 | CUST PU | N45 | B11 | NC | EA | AERO | 05 | 2021-07-03 | 2021-10-21 | AC-6028-B | 47 | 174.01 | 8178.47 | O
M1-02 | 30 | SO | 485977 | 8 | 0 | C10327 | LTL | N60 | B14 | C | EA | DEF | 01 | 2021-11-16 | 2022-02-02 | AC-4033-01 | 70 | 77.94 | 5455.8 | O
M1-02 | 20 | SO | 486323 | 8 | 3 | C10280 | BEST WAY | 2%10N30 | B07 | NC | EA | AERO | 02 | 2022-02-19 | 2022-04-01 | AC-9740-01 | 60 | 163.64 | 9818.4 | O
M1-02 | 30 | SO | 484570 | 7 | 3 | C10787 | LTL | N60 | B14 | A | EA | OEM | 02 | 2021-12-20 | 2022-04-21 | AC-6029-01 | 48 | 85.28 | 4093.44 | O
M1-02 | 20 | SO | 488403 | 5 | 3 | C10824 | UPS GND | N60 | B11 | E | EA | DEF | 02 | 2021-01-25 | 2021-06-10 | AC-6792-B | 45 | 82.77 | 3724.65 | P
M1-02 | 20 | BL | 483494 | 7 | 3 | C10525 | UPS GND | N60 | B22 | E | EA | OEM | 02 | 2021-12-22 | 2022-03-16 | AC-2998-A | 13 | 43.46 | 564.98 | O
M1-02 | 30 | SO | 484724 | 11 | 3 | C10211 | FDX 2D | N60 | B07 | E | EA | MRO | 01 | 2022-01-21 | 2022-05-08 | AC-3765-A | 88 | 115.75 | 10186 | O
M1-02 | 30 | SO | 481920 | 3 | 0 | C10973 | UPS GND | N60 | B22 | NC | EA | OEM | 01 | 2021-10-25 | 2022-02-04 | AC-8774-01 | 67 | 65.72 | 4403.24 | O
M1-02 | 20 | SO | 482815 | 7 | 1 | C10936 | UPS GND | N45 | B22 | B | EA | AERO | 01 | 2021-12-26 | 2022-04-25 | AC-1740-03 | 94 | 63.52 | 5970.88 | O
M1-02 | 30 | SO | 480058 | 1 | 0 | C10544 | BEST WAY | N45 | B11 | C | EA | OEM | 05 | 2021-12-12 | 2022-04-17 | AC-3275-03 | 22 | 110.63 | 2433.86 | O
M1-02 | 30 | SO | 482352 | 10 | 1 | C10688 | UPS GND | N45 | B22 | E | EA | MRO | 05 | 2021-11-29 | 2022-03-18 | AC-3833-03 | 55 | 85.64 | 4710.2 | O
M1-02 | 20 | SO | 482367 | 1 | 2 | C10787 | BEST WAY | 2%10N30 | B07 | C | EA | MRO | 05 | 2021-12-07 | 2022-04-21 | AC-2049-05 | 87 | 124.02 | 10789.74 | O
M1-02 | 30 | SO | 480322 | 7 | 2 | C10973 | UPS GND | 2%10N30 | B22 | E | EA | MRO | 01 | 2022-03-29 | 2022-05-18 | AC-4358-02 | 6 | 74.34 | 446.04 | O
M1-02 | 30 | BL | 485932 | 4 | 3 | C10249 | UPS GND | 2%10N30 | B11 | D | EA | DEF | 05 | 2022-01-23 | 2022-06-05 | AC-4388-B | 68 | 49.68 | 3378.24 | O
M1-02 | 20 | SO | 481784 | 1 | 3 | C10688 | CUST PU | N30 | B11 | E | EA | AERO | 01 | 2022-02-17 | 2022-05-08 | AC-6196-10 | 10 | 97.3 | 973 | O
M1-02 | 20 | BL | 484107 | 11 | 3 | C10950 | CUST PU | N30 | B22 | B | EA | OEM | 05 | 2021-11-28 | 2022-04-17 | AC-6072-03 | 62 | 99.96 | 6197.52 | O
M1-02 | 20 | SO | 483617 | 4 | 2 | C10664 | CUST PU | N30 | B07 | A | EA | MRO | 02 | 2021-12-19 | 2022-03-16 | AC-4556-A | 7 | 55.43 | 388.01 | O
M1-02 | 20 | SO | 482906 | 5 | 3 | C10824 | LTL | N30 | B07 | D | EA | AERO | 01 | 2022-02-18 | 2022-06-03 | AC-6707-10 | 42 | 162.01 | 6804.42 | O
M1-02 | 30 | SO | 480566 | 8 | 1 | C10966 | UPS GND | 2%10N30 | B07 | D | EA | DEF | 01 | 2022-02-10 | 2022-04-29 | AC-7439-02 | 20 | 147.24 | 2944.8 | O
M1-02 | 30 | SO | 487717 | 9 | 3 | C10238 | CUST PU | 2%10N30 | B14 | A | EA | DEF | 05 | 2021-11-04 | 2021-12-27 | AC-7555-03 | 8 | 169.24 | 1353.92 | P
M1-02 | 20 | SO | 480661 | 10 | 3 | C10321 | BEST WAY | N60 | B11 | C | EA | MRO | 01 | 2021-11-18 | 2022-01-04 | AC-7549-05 | 66 | 104.87 | 6921.42 | O
M1-02 | 30 | SO | 487931 | 11 | 2 | C10530 | FDX 2D | N30 | B22 | B | EA | OEM | 01 | 2021-08-14 | 2021-11-08 | AC-4825-B | 40 | 82.51 | 3300.4 | P
M1-02 | 30 | SO | 487589 | 1 | 1 | C10498 | FDX 2D | 2%10N30 | B07 | B | EA | OEM | 02 | 2021-04-05 | 2021-08-21 | AC-8994-B | 52 | 112.33 | 5841.16 | P
M1-02 | 20 | SO | 486658 | 12 | 3 | C10830 | UPS GND | N30 | B22 | D | EA | AERO | 01 | 2021-10-20 | 2022-01-23 | AC-6682-01 | 73 | 121.21 | 8848.33 | O
M1-02 | 20 | SO | 489207 | 8 | 2 | C10436 | UPS GND | N45 | B22 | E | EA | OEM | 02 | 2021-06-10 | 2021-08-11 | AC-1231-10 | 33 | 65.13 | 2149.29 | P
M1-02 | 20 | BL | 485674 | 12 | 3 | C10544 | CUST PU | 2%10N30 | B11 | B | EA | MRO | 01 | 2022-03-20 | 2022-05-05 | AC-4590-A | 45 | 84.64 | 3808.8 | O
M1-02 | 20 | SO | 488310 | 12 | 2 | C10455 | UPS GND | N45 | B11 | NC | EA | MRO | 05 | 2021-09-14 | 2021-10-31 | AC-3929-10 | 39 | 44.18 | 1723.02 | P
M1-02 | 20 | SO | 485575 | 10 | 2 | C10222 | CUST PU | N45 | B14 | C | EA | DEF | 01 | 2022-03-12 | 2022-04-14 | AC-6982-05 | 86 | 168.26 | 14470.36 | O
M1-02 | 20 | BL | 486184 | 2 | 1 | C10321 | LTL | 2%10N30 | B11 | A | EA | AERO | 05 | 2022-02-15 | 2022-06-09 | AC-8955-02 | 55 | 161.71 | 8894.05 | O
M1-02 | 20 | SO | 484129 | 12 | 3 | C10211 | UPS GND | 2%10N30 | B14 | NC | EA | DEF | 05 | 2021-12-20 | 2022-04-12 | AC-7361-10 | 58 | 66.05 | 3830.9 | O
M1-02 | 30 | BL | 489320 | 12 | 0 | C10332 | UPS GND | 2%10N30 | B11 | B | EA | MRO | 05 | 2021-11-27 | 2022-02-02 | AC-4212-B | 35 | 83.89 | 2936.15 | P
M1-02 | 20 | BL | 484205 | 3 | 0 | C10256 | FDX 2D | 2%10N30 | B11 | B | EA | AERO | 01 | 2022-02-24 | 2022-05-09 | AC-9748-05 | 73 | 138.25 | 10092.25 | O
M1-02 | 20 | SO | 487646 | 3 | 1 | C10664 | UPS GND | N30 | B14 | NC | EA | AERO | 02 | 2021-12-26 | 2022-01-24 | AC-8994-B | 33 | 169.14 | 5581.62 | P
M1-02 | 20 | SO | 484274 | 9 | 1 | C10501 | FDX 2D | N45 | B11 | E | EA | DEF | 01 | 2022-02-03 | 2022-04-07 | AC-7692-03 | 10 | 70.42 | 704.2 | O
M1-02 | 30 | SO | 484390 | 7 | 1 | C10436 | UPS GND | 2%10N30 | B07 | E | EA | OEM | 01 | 2021-12-29 | 2022-02-17 | AC-2924-03 | 40 | 151.57 | 6062.8 | O
M1-02 | 20 | BL | 487399 | 9 | 2 | C10664 | BEST WAY | N60 | B07 | D | EA | DEF | 05 | 2021-12-20 | 2022-02-26 | AC-7219-A | 17 | 87.91 | 1494.47 | P
M1-02 | 30 | BL | 486932 | 6 | 2 | C10664 | UPS GND | N30 | B22 | A | EA | MRO | 02 | 2022-03-10 | 2022-06-09 | AC-8358-03 | 77 | 59.02 | 4544.54 | O
M1-02 | 20 | SO | 486303 | 8 | 2 | C10455 | CUST PU | N30 | B11 | D | EA | AERO | 01 | 2021-11-12 | 2022-01-08 | AC-2098-10 | 69 | 101.87 | 7029.03 | O
M1-02 | 20 | SO | 485312 | 2 | 2 | C10973 | FDX 2D | N30 | B07 | B | EA | AERO | 01 | 2022-03-27 | 2022-05-28 | AC-9218-05 | 91 | 114 | 10374 | O
M1-02 | 20 | SO | 484654 | 6 | 1 | C10568 | BEST WAY | N30 | B07 | B | EA | MRO | 05 | 2022-02-02 | 2022-05-26 | AC-7135-05 | 14 | 51.02 | 714.28 | O
M1-02 | 20 | BL | 486861 | 8 | 1 | C10436 | FDX 2D | N45 | B22 | NC | EA | OEM | 05 | 2022-02-22 | 2022-05-03 | AC-8698-10 | 46 | 106.98 | 4921.08 | O
M1-02 | 20 | SO | 485021 | 7 | 2 | C10256 | LTL | 2%10N30 | B11 | D | EA | AERO | 01 | 2022-03-10 | 2022-04-24 | AC-5963-02 | 72 | 142.86 | 10285.92 | O
M1-02 | 20 | SO | 489526 | 10 | 0 | C10305 | LTL | N30 | B11 | A | EA | MRO | 05 | 2022-01-05 | 2022-05-08 | AC-8865-01 | 17 | 167.41 | 2845.97 | P
M1-02 | 20 | SO | 484899 | 1 | 2 | C10420 | FDX 2D | N30 | B11 | B | EA | AERO | 01 | 2022-04-21 | 2022-05-30 | AC-1073-B | 73 | 143.93 | 10506.89 | O
M1-02 | 20 | SO | 481694 | 4 | 2 | C10568 | FDX 2D | 2%10N30 | B22 | B | EA | OEM | 02 | 2022-03-04 | 2022-04-27 | AC-3293-A | 20 | 134 | 2680 | O
M1-02 | 20 | SO | 480927 | 10 | 0 | C10746 | BEST WAY | N45 | B07 | E | EA | DEF | 01 | 2022-03-28 | 2022-06-04 | AC-9481-02 | 11 | 100.61 | 1106.71 | O
M1-02 | 30 | BL | 482938 | 7 | 3 | C10238 | FDX 2D | N30 | B11 | A | EA | OEM | 05 | 2021-10-14 | 2022-02-06 | AC-6295-A | 45 | 46.56 | 2095.2 | O
M1-02 | 30 | SO | 489181 | 2 | 1 | C10331 | LTL | 2%10N30 | B11 | B | EA | DEF | 01 | 2021-11-17 | 2022-03-30 | AC-6859-A | 24 | 39.1 | 938.4 | P
M1-02 | 20 | SO | 489710 | 7 | 3 | C10461 | LTL | N60 | B22 | B | EA | OEM | 02 | 2021-08-28 | 2021-12-24 | AC-6197-02 | 2 | 217.72 | 435.44 | P
M1-02 | 30 | BL | 487938 | 11 | 3 | C10560 | FDX 2D | N30 | B14 | B | EA | MRO | 02 | 2021-04-15 | 2021-07-15 | AC-9290-02 | 6 | 144.53 | 867.18 | P
M1-02 | 30 | SO | 481320 | 3 | 2 | C10950 | LTL | N30 | B22 | B | EA | OEM | 05 | 2022-03-28 | 2022-05-16 | AC-3053-03 | 20 | 148.88 | 2977.6 | O
M1-02 | 20 | BL | 487638 | 12 | 0 | C10752 | FDX 2D | 2%10N30 | B07 | NC | EA | OEM | 05 | 2022-02-03 | 2022-03-25 | AC-4690-10 | 55 | 43.9 | 2414.5 | P
M1-02 | 20 | SO | 484596 | 6 | 3 | C10321 | FDX 2D | N30 | B14 | E | EA | OEM | 05 | 2021-12-25 | 2022-04-02 | AC-7122-03 | 93 | 170.12 | 15821.16 | O
M1-02 | 20 | SO | 486823 | 3 | 0 | C10860 | CUST PU | N30 | B07 | A | EA | AERO | 05 | 2021-10-06 | 2021-12-13 | AC-9587-B | 91 | 96.29 | 8762.39 | O
M1-02 | 20 | SO | 483757 | 6 | 3 | C10327 | FDX 2D | N45 | B07 | E | EA | OEM | 05 | 2021-06-01 | 2021-10-10 | AC-8050-01 | 98 | 42.71 | 4185.58 | O
M1-02 | 20 | SO | 484172 | 2 | 2 | C10252 | CUST PU | 2%10N30 | B22 | NC | EA | DEF | 05 | 2022-02-08 | 2022-05-16 | AC-4107-B | 16 | 126.69 | 2027.04 | O
M1-02 | 30 | SO | 487116 | 10 | 3 | C10281 | UPS GND | N60 | B11 | D | EA | OEM | 05 | 2022-02-19 | 2022-06-03 | AC-3107-B | 10 | 102.38 | 1023.8 | O
M1-02 | 30 | BL | 483821 | 11 | 2 | C10786 | CUST PU | N30 | B14 | E | EA | MRO | 01 | 2022-02-10 | 2022-05-21 | AC-6385-10 | 53 | 46.49 | 2463.97 | O
M1-02 | 20 | SO | 488278 | 12 | 3 | C10526 | FDX 2D | N30 | B22 | A | EA | MRO | 02 | 2022-04-05 | 2022-05-31 | AC-7108-10 | 45 | 78.37 | 3526.65 | P
M1-02 | 30 | SO | 487157 | 7 | 3 | C10900 | FDX 2D | N60 | B22 | NC | EA | AERO | 02 | 2022-05-09 | 2022-06-06 | AC-9624-02 | 19 | 95.19 | 1808.61 | O
M1-02 | 20 | BL | 487488 | 11 | 2 | C10436 | CUST PU | N30 | B22 | NC | EA | DEF | 02 | 2021-03-26 | 2021-06-24 | AC-5069-03 | 38 | 132.73 | 5043.74 | P
M1-02 | 20 | SO | 482504 | 3 | 2 | C10170 | BEST WAY | N30 | B14 | B | EA | OEM | 01 | 2022-01-24 | 2022-03-23 | AC-8900-01 | 34 | 114.66 | 3898.44 | O
M1-02 | 30 | SO | 486075 | 3 | 0 | C10321 | UPS GND | N60 | B22 | D | EA | OEM | 02 | 2022-01-26 | 2022-04-07 | AC-3287-02 | 15 | 174.88 | 2623.2 | O
M1-02 | 30 | SO | 484286 | 6 | 2 | C10281 | BEST WAY | 2%10N30 | B14 | B | EA | OEM | 02 | 2021-12-15 | 2022-04-30 | AC-7785-01 | 65 | 97.04 | 6307.6 | O
M1-02 | 20 | SO | 486273 | 3 | 1 | C10305 | FDX 2D | N45 | B07 | NC | EA | AERO | 01 | 2021-04-28 | 2021-06-03 | AC-5876-02 | 71 | 82.35 | 5846.85 | O
M1-02 | 20 | SO | 487975 | 5 | 3 | C10951 | BEST WAY | N60 | B07 | NC | EA | AERO | 02 | 2022-01-15 | 2022-02-17 | AC-7375-B | 15 | 78.66 | 1179.9 | P
M1-02 | 30 | SO | 484154 | 1 | 3 | C10331 | FDX 2D | N60 | B14 | E | EA | OEM | 01 | 2022-02-26 | 2022-05-23 | AC-3293-01 | 5 | 171.51 | 857.55 | O
M1-02 | 30 | SO | 488710 | 5 | 3 | C10170 | LTL | N30 | B11 | E | EA | MRO | 01 | 2021-05-16 | 2021-09-11 | AC-7457-B | 20 | 130.13 | 2602.6 | P
M1-02 | 30 | SO | 485437 | 8 | 2 | C10589 | BEST WAY | 2%10N30 | B07 | E | EA | DEF | 01 | 2022-02-14 | 2022-06-10 | AC-6293-05 | 95 | 65.14 | 6188.3 | O
M1-02 | 20 | SO | 482704 | 9 | 2 | C10222 | UPS GND | 2%10N30 | B11 | C | EA | OEM | 02 | 2021-12-31 | 2022-04-22 | AC-3456-10 | 16 | 163.9 | 2622.4 | O
M1-02 | 30 | SO | 488828 | 3 | 2 | C10331 | BEST WAY | N45 | B07 | E | EA | AERO | 05 | 2021-12-26 | 2022-02-08 | AC-1648-A | 29 | 113.39 | 3288.31 | P
M1-02 | 30 | SO | 481045 | 9 | 3 | C10256 | CUST PU | N30 | B14 | C | EA | OEM | 02 | 2022-03-27 | 2022-05-13 | AC-8955-02 | 29 | 46.55 | 1349.95 | O
M1-02 | 20 | SO | 482291 | 4 | 3 | C10327 | LTL | N45 | B07 | C | EA | AERO | 05 | 2021-05-16 | 2021-07-05 | AC-5441-02 | 38 | 126.56 | 4809.28 | O
M1-02 | 30 | SO | 482759 | 12 | 1 | C10436 | FDX 2D | N45 | B22 | E | EA | DEF | 01 | 2022-03-25 | 2022-05-10 | AC-5659-02 | 49 | 74.01 | 3626.49 | O
M1-02 | 20 | SO | 483518 | 2 | 1 | C10758 | BEST WAY | N45 | B14 | B | EA | MRO | 01 | 2021-06-08 | 2021-09-17 | AC-1584-B | 27 | 111.02 | 2997.54 | O
M1-02 | 30 | SO | 481735 | 4 | 2 | C10940 | LTL | 2%10N30 | B22 | B | EA | AERO | 01 | 2021-12-04 | 2022-04-10 | AC-6988-03 | 16 | 79.55 | 1272.8 | O
M1-02 | 20 | BL | 481615 | 5 | 2 | C10950 | FDX 2D | N60 | B22 | E | EA | OEM | 02 | 2022-03-18 | 2022-04-23 | AC-9582-10 | 47 | 105.86 | 4975.42 | O
M1-02 | 20 | SO | 485107 | 8 | 0 | C10560 | BEST WAY | N60 | B07 | A | EA | MRO | 02 | 2021-11-26 | 2022-04-01 | AC-9295-03 | 87 | 159.56 | 13881.72 | O
M1-02 | 30 | SO | 482922 | 9 | 2 | C10695 | BEST WAY | 2%10N30 | B22 | A | EA | AERO | 01 | 2022-01-06 | 2022-05-07 | AC-7613-10 | 6 | 157.45 | 944.7 | O
M1-02 | 20 | BL | 484071 | 1 | 2 | C10824 | UPS GND | 2%10N30 | B14 | E | EA | OEM | 01 | 2022-04-01 | 2022-04-30 | AC-2467-A | 16 | 73.5 | 1176 | O
M1-02 | 30 | BL | 488625 | 9 | 1 | C10817 | FDX 2D | N30 | B11 | A | EA | DEF | 05 | 2022-01-26 | 2022-02-28 | AC-8328-B | 44 | 82.7 | 3638.8 | P
M1-02 | 30 | SO | 480764 | 7 | 3 | C10560 | LTL | N45 | B14 | A | EA | OEM | 01 | 2022-04-06 | 2022-05-18 | AC-2970-01 | 16 | 142.14 | 2274.24 | O
M1-02 | 20 | BL | 489416 | 1 | 1 | C10273 | BEST WAY | N45 | B22 | E | EA | MRO | 05 | 2021-12-31 | 2022-03-15 | AC-3584-05 | 21 | 177.07 | 3718.47 | P
M1-02 | 30 | SO | 485235 | 6 | 3 | C10589 | UPS GND | 2%10N30 | B22 | NC | EA | OEM | 01 | 2022-01-05 | 2022-04-26 | AC-8566-B | 72 | 129.79 | 9344.88 | O
M1-02 | 20 | BL | 488953 | 5 | 0 | C10973 | LTL | N30 | B11 | NC | EA | DEF | 01 | 2021-11-26 | 2022-03-30 | AC-5805-10 | 6 | 103.21 | 619.26 | P
M1-02 | 20 | BL | 484565 | 4 | 3 | C10170 | FDX 2D | N45 | B07 | B | EA | DEF | 02 | 2022-05-04 | 2022-06-09 | AC-4935-10 | 72 | 72.64 | 5230.08 | O
M1-02 | 20 | SO | 487148 | 4 | 3 | C10806 | FDX 2D | N30 | B22 | D | EA | DEF | 02 | 2021-11-09 | 2022-03-28 | AC-8955-02 | 49 | 64.86 | 3178.14 | O
M1-02 | 30 | SO | 488399 | 1 | 1 | C10786 | FDX 2D | N60 | B11 | A | EA | AERO | 02 | 2022-02-24 | 2022-05-08 | AC-9332-01 | 15 | 97.42 | 1461.3 | P
M1-02 | 20 | SO | 484472 | 2 | 0 | C10377 | LTL | N60 | B11 | NC | EA | AERO | 01 | 2022-02-03 | 2022-03-24 | AC-2456-03 | 64 | 129.82 | 8308.48 | O
M1-02 | 30 | BL | 488181 | 7 | 0 | C10824 | FDX 2D | 2%10N30 | B14 | A | EA | AERO | 01 | 2022-03-07 | 2022-05-14 | AC-1084-B | 24 | 63.33 | 1519.92 | P
M1-02 | 30 | SO | 485884 | 5 | 2 | C10544 | UPS GND | 2%10N30 | B14 | NC | EA | MRO | 02 | 2021-12-16 | 2022-04-06 | AC-3357-05 | 29 | 63.34 | 1836.86 | O
M1-02 | 30 | SO | 482107 | 8 | 0 | C10186 | UPS GND | N45 | B22 | D | EA | AERO | 02 | 2022-01-13 | 2022-03-29 | AC-2723-03 | 32 | 73.04 | 2337.28 | O
M1-02 | 30 | BL | 483214 | 9 | 3 | C10321 | UPS GND | N60 | B11 | B | EA | OEM | 01 | 2022-01-18 | 2022-04-02 | AC-3758-02 | 46 | 59.58 | 2740.68 | O
M1-02 | 20 | SO | 486404 | 2 | 3 | C10752 | LTL | N45 | B11 | NC | EA | OEM | 05 | 2022-03-15 | 2022-06-02 | AC-9278-01 | 66 | 47.3 | 3121.8 | O
M1-02 | 20 | SO | 480317 | 7 | 3 | C10589 | FDX 2D | N45 | B11 | B | EA | MRO | 05 | 2022-03-23 | 2022-05-28 | AC-2958-B | 81 | 114.76 | 9295.56 | O
M1-02 | 20 | SO | 480279 | 4 | 2 | C10186 | LTL | N45 | B07 | B | EA | AERO | 02 | 2022-02-03 | 2022-04-11 | AC-9090-B | 10 | 60.23 | 602.3 | O
M1-02 | 20 | SO | 487770 | 2 | 1 | C10966 | BEST WAY | N60 | B22 | E | EA | AERO | 01 | 2021-11-11 | 2022-02-11 | AC-3359-A | 21 | 41.73 | 876.33 | P
M1-02 | 20 | BL | 488521 | 2 | 0 | C10519 | LTL | N30 | B11 | E | EA | DEF | 01 | 2022-01-27 | 2022-04-10 | AC-9688-B | 19 | 111.67 | 2121.73 | P
M1-02 | 20 | SO | 489636 | 12 | 0 | C10238 | BEST WAY | N30 | B22 | D | EA | MRO | 05 | 2022-03-30 | 2022-05-13 | AC-1459-B | 17 | 87.07 | 1480.19 | P
M1-02 | 30 | SO | 486599 | 7 | 0 | C10860 | FDX 2D | N60 | B14 | E | EA | MRO | 02 | 2021-12-23 | 2022-04-25 | AC-6768-05 | 65 | 51.06 | 3318.9 | O
M1-02 | 20 | SO | 480826 | 2 | 0 | C10787 | CUST PU | N30 | B14 | D | EA | OEM | 02 | 2022-04-01 | 2022-04-30 | AC-8538-10 | 56 | 81.35 | 4555.6 | O
M1-02 | 30 | SO | 489660 | 9 | 0 | C10806 | UPS GND | N45 | B22 | B | EA | MRO | 05 | 2022-03-18 | 2022-05-21 | AC-5424-05 | 19 | 94.38 | 1793.22 | P
M1-02 | 20 | SO | 481955 | 1 | 2 | C10664 | BEST WAY | N60 | B07 | A | EA | MRO | 02 | 2021-11-22 | 2022-01-28 | AC-6758-10 | 47 | 142.13 | 6680.11 | O
M1-02 | 20 | SO | 487292 | 2 | 3 | C10222 | LTL | N45 | B14 | E | EA | AERO | 02 | 2021-12-07 | 2022-04-09 | AC-1566-10 | 32 | 139.1 | 4451.2 | O
M1-02 | 30 | SO | 484231 | 4 | 2 | C10331 | BEST WAY | N60 | B14 | NC | EA | MRO | 05 | 2022-02-26 | 2022-05-31 | AC-7307-03 | 80 | 46.7 | 3736 | O
M1-02 | 30 | BL | 487913 | 12 | 0 | C10706 | BEST WAY | N60 | B07 | NC | EA | OEM | 01 | 2021-12-24 | 2022-04-15 | AC-2870-A | 54 | 48.31 | 2608.74 | P
M1-02 | 30 | SO | 484448 | 2 | 3 | C10256 | FDX 2D | N30 | B11 | A | EA | MRO | 02 | 2021-12-19 | 2022-04-18 | AC-7315-05 | 29 | 134.46 | 3899.34 | O
M1-02 | 20 | SO | 482557 | 4 | 0 | C10273 | LTL | N30 | B07 | E | EA | DEF | 01 | 2022-01-29 | 2022-05-21 | AC-2651-03 | 85 | 91.21 | 7752.85 | O
M1-02 | 30 | SO | 482282 | 7 | 1 | C10973 | UPS GND | 2%10N30 | B07 | NC | EA | AERO | 01 | 2022-02-07 | 2022-04-28 | AC-4736-B | 99 | 120.76 | 11955.24 | O
M1-02 | 20 | BL | 483379 | 3 | 0 | C10332 | LTL | 2%10N30 | B11 | B | EA | AERO | 05 | 2021-09-15 | 2021-10-16 | AC-2929-10 | 14 | 168.68 | 2361.52 | O
M1-02 | 20 | SO | 485648 | 11 | 1 | C10787 | LTL | N30 | B22 | A | EA | AERO | 05 | 2022-02-19 | 2022-05-10 | AC-4737-01 | 90 | 125.52 | 11296.8 | O
M1-02 | 30 | SO | 485686 | 9 | 2 | C10280 | LTL | N60 | B07 | NC | EA | AERO | 01 | 2022-03-18 | 2022-04-15 | AC-7038-02 | 94 | 157.72 | 14825.68 | O
M1-02 | 30 | SO | 484785 | 7 | 1 | C10936 | BEST WAY | N45 | B14 | NC | EA | DEF | 01 | 2022-03-08 | 2022-04-10 | AC-8974-05 | 60 | 120.5 | 7230 | O
M1-02 | 30 | SO | 482645 | 3 | 1 | C10756 | UPS GND | N60 | B07 | C | EA | MRO | 05 | 2022-04-21 | 2022-05-21 | AC-5472-02 | 46 | 172.97 | 7956.62 | O
M1-02 | 20 | SO | 481818 | 12 | 1 | C10170 | CUST PU | N60 | B11 | C | EA | MRO | 02 | 2021-10-29 | 2022-01-10 | AC-6682-01 | 94 | 102.95 | 9677.3 | O
M1-02 | 20 | SO | 484342 | 7 | 2 | C10787 | BEST WAY | N45 | B11 | B | EA | AERO | 01 | 2021-10-20 | 2022-01-11 | AC-8608-B | 43 | 129.91 | 5586.13 | O
M1-02 | 20 | SO | 480015 | 7 | 1 | C10211 | BEST WAY | N45 | B07 | C | EA | MRO | 05 | 2021-11-20 | 2022-03-26 | AC-6281-10 | 49 | 97.8 | 4792.2 | O
M1-02 | 20 | SO | 485748 | 7 | 3 | C10461 | BEST WAY | N60 | B11 | E | EA | OEM | 01 | 2022-03-15 | 2022-04-13 | AC-2028-B | 90 | 67.44 | 6069.6 | O
M1-02 | 30 | SO | 487578 | 4 | 3 | C10951 | FDX 2D | 2%10N30 | B11 | D | EA | MRO | 02 | 2021-05-02 | 2021-06-24 | AC-6702-02 | 36 | 178.49 | 6425.64 | P
M1-02 | 30 | SO | 482418 | 4 | 3 | C10327 | LTL | 2%10N30 | B07 | E | EA | OEM | 02 | 2021-09-11 | 2021-12-14 | AC-5371-10 | 88 | 45.58 | 4011.04 | O
M1-02 | 30 | SO | 488806 | 11 | 0 | C10860 | UPS GND | N60 | B11 | D | EA | DEF | 05 | 2021-12-31 | 2022-04-06 | AC-4980-01 | 55 | 69.16 | 3803.8 | P
M1-02 | 30 | SO | 489146 | 6 | 0 | C10264 | CUST PU | N45 | B14 | D | EA | OEM | 05 | 2022-02-23 | 2022-05-18 | AC-4109-05 | 6 | 110.5 | 663 | P
M1-02 | 20 | SO | 480288 | 4 | 2 | C10211 | BEST WAY | N45 | B07 | C | EA | AERO | 05 | 2021-11-04 | 2022-03-24 | AC-4104-05 | 46 | 170.25 | 7831.5 | O
M1-02 | 30 | SO | 486629 | 11 | 3 | C10664 | CUST PU | N30 | B07 | D | EA | MRO | 05 | 2022-02-26 | 2022-05-17 | AC-3127-02 | 80 | 108.16 | 8652.8 | O
M1-02 | 30 | SO | 482088 | 7 | 1 | C10695 | FDX 2D | N45 | B14 | B | EA | DEF | 02 | 2022-02-22 | 2022-05-18 | AC-1599-03 | 8 | 79.11 | 632.88 | O
M1-02 | 20 | SO | 486160 | 6 | 0 | C10305 | UPS GND | 2%10N30 | B22 | C | EA | AERO | 01 | 2022-03-14 | 2022-05-13 | AC-2349-05 | 21 | 165.59 | 3477.39 | O
M1-02 | 30 | SO | 487378 | 8 | 0 | C10327 | FDX 2D | 2%10N30 | B14 | C | EA | OEM | 01 | 2021-04-03 | 2021-06-15 | AC-5486-03 | 12 | 133.3 | 1599.6 | P
M1-02 | 20 | SO | 484364 | 4 | 3 | C10664 | FDX 2D | N45 | B14 | A | EA | MRO | 05 | 2022-01-30 | 2022-04-13 | AC-2073-01 | 48 | 161.16 | 7735.68 | O
M1-02 | 30 | SO | 480403 | 12 | 3 | C10746 | FDX 2D | N30 | B22 | C | EA | OEM | 01 | 2022-01-04 | 2022-03-18 | AC-3317-B | 37 | 78.75 | 2913.75 | O
M1-02 | 20 | SO | 486374 | 6 | 1 | C10222 | CUST PU | N60 | B07 | D | EA | OEM | 01 | 2022-01-27 | 2022-03-17 | AC-7788-A | 5 | 70.07 | 350.35 | O
M1-02 | 30 | SO | 481365 | 10 | 2 | C10568 | FDX 2D | N45 | B14 | B | EA | DEF | 05 | 2022-02-28 | 2022-04-12 | AC-1883-02 | 54 | 83.14 | 4489.56 | O
M1-02 | 20 | SO | 489069 | 1 | 0 | C10664 | UPS GND | 2%10N30 | B11 | A | EA | DEF | 02 | 2022-01-20 | 2022-05-09 | AC-6501-05 | 6 | 76.61 | 459.66 | P
M1-02 | 20 | SO | 484000 | 8 | 1 | C10758 | FDX 2D | N45 | B07 | B | EA | OEM | 01 | 2022-02-04 | 2022-03-26 | AC-8595-05 | 85 | 155.92 | 13253.2 | O
M1-02 | 20 | SO | 489268 | 10 | 0 | C10830 | FDX 2D | N30 | B11 | D | EA | DEF | 05 | 2021-09-25 | 2022-01-29 | AC-5092-02 | 29 | 128.56 | 3728.24 | P
M1-02 | 20 | SO | 487675 | 10 | 3 | C10251 | UPS GND | 2%10N30 | B11 | A | EA | AERO | 02 | 2021-07-29 | 2021-09-16 | AC-1084-B | 19 | 81.93 | 1556.67 | P
M1-02 | 20 | SO | 487967 | 1 | 1 | C10824 | BEST WAY | 2%10N30 | B22 | E | EA | AERO | 02 | 2021-07-18 | 2021-09-17 | AC-9025-05 | 46 | 95.52 | 4393.92 | P
M1-02 | 30 | BL | 484239 | 5 | 0 | C10256 | UPS GND | N45 | B11 | D | EA | MRO | 02 | 2021-11-01 | 2021-12-02 | AC-2967-A | 74 | 169.64 | 12553.36 | O
M1-02 | 30 | SO | 480290 | 12 | 1 | C10706 | FDX 2D | N45 | B14 | B | EA | OEM | 05 | 2022-02-12 | 2022-05-27 | AC-5036-01 | 58 | 81.99 | 4755.42 | O
M1-02 | 30 | BL | 489587 | 10 | 2 | C10900 | FDX 2D | 2%10N30 | B11 | C | EA | OEM | 01 | 2022-03-30 | 2022-06-08 | AC-4109-05 | 19 | 117.1 | 2224.9 | P
M1-02 | 30 | SO | 481709 | 1 | 2 | C10455 | LTL | N45 | B07 | A | EA | OEM | 05 | 2022-03-02 | 2022-05-22 | AC-1144-10 | 37 | 171.11 | 6331.07 | O
M1-02 | 30 | SO | 488839 | 5 | 2 | C10316 | LTL | N30 | B07 | E | EA | OEM | 02 | 2021-02-28 | 2021-07-06 | AC-1293-A | 46 | 122.34 | 5627.64 | P
M1-02 | 30 | SO | 487900 | 9 | 3 | C10852 | UPS GND | 2%10N30 | B14 | E | EA | MRO | 01 | 2022-04-13 | 2022-05-29 | AC-7794-A | 20 | 158.47 | 3169.4 | P
M1-02 | 20 | SO | 486166 | 8 | 3 | C10170 | FDX 2D | N60 | B22 | A | EA | AERO | 05 | 2022-01-31 | 2022-03-29 | AC-8974-05 | 49 | 54.63 | 2676.87 | O
M1-02 | 20 | BL | 483319 | 10 | 1 | C10170 | UPS GND | N30 | B22 | C | EA | DEF | 02 | 2021-10-10 | 2021-11-20 | AC-1448-02 | 60 | 107.54 | 6452.4 | O
M1-02 | 30 | SO | 488841 | 7 | 1 | C10264 | FDX 2D | N45 | B11 | E | EA | DEF | 01 | 2021-09-20 | 2022-02-02 | AC-3471-10 | 59 | 41.74 | 2462.66 | P
M1-02 | 20 | SO | 483675 | 6 | 3 | C10951 | UPS GND | N60 | B11 | D | EA | AERO | 01 | 2022-03-14 | 2022-05-18 | AC-6050-02 | 58 | 60.15 | 3488.7 | O
M1-02 | 30 | SO | 484377 | 5 | 3 | C10695 | CUST PU | 2%10N30 | B07 | E | EA | MRO | 02 | 2021-11-19 | 2022-03-29 | AC-4424-10 | 70 | 126.04 | 8822.8 | O
M1-02 | 30 | SO | 482741 | 9 | 3 | C10756 | FDX 2D | N60 | B07 | E | EA | MRO | 05 | 2021-12-10 | 2022-04-17 | AC-3423-05 | 66 | 121.15 | 7995.9 | O
M1-02 | 20 | BL | 488730 | 1 | 0 | C10852 | LTL | N30 | B14 | D | EA | DEF | 05 | 2021-09-20 | 2021-11-21 | AC-9025-05 | 51 | 106.1 | 5411.1 | P
M1-02 | 30 | SO | 486141 | 8 | 2 | C10568 | BEST WAY | N60 | B14 | NC | EA | DEF | 02 | 2022-03-02 | 2022-06-07 | AC-9648-02 | 82 | 135.8 | 11135.6 | O
M1-02 | 30 | SO | 482439 | 8 | 2 | C10249 | FDX 2D | N60 | B07 | C | EA | DEF | 02 | 2022-03-14 | 2022-04-17 | AC-9652-03 | 83 | 47.71 | 3959.93 | O
M1-02 | 30 | BL | 488008 | 1 | 3 | C10420 | BEST WAY | N30 | B22 | D | EA | MRO | 05 | 2021-07-03 | 2021-09-15 | AC-3696-02 | 58 | 70.42 | 4084.36 | P
M1-02 | 30 | BL | 485431 | 9 | 2 | C10950 | FDX 2D | N30 | B07 | D | EA | DEF | 01 | 2022-01-22 | 2022-04-15 | AC-6643-B | 36 | 123.31 | 4439.16 | O
M1-02 | 30 | SO | 489349 | 11 | 2 | C10273 | FDX 2D | N60 | B14 | A | EA | OEM | 05 | 2021-12-04 | 2022-04-02 | AC-4709-01 | 25 | 66.82 | 1670.5 | P
M1-02 | 30 | SO | 482362 | 9 | 3 | C10256 | FDX 2D | 2%10N30 | B11 | NC | EA | OEM | 02 | 2022-03-22 | 2022-05-10 | AC-1409-05 | 44 | 128.25 | 5643 | O
M1-02 | 30 | SO | 483074 | 1 | 1 | C10525 | LTL | N30 | B11 | E | EA | MRO | 01 | 2022-02-25 | 2022-05-23 | AC-7989-02 | 32 | 111.58 | 3570.56 | O
M1-02 | 30 | SO | 480978 | 11 | 2 | C10936 | BEST WAY | 2%10N30 | B07 | A | EA | AERO | 05 | 2021-08-24 | 2021-12-17 | AC-2677-01 | 32 | 104.76 | 3352.32 | O
M1-02 | 20 | SO | 486193 | 1 | 0 | C10331 | LTL | N45 | B07 | A | EA | DEF | 02 | 2022-01-05 | 2022-03-15 | AC-9541-B | 86 | 98.44 | 8465.84 | O
M1-02 | 20 | SO | 483896 | 9 | 2 | C10251 | LTL | N60 | B22 | NC | EA | OEM | 01 | 2022-04-01 | 2022-04-30 | AC-2613-10 | 68 | 103.07 | 7008.76 | O
M1-02 | 30 | SO | 481654 | 6 | 0 | C10973 | UPS GND | 2%10N30 | B14 | A | EA | MRO | 02 | 2022-02-22 | 2022-05-15 | AC-9159-A | 84 | 106.5 | 8946 | O
M1-02 | 30 | SO | 489444 | 5 | 0 | C10824 | LTL | 2%10N30 | B14 | A | EA | MRO | 01 | 2022-01-09 | 2022-04-18 | AC-1060-10 | 39 | 41.38 | 1613.82 | P
M1-02 | 30 | SO | 483359 | 9 | 2 | C10252 | BEST WAY | 2%10N30 | B11 | A | EA | DEF | 05 | 2022-03-30 | 2022-05-15 | AC-4737-01 | 69 | 133.46 | 9208.74 | O
M1-02 | 30 | BL | 486729 | 8 | 3 | C10281 | FDX 2D | N30 | B11 | A | EA | MRO | 01 | 2022-02-01 | 2022-04-04 | AC-1381-05 | 35 | 113.45 | 3970.75 | O
M1-02 | 30 | BL | 484105 | 12 | 0 | C10456 | UPS GND | N60 | B11 | D | EA | OEM | 02 | 2022-03-06 | 2022-05-31 | AC-2237-A | 70 | 138 | 9660 | O
M1-02 | 20 | BL | 483559 | 10 | 2 | C10806 | LTL | N30 | B07 | B | EA | DEF | 01 | 2021-08-20 | 2021-12-19 | AC-5198-03 | 84 | 134.04 | 11259.36 | O
M1-02 | 20 | SO | 485352 | 1 | 0 | C10568 | BEST WAY | N45 | B14 | C | EA | OEM | 01 | 2022-03-23 | 2022-06-01 | AC-1568-A | 76 | 102.76 | 7809.76 | O
M1-02 | 30 | SO | 486228 | 8 | 3 | C10746 | UPS GND | 2%10N30 | B14 | C | EA | MRO | 02 | 2022-01-19 | 2022-04-18 | AC-8073-10 | 47 | 148.79 | 6993.13 | O
M1-02 | 30 | SO | 489334 | 9 | 3 | C10238 | CUST PU | N60 | B11 | A | EA | MRO | 02 | 2022-04-25 | 2022-06-07 | AC-4109-05 | 4 | 99.17 | 396.68 | P
M1-02 | 20 | SO | 487480 | 7 | 3 | C10752 | UPS GND | 2%10N30 | B11 | E | EA | AERO | 01 | 2022-03-04 | 2022-05-04 | AC-1601-05 | 57 | 155.8 | 8880.6 | P
M1-02 | 20 | BL | 485288 | 10 | 3 | C10526 | BEST WAY | N60 | B22 | C | EA | AERO | 02 | 2021-12-25 | 2022-04-18 | AC-7122-03 | 69 | 64.99 | 4484.31 | O
M1-02 | 30 | BL | 481494 | 4 | 3 | C10589 | LTL | N60 | B14 | B | EA | AERO | 01 | 2022-03-04 | 2022-05-16 | AC-6074-10 | 6 | 116.36 | 698.16 | O
M1-02 | 20 | SO | 484423 | 1 | 3 | C10222 | CUST PU | 2%10N30 | B11 | D | EA | AERO | 02 | 2021-03-06 | 2021-05-29 | AC-5248-03 | 29 | 153.87 | 4462.23 | O
M1-02 | 30 | SO | 480712 | 11 | 0 | C10211 | UPS GND | N30 | B11 | E | EA | OEM | 05 | 2021-12-17 | 2022-04-09 | AC-2755-05 | 6 | 141.35 | 848.1 | O
M1-02 | 30 | SO | 485131 | 1 | 2 | C10498 | LTL | N30 | B07 | E | EA | OEM | 01 | 2021-03-28 | 2021-06-30 | AC-5074-03 | 58 | 79.75 | 4625.5 | O
M1-02 | 20 | SO | 482696 | 6 | 3 | C10560 | LTL | N45 | B14 | E | EA | OEM | 02 | 2022-01-11 | 2022-03-28 | AC-8427-05 | 80 | 166.62 | 13329.6 | O
M1-02 | 20 | BL | 486923 | 5 | 2 | C10456 | LTL | N30 | B14 | D | EA | DEF | 02 | 2021-04-02 | 2021-07-22 | AC-4132-01 | 86 | 127.81 | 10991.66 | O
M1-02 | 20 | BL | 484778 | 4 | 3 | C10170 | CUST PU | N60 | B14 | D | EA | OEM | 01 | 2022-01-03 | 2022-04-14 | AC-4509-B | 27 | 159.63 | 4310.01 | O
M1-02 | 30 | BL | 486087 | 5 | 0 | C10222 | LTL | 2%10N30 | B07 | A | EA | DEF | 01 | 2022-01-19 | 2022-04-23 | AC-7258-B | 78 | 73.46 | 5729.88 | O
M1-02 | 20 | SO | 480543 | 11 | 2 | C10211 | FDX 2D | N45 | B11 | A | EA | DEF | 05 | 2021-04-08 | 2021-06-17 | AC-6076-02 | 96 | 171.2 | 16435.2 | O
M1-02 | 30 | SO | 487109 | 9 | 2 | C10786 | CUST PU | 2%10N30 | B22 | D | EA | AERO | 02 | 2022-01-06 | 2022-03-19 | AC-4033-01 | 67 | 132.25 | 8860.75 | O
M1-02 | 20 | SO | 485739 | 7 | 3 | C10331 | FDX 2D | N60 | B07 | C | EA | DEF | 02 | 2022-02-12 | 2022-04-04 | AC-2371-A | 68 | 107.67 | 7321.56 | O
M1-02 | 30 | SO | 488532 | 9 | 0 | C10936 | CUST PU | N30 | B07 | A | EA | AERO | 01 | 2021-12-02 | 2022-03-14 | AC-2849-B | 17 | 94.35 | 1603.95 | P
M1-02 | 20 | BL | 487542 | 5 | 1 | C10281 | BEST WAY | N30 | B07 | B | EA | OEM | 02 | 2021-12-27 | 2022-03-30 | AC-8194-03 | 22 | 167.84 | 3692.48 | P
M1-02 | 20 | BL | 482210 | 1 | 2 | C10350 | CUST PU | N60 | B14 | NC | EA | MRO | 05 | 2022-03-18 | 2022-05-27 | AC-5825-B | 75 | 96.6 | 7245 | O
M1-02 | 20 | SO | 483123 | 1 | 1 | C10966 | BEST WAY | 2%10N30 | B22 | E | EA | OEM | 02 | 2021-11-15 | 2022-03-28 | AC-3984-10 | 59 | 67.12 | 3960.08 | O
M1-02 | 20 | SO | 481473 | 8 | 0 | C10746 | UPS GND | N30 | B11 | B | EA | MRO | 01 | 2022-01-23 | 2022-05-22 | AC-7083-B | 38 | 161.73 | 6145.74 | O
M1-02 | 30 | BL | 480950 | 1 | 0 | C10936 | CUST PU | N60 | B07 | NC | EA | MRO | 05 | 2021-09-22 | 2021-11-08 | AC-3649-B | 16 | 104.63 | 1674.08 | O
M1-02 | 30 | SO | 485047 | 7 | 2 | C10940 | CUST PU | N30 | B14 | A | EA | OEM | 02 | 2022-02-20 | 2022-05-07 | AC-9389-03 | 72 | 76.47 | 5505.84 | O
M1-02 | 30 | SO | 483229 | 4 | 0 | C10787 | FDX 2D | N45 | B07 | D | EA | MRO | 01 | 2022-03-03 | 2022-05-28 | AC-3293-01 | 63 | 172.12 | 10843.56 | O
M1-02 | 30 | BL | 481902 | 1 | 0 | C10186 | CUST PU | 2%10N30 | B07 | B | EA | AERO | 05 | 2022-03-29 | 2022-05-23 | AC-3722-05 | 61 | 150.92 | 9206.12 | O
M1-02 | 20 | BL | 482508 | 9 | 2 | C10461 | LTL | N45 | B11 | E | EA | MRO | 01 | 2021-09-11 | 2021-12-28 | AC-2574-A | 55 | 166.87 | 9177.85 | O
M1-02 | 20 | SO | 485361 | 6 | 2 | C10331 | LTL | 2%10N30 | B14 | A | EA | OEM | 05 | 2022-03-10 | 2022-05-16 | AC-9578-B | 35 | 56.92 | 1992.2 | O
M1-02 | 30 | SO | 486179 | 4 | 1 | C10664 | CUST PU | N30 | B14 | NC | EA | MRO | 05 | 2022-03-12 | 2022-04-29 | AC-9245-A | 27 | 121.29 | 3274.83 | O
M1-02 | 30 | SO | 480906 | 2 | 3 | C10238 | LTL | N60 | B07 | B | EA | AERO | 01 | 2021-09-01 | 2022-01-10 | AC-6332-B | 72 | 124.52 | 8965.44 | O
M1-02 | 20 | BL | 482998 | 6 | 3 | C10560 | FDX 2D | N60 | B07 | E | EA | AERO | 02 | 2022-02-09 | 2022-03-19 | AC-3656-02 | 50 | 86.9 | 4345 | O
M1-02 | 20 | SO | 483116 | 5 | 0 | C10238 | LTL | 2%10N30 | B14 | C | EA | OEM | 02 | 2021-11-11 | 2022-01-23 | AC-4358-02 | 23 | 130.73 | 3006.79 | O
M1-02 | 30 | BL | 482399 | 12 | 1 | C10280 | BEST WAY | 2%10N30 | B11 | E | EA | AERO | 05 | 2022-03-27 | 2022-05-12 | AC-3293-01 | 91 | 51.4 | 4677.4 | O
M1-02 | 20 | SO | 481999 | 11 | 3 | C10332 | LTL | 2%10N30 | B22 | B | EA | AERO | 01 | 2022-01-19 | 2022-05-19 | AC-3924-B | 92 | 49.36 | 4541.12 | O
M1-02 | 30 | SO | 489532 | 1 | 3 | C10951 | FDX 2D | N60 | B07 | NC | EA | OEM | 05 | 2021-12-28 | 2022-03-24 | AC-7894-02 | 22 | 288.29 | 6342.38 | P
M1-02 | 20 | BL | 485928 | 11 | 2 | C10211 | CUST PU | N60 | B22 | E | EA | AERO | 05 | 2021-09-28 | 2021-11-20 | AC-6660-03 | 84 | 113.02 | 9493.68 | O
M1-02 | 30 | SO | 485218 | 10 | 1 | C10264 | CUST PU | N60 | B22 | D | EA | OEM | 02 | 2022-03-27 | 2022-05-10 | AC-7083-B | 79 | 137.72 | 10879.88 | O
M1-02 | 30 | SO | 487778 | 8 | 1 | C10222 | BEST WAY | N30 | B14 | D | EA | OEM | 02 | 2021-12-08 | 2022-01-12 | AC-3675-B | 19 | 54.08 | 1027.52 | P
M1-02 | 20 | SO | 485775 | 9 | 0 | C10706 | LTL | 2%10N30 | B11 | D | EA | AERO | 05 | 2022-02-17 | 2022-06-10 | AC-4924-03 | 24 | 114.59 | 2750.16 | O
M1-02 | 30 | SO | 488329 | 9 | 1 | C10170 | FDX 2D | N60 | B22 | D | EA | DEF | 02 | 2021-03-21 | 2021-06-25 | AC-7457-B | 25 | 96.81 | 2420.25 | P
M1-02 | 20 | SO | 483133 | 8 | 3 | C10936 | CUST PU | N60 | B14 | NC | EA | MRO | 01 | 2021-12-29 | 2022-05-07 | AC-5010-A | 55 | 94.78 | 5212.9 | O
M1-02 | 20 | SO | 484007 | 12 | 0 | C10951 | FDX 2D | N45 | B07 | NC | EA | AERO | 01 | 2022-01-23 | 2022-03-19 | AC-4014-01 | 82 | 88.38 | 7247.16 | O
M1-02 | 30 | BL | 489677 | 4 | 0 | C10973 | BEST WAY | N45 | B07 | D | EA | AERO | 05 | 2021-12-08 | 2022-04-06 | AC-1392-B | 22 | 113.35 | 2493.7 | P
M1-02 | 30 | SO | 482588 | 10 | 3 | C10256 | FDX 2D | N45 | B14 | NC | EA | DEF | 01 | 2021-11-26 | 2022-03-28 | AC-8793-A | 25 | 162.55 | 4063.75 | O
M1-02 | 20 | BL | 486794 | 1 | 1 | C10305 | UPS GND | N45 | B14 | D | EA | MRO | 01 | 2022-01-11 | 2022-04-22 | AC-4101-02 | 77 | 143.98 | 11086.46 | O
M1-02 | 20 | BL | 482488 | 9 | 1 | C10461 | LTL | N30 | B07 | B | EA | MRO | 02 | 2021-01-23 | 2021-05-31 | AC-7848-B | 66 | 158.78 | 10479.48 | O
M1-02 | 30 | BL | 484048 | 7 | 0 | C10951 | CUST PU | 2%10N30 | B11 | E | EA | MRO | 02 | 2022-04-25 | 2022-05-23 | AC-3764-01 | 43 | 61.38 | 2639.34 | O
M1-02 | 20 | SO | 485632 | 9 | 2 | C10695 | BEST WAY | N45 | B11 | C | EA | AERO | 01 | 2022-02-19 | 2022-06-06 | AC-6484-05 | 36 | 91.32 | 3287.52 | O
M1-02 | 20 | SO | 485074 | 4 | 3 | C10786 | LTL | N30 | B14 | C | EA | OEM | 01 | 2021-08-25 | 2021-10-18 | AC-6484-05 | 92 | 96.03 | 8834.76 | O
M1-02 | 20 | BL | 483669 | 5 | 1 | C10824 | FDX 2D | N30 | B22 | A | EA | DEF | 01 | 2021-10-01 | 2021-12-25 | AC-1570-02 | 88 | 65.59 | 5771.92 | O
M1-02 | 20 | SO | 480660 | 10 | 1 | C10951 | LTL | N45 | B07 | B | EA | AERO | 01 | 2021-02-24 | 2021-06-16 | AC-7720-10 | 63 | 71.98 | 4534.74 | O
M1-02 | 30 | BL | 487028 | 8 | 3 | C10316 | CUST PU | N45 | B14 | C | EA | AERO | 05 | 2021-04-08 | 2021-07-26 | AC-8214-03 | 17 | 112.24 | 1908.08 | O
M1-02 | 20 | SO | 489690 | 2 | 3 | C10455 | UPS GND | N45 | B14 | NC | EA | MRO | 02 | 2022-02-20 | 2022-06-09 | AC-5424-05 | 33 | 41.62 | 1373.46 | P
M1-02 | 20 | SO | 488198 | 1 | 1 | C10456 | FDX 2D | N30 | B22 | B | EA | AERO | 01 | 2021-03-03 | 2021-07-04 | AC-3912-03 | 42 | 158.52 | 6657.84 | P
M1-02 | 20 | SO | 480633 | 3 | 2 | C10786 | UPS GND | N30 | B11 | NC | EA | OEM | 01 | 2022-01-05 | 2022-05-24 | AC-6612-B | 43 | 165.43 | 7113.49 | O
M1-02 | 30 | BL | 486968 | 5 | 0 | C10860 | UPS GND | N30 | B07 | NC | EA | MRO | 01 | 2022-02-25 | 2022-06-07 | AC-3181-02 | 68 | 128.43 | 8733.24 | O
M1-02 | 30 | SO | 482021 | 4 | 1 | C10332 | UPS GND | N30 | B07 | A | EA | MRO | 05 | 2021-05-05 | 2021-07-08 | AC-7817-A | 37 | 44.35 | 1640.95 | O
M1-02 | 30 | BL | 482075 | 4 | 0 | C10519 | LTL | 2%10N30 | B07 | C | EA | OEM | 05 | 2022-02-09 | 2022-05-15 | AC-3239-01 | 58 | 122.75 | 7119.5 | O
M1-02 | 20 | SO | 480417 | 4 | 0 | C10436 | FDX 2D | 2%10N30 | B11 | D | EA | AERO | 01 | 2022-03-09 | 2022-06-06 | AC-7648-01 | 41 | 121.07 | 4963.87 | O
M1-02 | 20 | SO | 489447 | 8 | 1 | C10951 | BEST WAY | N45 | B07 | D | EA | OEM | 01 | 2022-01-08 | 2022-03-27 | AC-2726-B | 21 | 32.72 | 687.12 | P
M1-02 | 30 | BL | 484529 | 6 | 1 | C10186 | BEST WAY | N60 | B14 | A | EA | DEF | 01 | 2022-03-11 | 2022-05-02 | AC-4029-A | 46 | 103.83 | 4776.18 | O
M1-02 | 30 | SO | 485026 | 7 | 3 | C10758 | LTL | N45 | B11 | E | EA | AERO | 02 | 2022-04-10 | 2022-06-04 | AC-1210-B | 72 | 74.67 | 5376.24 | O
M1-02 | 20 | SO | 480539 | 1 | 1 | C10436 | UPS GND | N60 | B14 | B | EA | MRO | 05 | 2022-02-12 | 2022-04-22 | AC-2650-03 | 70 | 146.54 | 10257.8 | O
M1-02 | 30 | SO | 489425 | 7 | 0 | C10436 | LTL | 2%10N30 | B11 | C | EA | AERO | 05 | 2022-01-31 | 2022-05-02 | AC-8653-01 | 27 | 28.3 | 764.1 | P
M1-02 | 30 | SO | 480746 | 3 | 2 | C10170 | CUST PU | N45 | B11 | NC | EA | OEM | 01 | 2021-12-13 | 2022-04-01 | AC-7586-02 | 21 | 152.12 | 3194.52 | O
M1-02 | 20 | SO | 486676 | 2 | 1 | C10519 | BEST WAY | N45 | B11 | E | EA | MRO | 02 | 2022-01-06 | 2022-03-13 | AC-7154-02 | 89 | 133.42 | 11874.38 | O
M1-02 | 30 | SO | 480408 | 6 | 1 | C10950 | UPS GND | 2%10N30 | B11 | C | EA | MRO | 01 | 2022-03-05 | 2022-04-22 | AC-4357-05 | 83 | 86.22 | 7156.26 | O
M1-02 | 30 | SO | 481860 | 10 | 3 | C10350 | UPS GND | N60 | B07 | D | EA | OEM | 02 | 2022-03-16 | 2022-04-18 | AC-4398-03 | 89 | 56.87 | 5061.43 | O
M1-02 | 30 | SO | 484919 | 4 | 1 | C10519 | UPS GND | N30 | B07 | B | EA | DEF | 02 | 2022-04-06 | 2022-05-18 | AC-4045-B | 41 | 84.49 | 3464.09 | O
M1-02 | 30 | SO | 481883 | 4 | 3 | C10824 | UPS GND | N60 | B07 | C | EA | OEM | 01 | 2022-03-23 | 2022-05-07 | AC-2827-02 | 40 | 83.06 | 3322.4 | O
M1-02 | 30 | SO | 483172 | 12 | 1 | C10436 | CUST PU | N30 | B22 | B | EA | AERO | 02 | 2022-02-01 | 2022-04-25 | AC-1574-05 | 64 | 99.91 | 6394.24 | O
M1-02 | 30 | SO | 483684 | 3 | 3 | C10420 | UPS GND | N45 | B14 | E | EA | DEF | 05 | 2021-12-08 | 2022-04-19 | AC-8929-A | 98 | 44.51 | 4361.98 | O
M1-02 | 30 | SO | 486559 | 12 | 0 | C10936 | BEST WAY | 2%10N30 | B22 | NC | EA | MRO | 01 | 2022-02-05 | 2022-03-18 | AC-8793-A | 75 | 161.76 | 12132 | O
M1-02 | 30 | SO | 483387 | 1 | 3 | C10530 | BEST WAY | 2%10N30 | B22 | NC | EA | DEF | 02 | 2021-07-28 | 2021-12-15 | AC-1301-B | 14 | 122.41 | 1713.74 | O
M1-02 | 30 | SO | 486487 | 9 | 3 | C10688 | CUST PU | 2%10N30 | B22 | NC | EA | DEF | 05 | 2022-03-04 | 2022-04-13 | AC-4790-01 | 17 | 151.92 | 2582.64 | O
M1-02 | 20 | SO | 484613 | 7 | 0 | C10264 | FDX 2D | N60 | B11 | A | EA | MRO | 01 | 2022-01-17 | 2022-05-15 | AC-9161-B | 24 | 48.41 | 1161.84 | O
M1-02 | 30 | SO | 488571 | 2 | 3 | C10251 | LTL | N60 | B22 | E | EA | AERO | 01 | 2022-04-07 | 2022-05-19 | AC-7176-02 | 9 | 131.98 | 1187.82 | P
M1-02 | 20 | SO | 484438 | 11 | 1 | C10786 | FDX 2D | N60 | B11 | B | EA | OEM | 02 | 2021-12-16 | 2022-03-24 | AC-9804-05 | 63 | 149.57 | 9422.91 | O
M1-02 | 30 | BL | 481425 | 5 | 1 | C10211 | LTL | N30 | B22 | E | EA | AERO | 01 | 2022-01-14 | 2022-03-29 | AC-1381-05 | 87 | 80.82 | 7031.34 | O
M1-02 | 30 | SO | 481018 | 4 | 3 | C10560 | BEST WAY | N60 | B14 | B | EA | MRO | 05 | 2022-01-24 | 2022-06-10 | AC-6385-10 | 60 | 164.19 | 9851.4 | O
M1-02 | 20 | SO | 488961 | 10 | 2 | C10327 | LTL | N45 | B22 | C | EA | AERO | 01 | 2022-04-01 | 2022-06-04 | AC-4307-01 | 13 | 57.19 | 743.47 | P
M1-02 | 30 | SO | 488542 | 7 | 2 | C10461 | BEST WAY | N60 | B14 | B | EA | DEF | 02 | 2021-07-02 | 2021-08-14 | AC-4082-10 | 33 | 149.85 | 4945.05 | P
M1-02 | 30 | SO | 489085 | 5 | 1 | C10331 | CUST PU | 2%10N30 | B07 | C | EA | DEF | 05 | 2022-03-20 | 2022-06-05 | AC-7811-02 | 23 | 131.82 | 3031.86 | P
M1-02 | 30 | BL | 482536 | 2 | 0 | C10273 | UPS GND | 2%10N30 | B11 | A | EA | AERO | 02 | 2022-01-19 | 2022-04-26 | AC-5246-01 | 22 | 140.68 | 3094.96 | O
M1-02 | 30 | SO | 482792 | 9 | 2 | C10327 | CUST PU | N60 | B11 | B | EA | MRO | 01 | 2022-01-10 | 2022-04-25 | AC-5951-03 | 12 | 110.44 | 1325.28 | O
M1-02 | 30 | SO | 487012 | 9 | 1 | C10222 | UPS GND | 2%10N30 | B07 | D | EA | OEM | 05 | 2021-06-08 | 2021-09-23 | AC-4358-02 | 75 | 159.09 | 11931.75 | O
M1-02 | 20 | BL | 481007 | 5 | 2 | C10852 | CUST PU | N30 | B11 | E | EA | OEM | 05 | 2022-04-10 | 2022-06-01 | AC-8880-03 | 7 | 102.45 | 717.15 | O
M1-02 | 20 | SO | 488812 | 10 | 3 | C10936 | FDX 2D | N60 | B22 | B | EA | DEF | 01 | 2022-01-06 | 2022-04-09 | AC-2334-02 | 53 | 40.67 | 2155.51 | P
M1-02 | 20 | SO | 487164 | 7 | 3 | C10238 | LTL | N45 | B14 | B | EA | DEF | 01 | 2021-12-07 | 2022-03-31 | AC-1248-B | 42 | 129.21 | 5426.82 | O
M1-02 | 30 | BL | 483246 | 2 | 0 | C10526 | LTL | N45 | B11 | NC | EA | OEM | 02 | 2022-01-25 | 2022-03-24 | AC-6792-A | 19 | 114.17 | 2169.23 | O
M1-02 | 20 | BL | 487774 | 6 | 1 | C10519 | BEST WAY | 2%10N30 | B07 | D | EA | OEM | 05 | 2022-02-16 | 2022-04-07 | AC-8498-A | 35 | 124.72 | 4365.2 | P
M1-02 | 20 | SO | 486601 | 3 | 2 | C10544 | LTL | N60 | B11 | B | EA | DEF | 05 | 2022-01-28 | 2022-03-19 | AC-1513-03 | 22 | 49.49 | 1088.78 | O
M1-02 | 20 | BL | 487859 | 12 | 3 | C10526 | UPS GND | N60 | B11 | E | EA | OEM | 05 | 2022-03-25 | 2022-04-28 | AC-2364-01 | 43 | 108.33 | 4658.19 | P
M1-02 | 30 | SO | 480495 | 7 | 2 | C10211 | LTL | N30 | B07 | E | EA | DEF | 05 | 2022-01-23 | 2022-05-23 | AC-4792-03 | 72 | 173.74 | 12509.28 | O
M1-02 | 20 | SO | 481492 | 7 | 1 | C10544 | CUST PU | N30 | B07 | NC | EA | OEM | 05 | 2022-03-13 | 2022-05-09 | AC-2938-03 | 67 | 57.83 | 3874.61 | O
M1-02 | 20 | SO | 487959 | 12 | 0 | C10950 | BEST WAY | N30 | B11 | E | EA | AERO | 01 | 2022-02-03 | 2022-05-20 | AC-2415-B | 28 | 146.76 | 4109.28 | P
M1-02 | 20 | BL | 487533 | 11 | 0 | C10806 | CUST PU | N45 | B14 | E | EA | DEF | 05 | 2021-11-27 | 2022-02-22 | AC-7555-03 | 16 | 153.99 | 2463.84 | P
M1-02 | 20 | SO | 483001 | 6 | 1 | C10752 | LTL | 2%10N30 | B07 | D | EA | DEF | 05 | 2022-02-24 | 2022-04-26 | AC-9526-B | 46 | 137.39 | 6319.94 | O
M1-02 | 20 | SO | 484357 | 8 | 0 | C10332 | BEST WAY | 2%10N30 | B07 | NC | EA | DEF | 01 | 2022-01-03 | 2022-02-01 | AC-1542-02 | 96 | 176.76 | 16968.96 | O
M1-02 | 30 | BL | 483435 | 7 | 1 | C10817 | FDX 2D | N30 | B22 | E | EA | MRO | 05 | 2022-04-12 | 2022-05-29 | AC-1632-03 | 55 | 57.42 | 3158.1 | O
M1-02 | 20 | SO | 488233 | 11 | 3 | C10824 | LTL | N45 | B07 | NC | EA | OEM | 05 | 2021-09-28 | 2022-01-24 | AC-1514-10 | 58 | 116.82 | 6775.56 | P
M1-02 | 30 | SO | 488637 | 6 | 3 | C10455 | UPS GND | 2%10N30 | B11 | B | EA | AERO | 02 | 2021-08-09 | 2021-11-18 | AC-7019-10 | 42 | 148.83 | 6250.86 | P
M1-02 | 30 | BL | 485908 | 8 | 0 | C10664 | BEST WAY | N45 | B14 | A | EA | AERO | 01 | 2022-01-29 | 2022-04-22 | AC-6074-10 | 95 | 62.46 | 5933.7 | O
M1-02 | 20 | SO | 489385 | 1 | 2 | C10752 | FDX 2D | N45 | B14 | A | EA | MRO | 01 | 2022-01-16 | 2022-05-01 | AC-3542-03 | 37 | 87.06 | 3221.22 | P
M1-02 | 20 | BL | 481892 | 7 | 2 | C10385 | CUST PU | N45 | B22 | B | EA | DEF | 02 | 2022-03-12 | 2022-05-06 | AC-4792-03 | 83 | 168.92 | 14020.36 | O
M1-02 | 30 | SO | 485396 | 1 | 1 | C10256 | BEST WAY | N45 | B11 | C | EA | OEM | 05 | 2022-04-09 | 2022-05-11 | AC-4615-01 | 25 | 98.01 | 2450.25 | O
M1-02 | 30 | SO | 485558 | 1 | 3 | C10249 | BEST WAY | N30 | B11 | NC | EA | OEM | 02 | 2022-04-05 | 2022-05-18 | AC-3815-B | 27 | 43.7 | 1179.9 | O
M1-02 | 20 | SO | 489420 | 11 | 0 | C10695 | CUST PU | N45 | B22 | A | EA | MRO | 05 | 2022-01-24 | 2022-05-14 | AC-8302-05 | 13 | 77.85 | 1012.05 | P
M1-02 | 30 | SO | 484450 | 5 | 3 | C10501 | BEST WAY | N60 | B22 | A | EA | OEM | 05 | 2022-02-18 | 2022-06-08 | AC-3103-B | 73 | 140.01 | 10220.73 | O
M1-02 | 30 | SO | 481765 | 4 | 1 | C10973 | LTL | N60 | B07 | B | EA | MRO | 05 | 2022-02-16 | 2022-06-02 | AC-4393-B | 47 | 103.11 | 4846.17 | O
M1-02 | 30 | BL | 487022 | 7 | 0 | C10305 | CUST PU | 2%10N30 | B22 | D | EA | MRO | 05 | 2022-02-12 | 2022-03-20 | AC-9725-A | 34 | 49.33 | 1677.22 | O
M1-02 | 30 | SO | 481026 | 7 | 0 | C10695 | UPS GND | N60 | B07 | A | EA | OEM | 01 | 2021-12-25 | 2022-03-18 | AC-2167-03 | 78 | 42.07 | 3281.46 | O
M1-02 | 30 | SO | 482345 | 9 | 3 | C10222 | LTL | N30 | B14 | E | EA | AERO | 02 | 2021-04-23 | 2021-06-23 | AC-9800-A | 17 | 58.86 | 1000.62 | O
M1-02 | 30 | SO | 480757 | 11 | 3 | C10664 | UPS GND | N60 | B07 | NC | EA | DEF | 02 | 2022-02-27 | 2022-06-10 | AC-9159-A | 48 | 119.6 | 5740.8 | O
M1-02 | 20 | SO | 489489 | 4 | 1 | C10211 | UPS GND | N60 | B14 | E | EA | OEM | 05 | 2021-09-13 | 2021-11-14 | AC-8463-05 | 37 | 74.83 | 2768.71 | P
M1-02 | 30 | BL | 487020 | 12 | 3 | C10251 | LTL | N45 | B14 | D | EA | OEM | 05 | 2022-03-12 | 2022-05-19 | AC-1704-A | 51 | 156.13 | 7962.63 | O
M1-02 | 30 | SO | 483058 | 9 | 1 | C10238 | BEST WAY | N45 | B14 | D | EA | MRO | 02 | 2022-02-23 | 2022-06-02 | AC-4314-03 | 78 | 100.39 | 7830.42 | O
M1-02 | 20 | SO | 488564 | 7 | 3 | C10519 | BEST WAY | 2%10N30 | B14 | NC | EA | MRO | 01 | 2021-11-30 | 2022-04-02 | AC-4792-10 | 37 | 179.62 | 6645.94 | P
M1-02 | 20 | SO | 489106 | 6 | 2 | C10305 | CUST PU | N45 | B14 | B | EA | MRO | 01 | 2021-12-27 | 2022-05-14 | AC-2250-05 | 38 | 106.27 | 4038.26 | P
M1-02 | 20 | SO | 485425 | 10 | 0 | C10526 | UPS GND | 2%10N30 | B11 | A | EA | OEM | 05 | 2021-12-06 | 2022-02-22 | AC-2274-A | 55 | 133.23 | 7327.65 | O
M1-02 | 20 | SO | 481174 | 3 | 1 | C10936 | UPS GND | N30 | B07 | D | EA | MRO | 01 | 2022-01-29 | 2022-05-16 | AC-4181-B | 48 | 156.4 | 7507.2 | O
M1-02 | 30 | SO | 481308 | 7 | 2 | C10695 | BEST WAY | N45 | B14 | B | EA | MRO | 01 | 2022-02-08 | 2022-05-02 | AC-7648-01 | 41 | 109.2 | 4477.2 | O
M1-02 | 20 | SO | 483536 | 11 | 3 | C10238 | FDX 2D | 2%10N30 | B14 | B | EA | OEM | 01 | 2021-04-24 | 2021-07-26 | AC-3896-05 | 87 | 133.59 | 11622.33 | O
M1-02 | 30 | SO | 487145 | 3 | 3 | C10966 | BEST WAY | 2%10N30 | B07 | D | EA | OEM | 05 | 2021-11-22 | 2022-03-15 | AC-3357-05 | 59 | 59.2 | 3492.8 | O
M1-02 | 20 | SO | 485379 | 9 | 0 | C10950 | FDX 2D | N45 | B14 | E | EA | MRO | 02 | 2022-02-08 | 2022-05-10 | AC-4033-01 | 48 | 176.51 | 8472.48 | O
M1-02 | 20 | SO | 486622 | 5 | 0 | C10501 | FDX 2D | 2%10N30 | B07 | D | EA | DEF | 05 | 2021-10-17 | 2021-12-20 | AC-4834-02 | 46 | 118.95 | 5471.7 | O
M1-02 | 20 | SO | 481314 | 2 | 2 | C10756 | FDX 2D | 2%10N30 | B11 | B | EA | AERO | 02 | 2021-08-20 | 2021-09-22 | AC-5791-B | 36 | 89.92 | 3237.12 | O
M1-02 | 30 | BL | 480174 | 10 | 2 | C10332 | CUST PU | 2%10N30 | B14 | C | EA | MRO | 05 | 2022-03-01 | 2022-06-06 | AC-4357-05 | 70 | 102.98 | 7208.6 | O
M1-02 | 20 | BL | 482006 | 6 | 3 | C10420 | FDX 2D | 2%10N30 | B22 | E | EA | AERO | 01 | 2022-01-05 | 2022-03-30 | AC-9788-B | 65 | 158.76 | 10319.4 | O
M1-02 | 30 | SO | 487708 | 4 | 0 | C10264 | BEST WAY | 2%10N30 | B11 | C | EA | DEF | 01 | 2021-09-12 | 2021-12-09 | AC-9141-03 | 42 | 122.53 | 5146.26 | P
M1-02 | 20 | SO | 486186 | 12 | 3 | C10256 | FDX 2D | N45 | B14 | C | EA | AERO | 01 | 2022-02-18 | 2022-05-13 | AC-3583-10 | 31 | 141.7 | 4392.7 | O
M1-02 | 30 | SO | 485266 | 5 | 1 | C10706 | CUST PU | N45 | B11 | B | EA | MRO | 02 | 2021-09-06 | 2021-12-06 | AC-9821-03 | 83 | 168.71 | 14002.93 | O
M1-02 | 30 | SO | 489267 | 3 | 1 | C10377 | LTL | N45 | B11 | C | EA | OEM | 01 | 2021-11-01 | 2021-12-26 | AC-3628-10 | 11 | 48.65 | 535.15 | P
M1-02 | 30 | BL | 487057 | 4 | 3 | C10186 | BEST WAY | N45 | B14 | D | EA | MRO | 02 | 2022-02-18 | 2022-06-01 | AC-6281-10 | 49 | 71.49 | 3503.01 | O
M1-02 | 20 | SO | 484551 | 1 | 0 | C10305 | UPS GND | 2%10N30 | B07 | C | EA | MRO | 05 | 2022-01-15 | 2022-04-04 | AC-6625-10 | 71 | 60.5 | 4295.5 | O
M1-02 | 30 | BL | 484513 | 1 | 0 | C10664 | CUST PU | N30 | B07 | A | EA | MRO | 02 | 2021-12-01 | 2022-04-09 | AC-7586-02 | 49 | 110.92 | 5435.08 | O
M1-02 | 20 | SO | 486045 | 2 | 3 | C10238 | FDX 2D | 2%10N30 | B22 | C | EA | OEM | 01 | 2021-12-31 | 2022-05-06 | AC-2081-A | 99 | 56.77 | 5620.23 | O
M1-02 | 30 | SO | 486240 | 9 | 2 | C10211 | LTL | N30 | B11 | E | EA | AERO | 05 | 2022-01-09 | 2022-05-03 | AC-3151-05 | 34 | 104.33 | 3547.22 | O
M1-02 | 20 | SO | 489004 | 7 | 2 | C10456 | LTL | N45 | B11 | NC | EA | DEF | 05 | 2022-04-07 | 2022-05-08 | AC-4074-03 | 2 | 50.97 | 101.94 | P
M1-02 | 30 | SO | 485709 | 10 | 1 | C10281 | BEST WAY | 2%10N30 | B11 | B | EA | AERO | 02 | 2022-02-10 | 2022-04-13 | AC-6864-05 | 37 | 79.44 | 2939.28 | O
M1-02 | 20 | SO | 485701 | 12 | 3 | C10787 | LTL | N45 | B14 | E | EA | AERO | 01 | 2022-04-14 | 2022-05-18 | AC-3418-01 | 48 | 98.43 | 4724.64 | O
M1-02 | 20 | BL | 484242 | 9 | 2 | C10519 | CUST PU | N60 | B07 | D | EA | OEM | 02 | 2021-09-27 | 2022-01-18 | AC-4400-10 | 15 | 80.2 | 1203 | O
M1-02 | 30 | SO | 481783 | 4 | 1 | C10455 | FDX 2D | N30 | B11 | C | EA | AERO | 05 | 2022-04-25 | 2022-06-08 | AC-6433-A | 36 | 128.78 | 4636.08 | O
M1-02 | 30 | BL | 489028 | 7 | 2 | C10560 | CUST PU | 2%10N30 | B11 | E | EA | AERO | 05 | 2022-01-03 | 2022-04-14 | AC-4600-10 | 8 | 137.77 | 1102.16 | P
M1-02 | 30 | BL | 486527 | 6 | 0 | C10758 | CUST PU | N30 | B22 | A | EA | AERO | 02 | 2022-01-30 | 2022-04-10 | AC-9400-03 | 41 | 51.05 | 2093.05 | O
M1-02 | 20 | SO | 481011 | 8 | 3 | C10746 | BEST WAY | 2%10N30 | B14 | A | EA | OEM | 02 | 2022-04-02 | 2022-05-08 | AC-8900-01 | 42 | 93.93 | 3945.06 | O
M1-02 | 30 | SO | 482184 | 3 | 3 | C10252 | LTL | N45 | B14 | E | EA | AERO | 01 | 2022-04-03 | 2022-05-09 | AC-9773-02 | 18 | 66.6 | 1198.8 | O
M1-02 | 30 | SO | 484681 | 11 | 3 | C10526 | UPS GND | 2%10N30 | B11 | A | EA | OEM | 01 | 2022-02-15 | 2022-06-04 | AC-6295-A | 98 | 47.86 | 4690.28 | O
M1-02 | 30 | SO | 480829 | 6 | 1 | C10860 | LTL | N60 | B14 | NC | EA | MRO | 01 | 2022-02-23 | 2022-05-28 | AC-1742-B | 95 | 177.76 | 16887.2 | O
M1-02 | 30 | SO | 482267 | 2 | 2 | C10273 | CUST PU | N60 | B22 | C | EA | AERO | 05 | 2022-02-10 | 2022-03-22 | AC-5248-03 | 41 | 131.7 | 5399.7 | O
M1-02 | 20 | SO | 486364 | 6 | 2 | C10332 | UPS GND | N60 | B22 | C | EA | DEF | 02 | 2021-12-26 | 2022-03-28 | AC-9587-B | 79 | 124.49 | 9834.71 | O
M1-02 | 20 | SO | 483332 | 11 | 0 | C10824 | BEST WAY | N45 | B22 | NC | EA | MRO | 05 | 2022-04-26 | 2022-05-30 | AC-7315-05 | 14 | 49.28 | 689.92 | O
M1-02 | 30 | SO | 483422 | 6 | 2 | C10280 | BEST WAY | N30 | B07 | A | EA | OEM | 01 | 2022-02-15 | 2022-05-16 | AC-6482-03 | 62 | 163.54 | 10139.48 | O
M1-02 | 20 | SO | 487881 | 10 | 1 | C10752 | UPS GND | N45 | B11 | A | EA | AERO | 01 | 2022-04-15 | 2022-06-08 | AC-1599-03 | 23 | 148.93 | 3425.39 | P
M1-02 | 30 | SO | 489766 | 1 | 2 | C10966 | BEST WAY | N30 | B11 | NC | EA | DEF | 05 | 2021-08-08 | 2021-10-28 | AC-4801-02 | 26 | 161.73 | 4204.98 | P
M1-02 | 20 | SO | 489562 | 6 | 0 | C10752 | BEST WAY | N30 | B11 | E | EA | OEM | 05 | 2021-10-30 | 2022-03-01 | AC-4972-05 | 24 | 119.83 | 2875.92 | P
M1-02 | 30 | SO | 488551 | 11 | 3 | C10860 | CUST PU | N30 | B22 | D | EA | DEF | 01 | 2021-05-29 | 2021-10-05 | AC-1570-02 | 24 | 78.42 | 1882.08 | P
M1-02 | 30 | BL | 486282 | 8 | 1 | C10824 | CUST PU | N30 | B22 | B | EA | MRO | 02 | 2021-07-06 | 2021-11-11 | AC-3852-05 | 32 | 71.68 | 2293.76 | O
M1-02 | 30 | SO | 481545 | 11 | 1 | C10758 | FDX 2D | N60 | B07 | A | EA | AERO | 01 | 2021-10-23 | 2021-12-19 | AC-9804-10 | 73 | 89.25 | 6515.25 | O
M1-02 | 30 | SO | 486112 | 12 | 0 | C10752 | CUST PU | N60 | B07 | A | EA | OEM | 01 | 2022-03-28 | 2022-06-07 | AC-9564-02 | 18 | 152.36 | 2742.48 | O
M1-02 | 30 | SO | 482850 | 10 | 1 | C10252 | FDX 2D | 2%10N30 | B07 | E | EA | MRO | 05 | 2022-01-15 | 2022-03-27 | AC-8284-10 | 68 | 58.78 | 3997.04 | O
M1-02 | 30 | SO | 488428 | 12 | 2 | C10530 | FDX 2D | N60 | B14 | B | EA | AERO | 02 | 2021-12-10 | 2022-03-30 | AC-4980-01 | 57 | 67.05 | 3821.85 | P
M1-02 | 20 | BL | 489615 | 12 | 0 | C10385 | BEST WAY | N60 | B07 | A | EA | OEM | 05 | 2022-01-01 | 2022-05-14 | AC-3277-05 | 5 | 32.63 | 163.15 | P
M1-02 | 20 | SO | 484925 | 7 | 3 | C10950 | BEST WAY | N60 | B07 | D | EA | DEF | 02 | 2021-09-09 | 2021-10-15 | AC-1480-01 | 67 | 164.14 | 10997.38 | O
M1-02 | 20 | SO | 482397 | 1 | 2 | C10758 | BEST WAY | 2%10N30 | B22 | B | EA | MRO | 01 | 2022-03-12 | 2022-04-17 | AC-7989-02 | 47 | 152.73 | 7178.31 | O
M1-02 | 20 | BL | 480366 | 10 | 0 | C10350 | BEST WAY | N45 | B14 | C | EA | AERO | 02 | 2022-03-13 | 2022-05-20 | AC-8214-03 | 52 | 136.43 | 7094.36 | O
M1-02 | 30 | SO | 483773 | 5 | 3 | C10852 | LTL | N45 | B22 | C | EA | AERO | 05 | 2022-02-12 | 2022-06-04 | AC-7406-05 | 99 | 48.48 | 4799.52 | O
M1-02 | 20 | SO | 483411 | 7 | 1 | C10756 | CUST PU | N60 | B07 | A | EA | DEF | 02 | 2022-01-09 | 2022-04-22 | AC-3053-03 | 92 | 172.69 | 15887.48 | O
M1-02 | 20 | BL | 484140 | 5 | 2 | C10305 | FDX 2D | N45 | B11 | C | EA | OEM | 05 | 2021-10-13 | 2022-01-14 | AC-7688-10 | 99 | 143.78 | 14234.22 | O
M1-02 | 20 | BL | 485583 | 2 | 0 | C10756 | CUST PU | N60 | B22 | E | EA | MRO | 01 | 2022-05-02 | 2022-05-31 | AC-7817-A | 17 | 99.7 | 1694.9 | O
M1-02 | 20 | SO | 481283 | 7 | 1 | C10519 | BEST WAY | N60 | B22 | B | EA | MRO | 02 | 2021-04-09 | 2021-08-14 | AC-6896-10 | 67 | 169.67 | 11367.89 | O
M1-02 | 20 | SO | 482258 | 9 | 0 | C10385 | FDX 2D | N30 | B07 | A | EA | DEF | 02 | 2022-04-18 | 2022-05-19 | AC-2368-03 | 85 | 157.78 | 13411.3 | O
M1-02 | 30 | SO | 484808 | 9 | 2 | C10281 | UPS GND | N45 | B22 | D | EA | MRO | 01 | 2021-07-18 | 2021-11-14 | AC-4029-A | 72 | 121.1 | 8719.2 | O
M1-02 | 20 | SO | 487941 | 7 | 0 | C10752 | LTL | N45 | B22 | NC | EA | OEM | 01 | 2022-01-29 | 2022-03-19 | AC-2415-B | 50 | 48.08 | 2404 | P
M1-02 | 20 | SO | 481623 | 1 | 2 | C10806 | UPS GND | N45 | B07 | D | EA | DEF | 01 | 2021-12-28 | 2022-03-19 | AC-8641-05 | 97 | 126.77 | 12296.69 | O
M1-02 | 30 | BL | 489021 | 1 | 3 | C10251 | BEST WAY | N45 | B07 | E | EA | AERO | 02 | 2022-02-27 | 2022-05-19 | AC-4512-A | 32 | 129.7 | 4150.4 | P
M1-02 | 20 | BL | 487115 | 10 | 1 | C10273 | BEST WAY | 2%10N30 | B11 | NC | EA | MRO | 05 | 2021-11-21 | 2022-03-28 | AC-6261-05 | 11 | 128.51 | 1413.61 | O
M1-02 | 30 | SO | 489039 | 9 | 1 | C10327 | UPS GND | N60 | B11 | A | EA | OEM | 05 | 2021-11-25 | 2022-04-11 | AC-6130-05 | 39 | 130.11 | 5074.29 | P
M1-02 | 30 | SO | 487363 | 9 | 1 | C10951 | LTL | N30 | B22 | NC | EA | OEM | 02 | 2022-03-10 | 2022-05-04 | AC-4597-10 | 37 | 83.76 | 3099.12 | P
M1-02 | 20 | SO | 486197 | 2 | 3 | C10756 | FDX 2D | N30 | B22 | E | EA | DEF | 01 | 2021-03-24 | 2021-07-15 | AC-5841-03 | 58 | 47.04 | 2728.32 | O
M1-02 | 20 | BL | 480220 | 8 | 0 | C10936 | CUST PU | 2%10N30 | B07 | D | EA | AERO | 05 | 2022-02-16 | 2022-05-15 | AC-5731-10 | 60 | 168.96 | 10137.6 | O
M1-02 | 20 | SO | 480586 | 11 | 1 | C10568 | BEST WAY | N60 | B07 | NC | EA | DEF | 05 | 2022-01-08 | 2022-04-10 | AC-8099-05 | 49 | 153.73 | 7532.77 | O
M1-02 | 30 | BL | 485086 | 7 | 3 | C10332 | FDX 2D | 2%10N30 | B22 | C | EA | OEM | 05 | 2022-01-15 | 2022-05-28 | AC-6433-01 | 95 | 125.02 | 11876.9 | O
M1-02 | 20 | SO | 485046 | 1 | 3 | C10695 | CUST PU | N45 | B22 | C | EA | OEM | 01 | 2021-08-06 | 2021-10-06 | AC-5097-02 | 92 | 127.52 | 11731.84 | O
M1-02 | 30 | BL | 483719 | 6 | 2 | C10186 | CUST PU | N30 | B07 | D | EA | OEM | 02 | 2022-01-03 | 2022-04-28 | AC-8915-05 | 33 | 57.48 | 1896.84 | O
M1-02 | 30 | SO | 488371 | 1 | 3 | C10332 | FDX 2D | 2%10N30 | B11 | NC | EA | AERO | 05 | 2022-01-23 | 2022-02-26 | AC-3929-10 | 32 | 154.1 | 4931.2 | P
M1-02 | 30 | SO | 488203 | 12 | 0 | C10695 | UPS GND | 2%10N30 | B14 | C | EA | OEM | 02 | 2021-11-18 | 2022-01-28 | AC-6827-05 | 27 | 175.15 | 4729.05 | P
M1-02 | 30 | SO | 487727 | 12 | 1 | C10973 | CUST PU | N45 | B11 | NC | EA | DEF | 01 | 2021-12-05 | 2022-04-24 | AC-6792-B | 60 | 126.47 | 7588.2 | P
M1-02 | 20 | SO | 486790 | 8 | 3 | C10420 | CUST PU | N30 | B11 | B | EA | MRO | 05 | 2021-05-21 | 2021-06-25 | AC-8806-01 | 73 | 127.62 | 9316.26 | O
M1-02 | 30 | SO | 482960 | 5 | 0 | C10786 | FDX 2D | N30 | B14 | D | EA | AERO | 02 | 2022-01-29 | 2022-04-17 | AC-5061-A | 4 | 148.45 | 593.8 | O
M1-02 | 30 | SO | 487769 | 1 | 1 | C10746 | UPS GND | N30 | B22 | A | EA | DEF | 01 | 2022-02-25 | 2022-04-07 | AC-2827-02 | 22 | 73.23 | 1611.06 | P
M1-02 | 30 | SO | 488412 | 4 | 1 | C10746 | CUST PU | N30 | B22 | D | EA | DEF | 02 | 2021-06-08 | 2021-07-24 | AC-7582-02 | 11 | 79.31 | 872.41 | P
M1-02 | 30 | SO | 484588 | 9 | 1 | C10900 | CUST PU | N30 | B07 | C | EA | MRO | 02 | 2021-12-17 | 2022-04-28 | AC-3359-A | 63 | 118.16 | 7444.08 | O
M1-02 | 30 | SO | 488762 | 3 | 1 | C10951 | FDX 2D | N45 | B22 | C | EA | AERO | 02 | 2022-02-13 | 2022-04-10 | AC-6549-A | 12 | 161.43 | 1937.16 | P
M1-02 | 20 | SO | 485711 | 1 | 1 | C10264 | BEST WAY | N60 | B11 | A | EA | MRO | 02 | 2022-01-08 | 2022-03-23 | AC-1382-B | 92 | 95.9 | 8822.8 | O
M1-02 | 20 | SO | 480918 | 8 | 1 | C10377 | UPS GND | N60 | B22 | B | EA | OEM | 01 | 2021-12-29 | 2022-02-10 | AC-8099-05 | 15 | 67.22 | 1008.3 | O
M1-02 | 30 | SO | 482297 | 7 | 2 | C10186 | CUST PU | N30 | B14 | B | EA | MRO | 01 | 2022-03-20 | 2022-04-29 | AC-3764-01 | 86 | 79.19 | 6810.34 | O
M1-02 | 20 | SO | 482082 | 6 | 0 | C10249 | BEST WAY | N45 | B07 | B | EA | AERO | 01 | 2021-10-24 | 2022-01-10 | AC-4241-02 | 91 | 133.03 | 12105.73 | O
M1-02 | 30 | SO | 481636 | 12 | 0 | C10530 | FDX 2D | N60 | B07 | B | EA | DEF | 01 | 2021-12-22 | 2022-04-13 | AC-7122-03 | 95 | 170.52 | 16199.4 | O
M1-02 | 30 | BL | 480670 | 9 | 1 | C10222 | CUST PU | N30 | B11 | E | EA | AERO | 01 | 2022-01-15 | 2022-03-17 | AC-6845-03 | 71 | 96.44 | 6847.24 | O
M1-02 | 20 | BL | 483511 | 11 | 3 | C10305 | LTL | 2%10N30 | B22 | B | EA | DEF | 01 | 2021-05-31 | 2021-07-13 | AC-9491-03 | 49 | 134.52 | 6591.48 | O
M1-02 | 30 | SO | 481254 | 3 | 0 | C10321 | CUST PU | N45 | B22 | D | EA | DEF | 01 | 2022-02-22 | 2022-05-22 | AC-3024-A | 48 | 156.63 | 7518.24 | O
M1-02 | 20 | SO | 488067 | 5 | 3 | C10321 | CUST PU | N60 | B07 | C | EA | OEM | 01 | 2021-10-10 | 2022-01-25 | AC-9084-10 | 50 | 129.8 | 6490 | P
M1-02 | 30 | SO | 480991 | 10 | 0 | C10305 | CUST PU | N60 | B22 | A | EA | MRO | 01 | 2022-03-18 | 2022-04-23 | AC-8552-01 | 69 | 125.64 | 8669.16 | O
M1-02 | 20 | SO | 480793 | 2 | 2 | C10211 | FDX 2D | N60 | B07 | E | EA | AERO | 02 | 2022-02-25 | 2022-05-13 | AC-7714-10 | 38 | 113.61 | 4317.18 | O
M1-02 | 20 | SO | 489541 | 6 | 0 | C10787 | FDX 2D | 2%10N30 | B22 | E | EA | DEF | 02 | 2022-04-11 | 2022-05-19 | AC-1060-10 | 33 | 34.07 | 1124.31 | P
M1-02 | 30 | SO | 483471 | 9 | 2 | C10456 | CUST PU | N60 | B14 | A | EA | DEF | 01 | 2021-04-14 | 2021-07-11 | AC-6053-01 | 36 | 79.39 | 2858.04 | O
M1-02 | 30 | BL | 487043 | 9 | 3 | C10746 | UPS GND | N60 | B11 | E | EA | OEM | 02 | 2021-10-21 | 2022-01-09 | AC-6845-03 | 81 | 134.09 | 10861.29 | O
M1-02 | 30 | SO | 480907 | 7 | 1 | C10519 | LTL | N60 | B07 | NC | EA | DEF | 02 | 2021-08-07 | 2021-12-12 | AC-6433-A | 49 | 165.33 | 8101.17 | O
M1-02 | 20 | BL | 480967 | 1 | 2 | C10806 | LTL | N60 | B14 | C | EA | AERO | 05 | 2022-01-09 | 2022-03-28 | AC-1084-B | 4 | 172.86 | 691.44 | O
M1-02 | 30 | BL | 488694 | 11 | 3 | C10940 | LTL | 2%10N30 | B07 | B | EA | OEM | 05 | 2021-05-24 | 2021-07-28 | AC-3912-03 | 7 | 179.67 | 1257.69 | P
M1-02 | 30 | SO | 483728 | 1 | 1 | C10252 | FDX 2D | N60 | B07 | D | EA | OEM | 05 | 2022-04-17 | 2022-06-04 | AC-3559-A | 61 | 49.9 | 3043.9 | O
M1-02 | 20 | BL | 480342 | 7 | 2 | C10758 | UPS GND | N30 | B11 | B | EA | DEF | 05 | 2021-11-10 | 2022-01-28 | AC-9564-02 | 99 | 98.15 | 9716.85 | O
M1-02 | 30 | SO | 484999 | 5 | 1 | C10273 | BEST WAY | N30 | B11 | D | EA | MRO | 01 | 2022-01-29 | 2022-04-12 | AC-1601-05 | 62 | 177.58 | 11009.96 | O
M1-02 | 30 | SO | 489238 | 7 | 3 | C10252 | CUST PU | N45 | B11 | NC | EA | DEF | 02 | 2021-11-13 | 2021-12-17 | AC-9101-02 | 38 | 53.62 | 2037.56 | P
M1-02 | 30 | SO | 487184 | 9 | 1 | C10695 | FDX 2D | 2%10N30 | B22 | A | EA | AERO | 01 | 2021-12-02 | 2021-12-31 | AC-7110-A | 30 | 74.09 | 2222.7 | O
M1-02 | 20 | SO | 481880 | 7 | 0 | C10860 | LTL | N30 | B22 | A | EA | OEM | 02 | 2021-06-20 | 2021-08-24 | AC-8676-03 | 70 | 49.34 | 3453.8 | O
M1-02 | 30 | SO | 484963 | 12 | 0 | C10973 | UPS GND | N45 | B22 | D | EA | DEF | 01 | 2022-03-25 | 2022-05-16 | AC-3312-03 | 45 | 106.24 | 4780.8 | O
M1-02 | 30 | SO | 486605 | 8 | 3 | C10589 | BEST WAY | 2%10N30 | B22 | NC | EA | DEF | 01 | 2022-02-25 | 2022-04-17 | AC-4541-10 | 95 | 172.38 | 16376.1 | O
M1-02 | 20 | SO | 484330 | 4 | 1 | C10331 | CUST PU | N30 | B22 | E | EA | AERO | 05 | 2021-12-11 | 2022-01-14 | AC-1632-03 | 72 | 72.98 | 5254.56 | O
M1-02 | 30 | SO | 486366 | 9 | 0 | C10305 | UPS GND | N60 | B22 | NC | EA | MRO | 02 | 2022-01-16 | 2022-05-13 | AC-9541-B | 28 | 67.51 | 1890.28 | O
M1-02 | 20 | SO | 485033 | 7 | 3 | C10251 | FDX 2D | N45 | B11 | B | EA | AERO | 02 | 2022-05-03 | 2022-06-04 | AC-2895-B | 9 | 84.12 | 757.08 | O
M1-02 | 30 | SO | 482656 | 4 | 3 | C10966 | FDX 2D | N60 | B07 | E | EA | MRO | 02 | 2022-03-23 | 2022-05-20 | AC-9491-03 | 20 | 158.36 | 3167.2 | O
M1-02 | 20 | SO | 484038 | 10 | 1 | C10186 | BEST WAY | N60 | B22 | C | EA | DEF | 05 | 2022-02-25 | 2022-05-23 | AC-5036-01 | 72 | 74.29 | 5348.88 | O
M1-02 | 30 | SO | 486465 | 2 | 0 | C10455 | BEST WAY | N45 | B07 | C | EA | MRO | 01 | 2022-02-21 | 2022-05-08 | AC-5284-02 | 67 | 157.06 | 10523.02 | O
M1-02 | 20 | BL | 481388 | 7 | 3 | C10211 | BEST WAY | 2%10N30 | B14 | B | EA | MRO | 02 | 2021-04-14 | 2021-06-20 | AC-9834-01 | 92 | 138.56 | 12747.52 | O
M1-02 | 30 | SO | 480926 | 8 | 1 | C10251 | LTL | N60 | B07 | A | EA | AERO | 02 | 2022-04-23 | 2022-06-05 | AC-9767-B | 75 | 43.67 | 3275.25 | O
M1-02 | 20 | SO | 487988 | 2 | 1 | C10568 | LTL | N60 | B14 | E | EA | OEM | 02 | 2021-06-10 | 2021-09-16 | AC-2827-02 | 5 | 69.2 | 346 | P
M1-02 | 20 | BL | 483982 | 7 | 0 | C10321 | BEST WAY | N60 | B22 | C | EA | AERO | 05 | 2021-06-23 | 2021-09-23 | AC-4992-B | 73 | 163.99 | 11971.27 | O
M1-02 | 20 | SO | 485174 | 2 | 2 | C10752 | BEST WAY | N45 | B22 | E | EA | DEF | 05 | 2021-09-23 | 2021-11-25 | AC-5341-10 | 16 | 75.36 | 1205.76 | O
M1-02 | 20 | BL | 484909 | 5 | 1 | C10786 | LTL | N30 | B22 | D | EA | MRO | 01 | 2022-03-03 | 2022-05-19 | AC-8872-B | 79 | 79.9 | 6312.1 | O
M1-02 | 30 | BL | 489056 | 1 | 1 | C10264 | CUST PU | N45 | B07 | D | EA | AERO | 02 | 2022-02-28 | 2022-05-05 | AC-6130-05 | 9 | 83.4 | 750.6 | P
M1-02 | 20 | BL | 488385 | 8 | 3 | C10519 | CUST PU | 2%10N30 | B07 | A | EA | MRO | 02 | 2022-01-12 | 2022-04-20 | AC-7572-B | 21 | 159.21 | 3343.41 | P
M1-02 | 20 | SO | 484873 | 1 | 0 | C10461 | CUST PU | N45 | B07 | D | EA | AERO | 01 | 2021-11-24 | 2022-04-10 | AC-1599-03 | 4 | 119.6 | 478.4 | O
M1-02 | 20 | SO | 481743 | 10 | 3 | C10824 | FDX 2D | N45 | B22 | NC | EA | DEF | 01 | 2022-02-27 | 2022-04-24 | AC-5303-B | 90 | 133.24 | 11991.6 | O
M1-02 | 20 | SO | 488985 | 11 | 2 | C10238 | FDX 2D | 2%10N30 | B07 | A | EA | OEM | 02 | 2022-03-15 | 2022-05-22 | AC-9591-03 | 33 | 122.25 | 4034.25 | P
M1-02 | 30 | SO | 485935 | 2 | 0 | C10786 | UPS GND | N30 | B07 | A | EA | OEM | 02 | 2022-02-16 | 2022-04-16 | AC-8341-03 | 86 | 67.16 | 5775.76 | O
M1-02 | 30 | BL | 489187 | 4 | 1 | C10420 | CUST PU | N30 | B11 | E | EA | MRO | 01 | 2022-01-20 | 2022-04-10 | AC-4074-03 | 8 | 34.98 | 279.84 | P
M1-02 | 20 | SO | 483302 | 2 | 2 | C10273 | LTL | 2%10N30 | B07 | C | EA | OEM | 02 | 2022-02-26 | 2022-05-01 | AC-6707-10 | 96 | 63.45 | 6091.2 | O
M1-02 | 20 | SO | 485570 | 8 | 3 | C10966 | CUST PU | N60 | B11 | A | EA | AERO | 05 | 2021-11-30 | 2022-03-20 | AC-2167-03 | 55 | 63.52 | 3493.6 | O
M1-02 | 30 | SO | 484972 | 11 | 0 | C10251 | UPS GND | N30 | B14 | A | EA | OEM | 05 | 2022-02-13 | 2022-05-26 | AC-3945-A | 58 | 99.24 | 5755.92 | O
M1-02 | 30 | SO | 483496 | 6 | 2 | C10222 | BEST WAY | 2%10N30 | B07 | A | EA | OEM | 05 | 2022-04-05 | 2022-06-09 | AC-1084-B | 31 | 86.26 | 2674.06 | O
M1-02 | 20 | SO | 485397 | 10 | 3 | C10456 | CUST PU | N30 | B14 | B | EA | AERO | 05 | 2021-12-12 | 2022-04-29 | AC-5951-03 | 40 | 129.39 | 5175.6 | O
M1-02 | 30 | SO | 480333 | 10 | 2 | C10746 | LTL | N45 | B11 | A | EA | OEM | 01 | 2021-12-08 | 2022-04-13 | AC-1740-03 | 70 | 87.2 | 6104 | O
M1-02 | 30 | SO | 485141 | 7 | 0 | C10280 | UPS GND | N60 | B07 | C | EA | AERO | 01 | 2021-07-19 | 2021-10-21 | AC-8126-10 | 96 | 175.69 | 16866.24 | O
M1-02 | 30 | SO | 485053 | 12 | 0 | C10560 | BEST WAY | 2%10N30 | B11 | C | EA | AERO | 01 | 2022-01-18 | 2022-05-28 | AC-1023-B | 84 | 139.04 | 11679.36 | O
M1-02 | 30 | SO | 488082 | 6 | 0 | C10321 | LTL | N45 | B07 | NC | EA | MRO | 02 | 2022-02-09 | 2022-04-18 | AC-3060-02 | 36 | 40.36 | 1452.96 | P
M1-02 | 30 | SO | 481279 | 8 | 1 | C10436 | CUST PU | 2%10N30 | B07 | B | EA | OEM | 01 | 2022-03-12 | 2022-05-28 | AC-5856-02 | 57 | 160.45 | 9145.65 | O
M1-02 | 20 | SO | 482494 | 5 | 1 | C10350 | UPS GND | N45 | B22 | D | EA | AERO | 05 | 2021-10-04 | 2021-12-11 | AC-3357-05 | 84 | 156.45 | 13141.8 | O
M1-02 | 20 | SO | 485387 | 1 | 0 | C10498 | BEST WAY | N30 | B22 | B | EA | MRO | 05 | 2021-09-08 | 2022-01-24 | AC-2561-05 | 51 | 52.4 | 2672.4 | O
M1-02 | 20 | BL | 480371 | 1 | 1 | C10526 | FDX 2D | 2%10N30 | B07 | A | EA | OEM | 01 | 2022-03-14 | 2022-06-04 | AC-1748-A | 77 | 169.26 | 13033.02 | O
M1-02 | 30 | SO | 488879 | 8 | 1 | C10936 | UPS GND | N30 | B14 | A | EA | AERO | 01 | 2022-02-13 | 2022-05-14 | AC-1231-10 | 36 | 123.34 | 4440.24 | P
M1-02 | 30 | SO | 481435 | 4 | 2 | C10526 | UPS GND | 2%10N30 | B07 | NC | EA | OEM | 05 | 2021-11-22 | 2022-03-31 | AC-4550-03 | 4 | 44.06 | 176.24 | O
M1-02 | 30 | SO | 483460 | 9 | 3 | C10758 | FDX 2D | N60 | B14 | B | EA | OEM | 01 | 2022-01-10 | 2022-05-13 | AC-1894-02 | 83 | 55.2 | 4581.6 | O
M1-02 | 30 | SO | 480073 | 7 | 2 | C10281 | FDX 2D | N30 | B14 | A | EA | OEM | 02 | 2022-03-15 | 2022-04-17 | AC-3312-03 | 59 | 89.97 | 5308.23 | O
M1-02 | 20 | SO | 480554 | 3 | 3 | C10385 | UPS GND | N30 | B07 | E | EA | DEF | 01 | 2022-02-23 | 2022-05-03 | AC-5441-02 | 63 | 69.9 | 4403.7 | O
M1-02 | 20 | SO | 484755 | 4 | 1 | C10940 | CUST PU | N60 | B11 | D | EA | MRO | 01 | 2021-10-25 | 2021-11-23 | AC-3559-A | 22 | 43.28 | 952.16 | O
M1-02 | 30 | SO | 483657 | 5 | 1 | C10350 | BEST WAY | N30 | B14 | A | EA | MRO | 05 | 2022-02-19 | 2022-06-02 | AC-1773-B | 63 | 104.97 | 6613.11 | O
M1-02 | 20 | BL | 480980 | 2 | 1 | C10332 | LTL | N45 | B07 | D | EA | OEM | 05 | 2022-02-10 | 2022-05-20 | AC-2849-B | 97 | 104.47 | 10133.59 | O
M1-02 | 30 | SO | 487830 | 4 | 1 | C10688 | UPS GND | 2%10N30 | B11 | NC | EA | OEM | 02 | 2021-12-14 | 2022-02-03 | AC-1570-02 | 8 | 88.86 | 710.88 | P
M1-02 | 30 | SO | 487780 | 8 | 3 | C10385 | BEST WAY | N45 | B07 | NC | EA | MRO | 05 | 2022-01-02 | 2022-03-22 | AC-6271-03 | 4 | 133.76 | 535.04 | P
M1-02 | 20 | SO | 486993 | 4 | 1 | C10280 | UPS GND | N30 | B22 | A | EA | AERO | 02 | 2022-01-28 | 2022-03-18 | AC-7648-01 | 88 | 70.26 | 6182.88 | O
M1-02 | 20 | SO | 484456 | 7 | 1 | C10950 | UPS GND | 2%10N30 | B11 | C | EA | OEM | 02 | 2021-12-19 | 2022-05-02 | AC-4181-B | 17 | 89.35 | 1518.95 | O
M1-02 | 30 | BL | 487364 | 9 | 0 | C10273 | LTL | N30 | B07 | E | EA | AERO | 01 | 2021-05-25 | 2021-07-26 | AC-4082-10 | 5 | 81.25 | 406.25 | P
M1-02 | 30 | BL | 485823 | 1 | 3 | C10332 | LTL | N45 | B14 | E | EA | OEM | 01 | 2022-03-30 | 2022-06-04 | AC-9425-05 | 58 | 130.58 | 7573.64 | O
M1-02 | 30 | SO | 489605 | 5 | 3 | C10530 | LTL | N45 | B22 | A | EA | OEM | 01 | 2022-01-22 | 2022-06-05 | AC-3592-B | 13 | 62.32 | 810.16 | P
M1-02 | 20 | BL | 486775 | 6 | 2 | C10211 | CUST PU | N60 | B07 | E | EA | MRO | 05 | 2021-12-18 | 2022-03-16 | AC-8916-03 | 78 | 76.64 | 5977.92 | O
M1-02 | 30 | SO | 481832 | 7 | 1 | C10377 | UPS GND | 2%10N30 | B14 | C | EA | MRO | 05 | 2021-12-17 | 2022-02-20 | AC-7877-03 | 19 | 167.03 | 3173.57 | O
M1-02 | 20 | SO | 480257 | 12 | 2 | C10806 | CUST PU | N45 | B14 | C | EA | AERO | 05 | 2022-03-11 | 2022-05-14 | AC-1599-03 | 66 | 164.72 | 10871.52 | O
M1-02 | 30 | SO | 486207 | 7 | 1 | C10786 | FDX 2D | N45 | B11 | NC | EA | AERO | 02 | 2021-05-08 | 2021-09-14 | AC-2415-B | 61 | 97.88 | 5970.68 | O
M1-02 | 20 | SO | 482776 | 8 | 2 | C10519 | BEST WAY | N30 | B11 | C | EA | AERO | 01 | 2022-01-26 | 2022-04-30 | AC-5291-10 | 22 | 171.79 | 3779.38 | O
M1-02 | 20 | SO | 483666 | 3 | 0 | C10900 | FDX 2D | N45 | B14 | E | EA | OEM | 05 | 2021-04-27 | 2021-07-28 | AC-5198-03 | 4 | 42.03 | 168.12 | O
M1-02 | 30 | SO | 482535 | 5 | 0 | C10256 | CUST PU | 2%10N30 | B07 | D | EA | MRO | 02 | 2021-05-06 | 2021-08-22 | AC-6774-02 | 38 | 155 | 5890 | O
M1-02 | 30 | BL | 480984 | 2 | 0 | C10824 | BEST WAY | N60 | B22 | D | EA | AERO | 05 | 2022-02-08 | 2022-04-27 | AC-1566-10 | 5 | 174.19 | 870.95 | O
M1-02 | 30 | SO | 481591 | 2 | 1 | C10436 | FDX 2D | N45 | B07 | D | EA | AERO | 02 | 2021-12-08 | 2022-04-21 | AC-3649-B | 59 | 57.99 | 3421.41 | O
M1-02 | 30 | SO | 486119 | 10 | 3 | C10211 | LTL | 2%10N30 | B22 | D | EA | OEM | 05 | 2021-04-27 | 2021-08-02 | AC-7840-A | 67 | 166.17 | 11133.39 | O
M1-02 | 30 | SO | 485722 | 9 | 0 | C10758 | FDX 2D | 2%10N30 | B11 | A | EA | DEF | 05 | 2021-05-28 | 2021-08-06 | AC-9459-10 | 47 | 80.95 | 3804.65 | O
M1-02 | 20 | SO | 487307 | 1 | 3 | C10456 | CUST PU | N30 | B14 | NC | EA | MRO | 01 | 2022-04-21 | 2022-06-04 | AC-6482-03 | 74 | 137 | 10138 | O
M1-02 | 20 | BL | 488783 | 5 | 0 | C10746 | UPS GND | 2%10N30 | B11 | C | EA | MRO | 01 | 2021-04-23 | 2021-09-06 | AC-3103-B | 59 | 167.77 | 9898.43 | P
M1-02 | 30 | SO | 485336 | 3 | 1 | C10350 | BEST WAY | 2%10N30 | B14 | A | EA | AERO | 01 | 2022-02-13 | 2022-04-27 | AC-7589-02 | 85 | 88.81 | 7548.85 | O
M1-02 | 30 | SO | 486356 | 3 | 2 | C10817 | UPS GND | N30 | B11 | C | EA | AERO | 05 | 2022-02-25 | 2022-04-14 | AC-7586-02 | 94 | 134.34 | 12627.96 | O
M1-02 | 30 | SO | 484991 | 1 | 2 | C10806 | LTL | N45 | B22 | E | EA | OEM | 01 | 2022-03-11 | 2022-05-15 | AC-1710-05 | 58 | 97.54 | 5657.32 | O
M1-02 | 30 | SO | 485479 | 12 | 2 | C10756 | UPS GND | N45 | B11 | A | EA | OEM | 01 | 2022-01-21 | 2022-03-18 | AC-1740-03 | 77 | 170.73 | 13146.21 | O
M1-02 | 30 | BL | 480888 | 10 | 0 | C10251 | FDX 2D | N60 | B22 | A | EA | OEM | 01 | 2021-01-20 | 2021-05-27 | AC-7103-B | 42 | 77.75 | 3265.5 | O
M1-02 | 30 | SO | 489585 | 7 | 3 | C10560 | CUST PU | N60 | B22 | A | EA | OEM | 05 | 2022-01-15 | 2022-05-03 | AC-4972-05 | 7 | 127.23 | 890.61 | P
M1-02 | 30 | SO | 489656 | 5 | 0 | C10327 | FDX 2D | N45 | B14 | A | EA | OEM | 05 | 2021-11-25 | 2022-03-28 | AC-8653-01 | 7 | 126.18 | 883.26 | P
M1-02 | 30 | SO | 485122 | 4 | 2 | C10560 | CUST PU | N60 | B07 | B | EA | DEF | 05 | 2022-05-08 | 2022-06-10 | AC-1448-02 | 87 | 100.12 | 8710.44 | O
M1-02 | 20 | SO | 488286 | 5 | 0 | C10251 | LTL | N60 | B11 | A | EA | OEM | 01 | 2021-12-20 | 2022-02-12 | AC-9448-05 | 54 | 124.7 | 6733.8 | P
M1-02 | 30 | BL | 488988 | 7 | 2 | C10281 | LTL | 2%10N30 | B14 | D | EA | DEF | 01 | 2022-01-13 | 2022-04-04 | AC-8463-05 | 7 | 58.13 | 406.91 | P
M1-02 | 20 | SO | 485815 | 4 | 2 | C10973 | LTL | N30 | B07 | A | EA | OEM | 05 | 2022-01-12 | 2022-05-16 | AC-3583-10 | 39 | 96.24 | 3753.36 | O
M1-02 | 30 | SO | 483488 | 1 | 0 | C10951 | UPS GND | N45 | B11 | C | EA | OEM | 01 | 2021-12-11 | 2022-04-30 | AC-6433-10 | 42 | 120.55 | 5063.1 | O
M1-02 | 20 | SO | 484011 | 7 | 0 | C10860 | UPS GND | N30 | B11 | C | EA | OEM | 05 | 2021-05-09 | 2021-07-11 | AC-5248-03 | 43 | 136.8 | 5882.4 | O
M1-02 | 30 | BL | 487082 | 11 | 1 | C10966 | UPS GND | N45 | B14 | E | EA | MRO | 01 | 2021-08-16 | 2021-12-26 | AC-1467-01 | 98 | 92.06 | 9021.88 | O
M1-02 | 30 | SO | 481047 | 9 | 0 | C10526 | CUST PU | N30 | B22 | E | EA | AERO | 05 | 2022-01-10 | 2022-04-10 | AC-8916-03 | 27 | 156.19 | 4217.13 | O
M1-02 | 30 | SO | 484865 | 7 | 2 | C10900 | BEST WAY | N45 | B14 | C | EA | MRO | 05 | 2022-02-13 | 2022-03-18 | AC-4241-02 | 69 | 49.65 | 3425.85 | O
M1-02 | 30 | SO | 482204 | 9 | 0 | C10501 | LTL | N60 | B22 | NC | EA | DEF | 02 | 2022-01-27 | 2022-04-28 | AC-3239-01 | 24 | 57.93 | 1390.32 | O
M1-02 | 20 | SO | 484914 | 8 | 0 | C10806 | CUST PU | N30 | B11 | C | EA | OEM | 01 | 2022-02-04 | 2022-04-16 | AC-7355-A | 98 | 149.09 | 14610.82 | O
M1-02 | 20 | BL | 487294 | 11 | 1 | C10170 | FDX 2D | 2%10N30 | B22 | E | EA | AERO | 02 | 2022-02-14 | 2022-04-05 | AC-9159-A | 69 | 146.97 | 10140.93 | O
M1-02 | 20 | SO | 484604 | 11 | 0 | C10238 | FDX 2D | N60 | B11 | C | EA | AERO | 02 | 2021-04-11 | 2021-06-29 | AC-8139-02 | 35 | 157.26 | 5504.1 | O
M1-02 | 30 | SO | 486417 | 7 | 1 | C10695 | CUST PU | N30 | B07 | A | EA | OEM | 05 | 2021-03-22 | 2021-07-09 | AC-1170-05 | 45 | 133.48 | 6006.6 | O
M1-02 | 20 | SO | 480822 | 6 | 3 | C10238 | CUST PU | N60 | B14 | D | EA | MRO | 05 | 2021-10-10 | 2022-02-13 | AC-3767-10 | 25 | 132.99 | 3324.75 | O
M1-02 | 20 | BL | 484712 | 10 | 2 | C10501 | CUST PU | 2%10N30 | B07 | B | EA | MRO | 05 | 2021-12-26 | 2022-04-09 | AC-8284-10 | 45 | 67.23 | 3025.35 | O
M1-02 | 30 | SO | 487716 | 7 | 3 | C10331 | BEST WAY | N30 | B14 | E | EA | DEF | 05 | 2022-02-16 | 2022-03-31 | AC-1514-10 | 47 | 133.96 | 6296.12 | P
M1-02 | 30 | SO | 486843 | 5 | 3 | C10305 | FDX 2D | N60 | B14 | NC | EA | OEM | 01 | 2022-05-02 | 2022-06-09 | AC-2146-05 | 31 | 151.29 | 4689.99 | O
M1-02 | 30 | SO | 486604 | 5 | 0 | C10560 | UPS GND | N45 | B07 | A | EA | DEF | 05 | 2021-11-06 | 2021-12-24 | AC-9245-A | 58 | 164.32 | 9530.56 | O
M1-02 | 20 | SO | 480697 | 12 | 1 | C10456 | LTL | N60 | B14 | A | EA | AERO | 05 | 2021-08-06 | 2021-12-01 | AC-3829-05 | 52 | 88.8 | 4617.6 | O
M1-02 | 20 | SO | 483304 | 10 | 0 | C10752 | UPS GND | N60 | B14 | E | EA | DEF | 02 | 2022-03-09 | 2022-04-30 | AC-4443-A | 86 | 134.83 | 11595.38 | O
M1-02 | 20 | SO | 489479 | 5 | 0 | C10501 | CUST PU | N30 | B22 | NC | EA | AERO | 05 | 2021-09-25 | 2021-11-12 | AC-8100-02 | 40 | 77.4 | 3096 | P
M1-02 | 30 | BL | 483605 | 11 | 1 | C10664 | CUST PU | 2%10N30 | B14 | NC | EA | OEM | 01 | 2021-10-17 | 2022-02-24 | AC-5781-02 | 82 | 60.73 | 4979.86 | O
M1-02 | 20 | BL | 488687 | 6 | 2 | C10281 | LTL | N30 | B07 | C | EA | AERO | 02 | 2021-12-04 | 2022-04-11 | AC-4825-B | 51 | 179.21 | 9139.71 | P
M1-02 | 30 | SO | 486986 | 3 | 2 | C10973 | LTL | 2%10N30 | B22 | C | EA | MRO | 01 | 2022-02-11 | 2022-05-22 | AC-9159-A | 4 | 165.22 | 660.88 | O
M1-02 | 30 | SO | 480428 | 11 | 1 | C10321 | LTL | N30 | B14 | E | EA | AERO | 01 | 2022-04-04 | 2022-05-23 | AC-1574-05 | 43 | 152.14 | 6542.02 | O
M1-02 | 20 | SO | 484494 | 12 | 3 | C10746 | LTL | N60 | B11 | NC | EA | AERO | 02 | 2022-01-14 | 2022-05-10 | AC-3312-03 | 60 | 146.92 | 8815.2 | O
M1-02 | 20 | SO | 489542 | 7 | 2 | C10498 | BEST WAY | N45 | B14 | B | EA | AERO | 01 | 2022-01-16 | 2022-04-13 | AC-8338-01 | 39 | 113.38 | 4421.82 | P
M1-02 | 20 | BL | 488699 | 8 | 0 | C10544 | UPS GND | N30 | B11 | C | EA | DEF | 01 | 2022-01-13 | 2022-04-21 | AC-1648-A | 39 | 174.06 | 6788.34 | P
M1-02 | 20 | BL | 489703 | 8 | 3 | C10264 | LTL | 2%10N30 | B11 | NC | EA | AERO | 05 | 2022-04-07 | 2022-06-10 | AC-6921-B | 6 | 45.42 | 272.52 | P
M1-02 | 20 | SO | 486088 | 7 | 3 | C10706 | CUST PU | 2%10N30 | B14 | E | EA | MRO | 05 | 2021-03-29 | 2021-08-10 | AC-8270-10 | 27 | 115.8 | 3126.6 | O
M1-02 | 20 | SO | 481943 | 3 | 0 | C10331 | BEST WAY | 2%10N30 | B11 | E | EA | DEF | 05 | 2022-03-28 | 2022-04-27 | AC-7406-05 | 62 | 132.16 | 8193.92 | O
M1-02 | 30 | SO | 488352 | 2 | 1 | C10280 | CUST PU | N45 | B22 | NC | EA | MRO | 01 | 2022-01-21 | 2022-03-24 | AC-8035-02 | 37 | 58.74 | 2173.38 | P
M1-02 | 30 | SO | 484511 | 11 | 3 | C10461 | BEST WAY | N30 | B07 | A | EA | OEM | 02 | 2022-02-21 | 2022-04-14 | AC-8099-05 | 95 | 42.13 | 4002.35 | O
M1-02 | 20 | SO | 481728 | 5 | 3 | C10222 | UPS GND | N30 | B14 | A | EA | AERO | 05 | 2021-12-12 | 2022-04-18 | AC-7699-03 | 55 | 173.89 | 9563.95 | O
M1-02 | 20 | SO | 483871 | 10 | 1 | C10951 | UPS GND | 2%10N30 | B07 | A | EA | MRO | 02 | 2022-01-07 | 2022-03-17 | AC-8506-A | 65 | 49.4 | 3211 | O
M1-02 | 30 | SO | 486348 | 10 | 2 | C10900 | BEST WAY | 2%10N30 | B14 | C | EA | MRO | 01 | 2022-04-01 | 2022-05-23 | AC-1710-05 | 20 | 118.74 | 2374.8 | O
M1-02 | 30 | SO | 486233 | 11 | 1 | C10756 | CUST PU | N30 | B11 | NC | EA | DEF | 05 | 2022-02-05 | 2022-05-09 | AC-1480-01 | 69 | 116.88 | 8064.72 | O
M1-02 | 30 | BL | 485297 | 11 | 2 | C10664 | FDX 2D | 2%10N30 | B07 | E | EA | DEF | 01 | 2022-03-10 | 2022-05-14 | AC-8956-B | 69 | 130.35 | 8994.15 | O
M1-02 | 20 | SO | 489674 | 1 | 3 | C10305 | LTL | N30 | B14 | A | EA | OEM | 01 | 2022-04-01 | 2022-05-06 | AC-8805-01 | 12 | 83.94 | 1007.28 | P
M1-02 | 30 | SO | 481001 | 11 | 3 | C10940 | UPS GND | N60 | B11 | A | EA | DEF | 02 | 2022-01-15 | 2022-04-10 | AC-9207-02 | 67 | 172.38 | 11549.46 | O
M1-02 | 30 | BL | 489358 | 7 | 3 | C10377 | FDX 2D | N30 | B11 | D | EA | DEF | 01 | 2021-07-15 | 2021-08-22 | AC-9591-03 | 22 | 68.55 | 1508.1 | P
M1-02 | 30 | BL | 489458 | 12 | 2 | C10830 | LTL | N30 | B14 | E | EA | OEM | 02 | 2022-03-23 | 2022-05-20 | AC-7953-A | 17 | 59.85 | 1017.45 | P
M1-02 | 20 | SO | 482613 | 5 | 1 | C10787 | FDX 2D | N45 | B14 | A | EA | MRO | 05 | 2022-03-24 | 2022-05-21 | AC-7038-02 | 8 | 116.96 | 935.68 | O
M1-02 | 20 | SO | 484815 | 5 | 2 | C10281 | CUST PU | N60 | B07 | C | EA | DEF | 01 | 2022-01-18 | 2022-04-09 | AC-6570-05 | 92 | 120.26 | 11063.92 | O
M1-02 | 20 | SO | 481603 | 4 | 1 | C10786 | FDX 2D | N45 | B11 | NC | EA | MRO | 05 | 2022-03-02 | 2022-05-13 | AC-9740-01 | 32 | 158.46 | 5070.72 | O
M1-02 | 30 | SO | 480795 | 7 | 3 | C10519 | UPS GND | 2%10N30 | B14 | B | EA | OEM | 01 | 2021-05-07 | 2021-07-16 | AC-7102-A | 79 | 82.39 | 6508.81 | O
M1-02 | 30 | BL | 480833 | 4 | 2 | C10256 | CUST PU | N60 | B14 | E | EA | OEM | 02 | 2021-05-01 | 2021-07-25 | AC-3456-B | 69 | 101.63 | 7012.47 | O
M1-02 | 30 | SO | 484366 | 4 | 3 | C10321 | CUST PU | 2%10N30 | B14 | E | EA | AERO | 05 | 2022-03-23 | 2022-05-13 | AC-4400-10 | 68 | 66.77 | 4540.36 | O
M1-02 | 30 | SO | 484722 | 2 | 3 | C10222 | UPS GND | N45 | B07 | B | EA | MRO | 02 | 2022-03-24 | 2022-05-01 | AC-7896-01 | 92 | 127.45 | 11725.4 | O
M1-02 | 30 | BL | 480567 | 6 | 1 | C10746 | BEST WAY | N30 | B11 | A | EA | MRO | 01 | 2021-05-27 | 2021-07-05 | AC-4132-01 | 57 | 137.42 | 7832.94 | O
M1-02 | 20 | SO | 486090 | 8 | 0 | C10526 | UPS GND | N45 | B22 | B | EA | AERO | 02 | 2022-02-09 | 2022-05-21 | AC-3067-10 | 49 | 175.21 | 8585.29 | O
M1-02 | 20 | SO | 487374 | 11 | 0 | C10350 | BEST WAY | N30 | B14 | NC | EA | AERO | 02 | 2021-07-09 | 2021-10-03 | AC-8665-02 | 15 | 74.19 | 1112.85 | P
M1-02 | 30 | BL | 485189 | 9 | 2 | C10786 | FDX 2D | 2%10N30 | B14 | NC | EA | AERO | 01 | 2022-02-14 | 2022-04-23 | AC-5074-03 | 11 | 132.76 | 1460.36 | O
M1-02 | 30 | SO | 486199 | 5 | 2 | C10501 | CUST PU | N30 | B14 | D | EA | MRO | 02 | 2022-01-09 | 2022-03-18 | AC-9481-02 | 65 | 68.97 | 4483.05 | O
M1-02 | 20 | SO | 481200 | 8 | 1 | C10530 | LTL | N60 | B22 | B | EA | OEM | 05 | 2021-05-11 | 2021-09-19 | AC-4566-A | 31 | 164.45 | 5097.95 | O
M1-02 | 20 | BL | 482735 | 3 | 1 | C10568 | CUST PU | 2%10N30 | B07 | E | EA | OEM | 01 | 2022-04-02 | 2022-05-15 | AC-1793-03 | 78 | 144.78 | 11292.84 | O
M1-02 | 30 | SO | 481527 | 3 | 1 | C10530 | BEST WAY | N60 | B07 | E | EA | MRO | 05 | 2021-06-01 | 2021-07-25 | AC-3765-A | 32 | 99.17 | 3173.44 | O
M1-02 | 20 | SO | 487027 | 9 | 2 | C10186 | BEST WAY | N45 | B14 | D | EA | AERO | 05 | 2022-03-15 | 2022-04-27 | AC-5331-02 | 86 | 46.51 | 3999.86 | O
M1-02 | 20 | BL | 489298 | 7 | 3 | C10568 | CUST PU | 2%10N30 | B22 | A | EA | DEF | 01 | 2022-03-18 | 2022-04-25 | AC-3086-05 | 2 | 61.08 | 122.16 | P
M1-02 | 20 | SO | 485348 | 12 | 3 | C10526 | FDX 2D | N60 | B07 | B | EA | OEM | 01 | 2022-04-18 | 2022-06-09 | AC-1649-B | 75 | 52.89 | 3966.75 | O
M1-02 | 30 | SO | 488242 | 8 | 0 | C10695 | LTL | N30 | B07 | NC | EA | OEM | 02 | 2022-01-11 | 2022-03-19 | AC-4873-10 | 38 | 60.13 | 2284.94 | P
M1-02 | 20 | SO | 489199 | 8 | 3 | C10688 | UPS GND | N30 | B07 | E | EA | DEF | 02 | 2022-02-24 | 2022-06-06 | AC-7644-B | 21 | 105.52 | 2215.92 | P
M1-02 | 20 | SO | 481925 | 12 | 3 | C10420 | FDX 2D | N60 | B14 | A | EA | AERO | 05 | 2021-05-07 | 2021-08-29 | AC-5331-02 | 95 | 151.63 | 14404.85 | O
M1-02 | 20 | BL | 480527 | 3 | 1 | C10186 | BEST WAY | N45 | B07 | A | EA | OEM | 01 | 2022-03-13 | 2022-04-15 | AC-6612-B | 75 | 93.65 | 7023.75 | O
M1-02 | 30 | BL | 486723 | 1 | 1 | C10519 | BEST WAY | 2%10N30 | B07 | D | EA | OEM | 05 | 2022-02-18 | 2022-05-02 | AC-9183-05 | 4 | 69.07 | 276.28 | O
M1-02 | 30 | SO | 483098 | 11 | 1 | C10756 | LTL | N60 | B11 | NC | EA | DEF | 02 | 2021-12-04 | 2022-04-13 | AC-3277-A | 100 | 48.16 | 4816 | O
M1-02 | 20 | SO | 488959 | 10 | 0 | C10456 | FDX 2D | N60 | B14 | C | EA | DEF | 02 | 2021-09-08 | 2021-10-22 | AC-1773-02 | 5 | 28.06 | 140.3 | P
M1-02 | 30 | BL | 484827 | 5 | 0 | C10544 | UPS GND | N30 | B22 | C | EA | OEM | 02 | 2022-03-02 | 2022-05-10 | AC-3103-B | 8 | 164.68 | 1317.44 | O
M1-02 | 30 | SO | 484928 | 7 | 1 | C10321 | LTL | 2%10N30 | B14 | E | EA | MRO | 05 | 2022-01-28 | 2022-06-07 | AC-3920-05 | 10 | 56.39 | 563.9 | O
M1-02 | 30 | SO | 488126 | 11 | 1 | C10252 | CUST PU | 2%10N30 | B07 | NC | EA | DEF | 01 | 2021-07-27 | 2021-12-03 | AC-7582-02 | 44 | 73.08 | 3215.52 | P
M1-02 | 30 | SO | 481413 | 2 | 0 | C10252 | CUST PU | 2%10N30 | B11 | D | EA | OEM | 02 | 2021-09-20 | 2022-02-05 | AC-9838-B | 88 | 154.59 | 13603.92 | O
M1-02 | 30 | SO | 485765 | 5 | 0 | C10252 | CUST PU | 2%10N30 | B22 | NC | EA | OEM | 05 | 2022-03-04 | 2022-04-08 | AC-3002-03 | 99 | 96.87 | 9590.13 | O
M1-02 | 20 | SO | 480910 | 5 | 3 | C10252 | FDX 2D | 2%10N30 | B22 | NC | EA | MRO | 02 | 2022-03-18 | 2022-05-22 | AC-4001-10 | 76 | 173.83 | 13211.08 | O
M1-02 | 30 | SO | 488441 | 4 | 1 | C10456 | LTL | N45 | B07 | NC | EA | DEF | 02 | 2021-11-24 | 2022-02-08 | AC-2364-01 | 26 | 119.6 | 3109.6 | P
M1-02 | 20 | BL | 487172 | 4 | 0 | C10211 | FDX 2D | N30 | B22 | NC | EA | AERO | 02 | 2022-02-28 | 2022-05-13 | AC-6911-02 | 97 | 160.39 | 15557.83 | O
M1-02 | 30 | SO | 485797 | 9 | 3 | C10746 | FDX 2D | N45 | B11 | A | EA | AERO | 05 | 2021-08-06 | 2021-11-21 | AC-7103-B | 41 | 175.84 | 7209.44 | O
M1-02 | 30 | BL | 489012 | 3 | 3 | C10281 | UPS GND | 2%10N30 | B11 | E | EA | DEF | 02 | 2022-01-23 | 2022-06-06 | AC-2135-A | 7 | 119.71 | 837.97 | P
M1-02 | 30 | SO | 484088 | 3 | 0 | C10252 | FDX 2D | N60 | B07 | A | EA | OEM | 01 | 2022-02-16 | 2022-05-19 | AC-3127-02 | 56 | 155.24 | 8693.44 | O
M1-02 | 30 | SO | 487416 | 11 | 2 | C10252 | UPS GND | N30 | B14 | E | EA | OEM | 02 | 2021-09-21 | 2021-12-04 | AC-3396-01 | 56 | 104.65 | 5860.4 | P
M1-02 | 20 | BL | 489687 | 7 | 2 | C10256 | CUST PU | 2%10N30 | B07 | B | EA | MRO | 02 | 2022-01-15 | 2022-05-05 | AC-4307-01 | 39 | 134.01 | 5226.39 | P
M1-02 | 20 | SO | 480215 | 3 | 2 | C10900 | CUST PU | N45 | B14 | NC | EA | OEM | 01 | 2021-12-12 | 2022-04-16 | AC-8336-B | 45 | 94.92 | 4271.4 | O
M1-02 | 20 | BL | 484775 | 7 | 2 | C10695 | LTL | N60 | B11 | B | EA | MRO | 05 | 2022-01-18 | 2022-06-07 | AC-2081-A | 6 | 97.4 | 584.4 | O
M1-02 | 30 | SO | 488656 | 11 | 0 | C10170 | BEST WAY | 2%10N30 | B14 | D | EA | AERO | 02 | 2022-01-11 | 2022-04-12 | AC-7397-01 | 49 | 134.06 | 6568.94 | P
M1-02 | 30 | SO | 485666 | 11 | 1 | C10530 | BEST WAY | 2%10N30 | B14 | NC | EA | DEF | 02 | 2021-12-13 | 2022-03-14 | AC-2555-A | 90 | 151.42 | 13627.8 | O
M1-02 | 20 | SO | 480053 | 6 | 1 | C10560 | CUST PU | N45 | B07 | D | EA | AERO | 02 | 2022-03-30 | 2022-05-20 | AC-7395-10 | 54 | 43.69 | 2359.26 | O
M1-02 | 30 | BL | 483154 | 3 | 1 | C10758 | FDX 2D | N30 | B22 | D | EA | DEF | 02 | 2021-02-28 | 2021-05-30 | AC-6446-10 | 62 | 174.39 | 10812.18 | O
M1-02 | 20 | BL | 481659 | 9 | 0 | C10706 | FDX 2D | N45 | B22 | D | EA | OEM | 02 | 2021-12-23 | 2022-04-22 | AC-5731-10 | 12 | 152.11 | 1825.32 | O
M1-02 | 20 | SO | 488365 | 6 | 3 | C10940 | LTL | 2%10N30 | B22 | D | EA | OEM | 02 | 2021-11-22 | 2022-03-17 | AC-8665-02 | 39 | 94.1 | 3669.9 | P
M1-02 | 30 | SO | 484890 | 3 | 2 | C10966 | BEST WAY | N60 | B22 | NC | EA | AERO | 02 | 2022-05-05 | 2022-06-08 | AC-7154-02 | 92 | 153.16 | 14090.72 | O
M1-02 | 30 | SO | 483448 | 9 | 3 | C10436 | CUST PU | N45 | B07 | D | EA | AERO | 05 | 2021-11-14 | 2022-03-26 | AC-1978-10 | 20 | 84.92 | 1698.4 | O
M1-02 | 30 | SO | 482605 | 10 | 2 | C10256 | UPS GND | N45 | B14 | A | EA | DEF | 01 | 2022-04-01 | 2022-05-16 | AC-2300-02 | 25 | 87.11 | 2177.75 | O
M1-02 | 30 | SO | 488996 | 9 | 1 | C10238 | BEST WAY | N30 | B07 | E | EA | DEF | 02 | 2022-02-13 | 2022-05-26 | AC-6196-A | 17 | 100.03 | 1700.51 | P
M1-02 | 30 | SO | 484941 | 11 | 1 | C10787 | FDX 2D | 2%10N30 | B07 | C | EA | AERO | 05 | 2021-12-26 | 2022-05-12 | AC-2063-10 | 71 | 98.18 | 6970.78 | O
M1-02 | 20 | SO | 486703 | 12 | 2 | C10900 | CUST PU | N45 | B22 | A | EA | DEF | 02 | 2022-01-20 | 2022-02-23 | AC-1791-05 | 67 | 95.72 | 6413.24 | O
M1-02 | 20 | SO | 485889 | 9 | 1 | C10327 | UPS GND | 2%10N30 | B11 | C | EA | DEF | 02 | 2021-11-26 | 2022-03-28 | AC-3937-10 | 7 | 100.71 | 704.97 | O
M1-02 | 30 | SO | 484320 | 7 | 0 | C10305 | CUST PU | N45 | B11 | B | EA | DEF | 05 | 2022-04-12 | 2022-05-20 | AC-4556-A | 57 | 160.52 | 9149.64 | O
M1-02 | 30 | SO | 487342 | 2 | 3 | C10249 | LTL | N45 | B07 | NC | EA | DEF | 01 | 2022-02-01 | 2022-04-16 | AC-5968-02 | 31 | 118.34 | 3668.54 | O
M1-02 | 30 | SO | 480479 | 7 | 3 | C10316 | CUST PU | N60 | B14 | NC | EA | DEF | 05 | 2022-03-30 | 2022-06-08 | AC-7613-10 | 20 | 165.77 | 3315.4 | O
M1-02 | 20 | BL | 481393 | 2 | 0 | C10544 | BEST WAY | N30 | B07 | NC | EA | OEM | 05 | 2022-02-03 | 2022-06-10 | AC-6446-10 | 36 | 58.65 | 2111.4 | O
M1-02 | 20 | SO | 480873 | 2 | 2 | C10695 | FDX 2D | N30 | B14 | NC | EA | AERO | 05 | 2022-04-09 | 2022-05-25 | AC-1704-A | 46 | 133.83 | 6156.18 | O
M1-02 | 30 | SO | 483579 | 2 | 2 | C10560 | FDX 2D | 2%10N30 | B11 | A | EA | AERO | 01 | 2021-08-18 | 2022-01-04 | AC-8793-A | 56 | 139.96 | 7837.76 | O
M1-02 | 30 | SO | 483338 | 4 | 3 | C10817 | UPS GND | N60 | B22 | E | EA | MRO | 05 | 2022-05-05 | 2022-06-04 | AC-4935-10 | 55 | 106.44 | 5854.2 | O
M1-02 | 20 | SO | 489381 | 4 | 2 | C10589 | FDX 2D | N45 | B14 | D | EA | AERO | 02 | 2021-11-27 | 2022-04-03 | AC-6113-02 | 32 | 54.41 | 1741.12 | P
M1-02 | 30 | BL | 486421 | 9 | 0 | C10420 | LTL | 2%10N30 | B07 | B | EA | MRO | 05 | 2022-03-26 | 2022-05-14 | AC-2084-A | 39 | 59.57 | 2323.23 | O
M1-02 | 30 | SO | 483644 | 3 | 0 | C10786 | BEST WAY | N60 | B14 | A | EA | AERO | 02 | 2021-12-25 | 2022-02-28 | AC-4400-10 | 88 | 120.63 | 10615.44 | O
M1-02 | 20 | BL | 482626 | 5 | 1 | C10758 | BEST WAY | N45 | B22 | E | EA | OEM | 02 | 2022-01-17 | 2022-05-14 | AC-2334-02 | 20 | 46.44 | 928.8 | O
M1-02 | 30 | SO | 481094 | 7 | 1 | C10973 | CUST PU | N45 | B22 | E | EA | AERO | 05 | 2022-02-20 | 2022-03-20 | AC-8240-B | 39 | 155.1 | 6048.9 | O
M1-02 | 20 | SO | 482375 | 10 | 1 | C10211 | BEST WAY | N30 | B11 | E | EA | OEM | 01 | 2022-03-27 | 2022-05-22 | AC-2677-01 | 77 | 70.08 | 5396.16 | O
M1-02 | 30 | SO | 484840 | 3 | 0 | C10456 | CUST PU | N30 | B11 | NC | EA | MRO | 01 | 2022-01-16 | 2022-04-30 | AC-2827-02 | 6 | 43.36 | 260.16 | O
M1-02 | 30 | SO | 482031 | 2 | 3 | C10385 | UPS GND | N30 | B07 | B | EA | MRO | 02 | 2022-03-07 | 2022-04-27 | AC-4443-A | 76 | 109.09 | 8290.84 | O
M1-02 | 30 | BL | 484696 | 11 | 0 | C10519 | CUST PU | N60 | B14 | C | EA | OEM | 01 | 2021-11-24 | 2022-02-14 | AC-7846-05 | 71 | 139 | 9869 | O
M1-02 | 30 | BL | 483734 | 3 | 2 | C10249 | LTL | N30 | B11 | D | EA | MRO | 02 | 2022-03-03 | 2022-04-06 | AC-3067-10 | 69 | 87.52 | 6038.88 | O
M1-02 | 30 | SO | 484554 | 8 | 1 | C10222 | BEST WAY | N60 | B07 | D | EA | DEF | 02 | 2021-06-24 | 2021-09-17 | AC-1179-B | 61 | 53.31 | 3251.91 | O
M1-02 | 30 | SO | 487626 | 4 | 2 | C10498 | UPS GND | N30 | B07 | D | EA | DEF | 05 | 2021-07-31 | 2021-12-06 | AC-4386-01 | 10 | 121.15 | 1211.5 | P
M1-02 | 20 | SO | 488969 | 1 | 3 | C10706 | BEST WAY | 2%10N30 | B11 | D | EA | OEM | 05 | 2022-03-15 | 2022-06-06 | AC-8338-01 | 23 | 59.13 | 1359.99 | P
M1-02 | 30 | BL | 483830 | 6 | 1 | C10852 | UPS GND | 2%10N30 | B07 | NC | EA | AERO | 05 | 2021-12-25 | 2022-04-13 | AC-4792-03 | 59 | 174.96 | 10322.64 | O
M1-02 | 30 | SO | 487999 | 10 | 3 | C10544 | UPS GND | 2%10N30 | B11 | C | EA | DEF | 01 | 2021-08-16 | 2021-11-30 | AC-9448-05 | 24 | 158.12 | 3794.88 | P
M1-02 | 20 | SO | 485997 | 2 | 1 | C10544 | LTL | N45 | B22 | B | EA | MRO | 05 | 2022-03-07 | 2022-04-17 | AC-5841-03 | 34 | 116.66 | 3966.44 | O
M1-02 | 20 | SO | 485616 | 5 | 0 | C10186 | UPS GND | N30 | B14 | B | EA | AERO | 02 | 2021-06-06 | 2021-08-08 | AC-6758-10 | 48 | 166.17 | 7976.16 | O
M1-02 | 30 | BL | 485404 | 9 | 2 | C10436 | LTL | N30 | B11 | C | EA | OEM | 01 | 2021-05-24 | 2021-10-02 | AC-6469-10 | 100 | 99.94 | 9994 | O
M1-02 | 30 | SO | 482222 | 9 | 0 | C10824 | BEST WAY | 2%10N30 | B22 | A | EA | AERO | 02 | 2021-05-23 | 2021-09-04 | AC-9582-10 | 87 | 95.9 | 8343.3 | O
M1-02 | 20 | SO | 488046 | 2 | 3 | C10746 | LTL | N30 | B14 | NC | EA | OEM | 01 | 2022-04-18 | 2022-05-21 | AC-7572-B | 29 | 54.98 | 1594.42 | P
M1-02 | 30 | SO | 489316 | 6 | 2 | C10273 | CUST PU | N30 | B14 | B | EA | MRO | 02 | 2022-02-01 | 2022-05-10 | AC-1231-10 | 17 | 87.93 | 1494.81 | P
M1-02 | 30 | SO | 482918 | 9 | 0 | C10746 | FDX 2D | N60 | B14 | E | EA | DEF | 01 | 2022-02-14 | 2022-05-17 | AC-7368-03 | 20 | 111.49 | 2229.8 | O
M1-02 | 20 | SO | 482378 | 2 | 1 | C10461 | UPS GND | N30 | B22 | B | EA | AERO | 02 | 2022-02-24 | 2022-04-28 | AC-1236-10 | 90 | 136.56 | 12290.4 | O
M1-02 | 20 | SO | 483538 | 11 | 2 | C10321 | FDX 2D | 2%10N30 | B11 | D | EA | MRO | 05 | 2022-01-18 | 2022-05-29 | AC-8579-10 | 62 | 170.07 | 10544.34 | O
M1-02 | 20 | SO | 486218 | 2 | 0 | C10526 | UPS GND | N30 | B07 | NC | EA | DEF | 01 | 2022-02-14 | 2022-03-22 | AC-1649-B | 17 | 146.65 | 2493.05 | O
M1-02 | 20 | SO | 488704 | 3 | 0 | C10560 | UPS GND | N60 | B22 | B | EA | AERO | 02 | 2022-01-17 | 2022-05-05 | AC-4690-10 | 14 | 179.94 | 2519.16 | P
M1-02 | 20 | SO | 481525 | 5 | 0 | C10186 | UPS GND | 2%10N30 | B11 | NC | EA | DEF | 01 | 2021-11-26 | 2022-03-18 | AC-5036-01 | 48 | 160.4 | 7699.2 | O
M1-02 | 20 | SO | 484406 | 8 | 2 | C10251 | CUST PU | N45 | B14 | NC | EA | MRO | 01 | 2021-07-25 | 2021-09-02 | AC-4129-B | 78 | 173.11 | 13502.58 | O
M1-02 | 30 | SO | 482694 | 9 | 0 | C10305 | LTL | 2%10N30 | B14 | E | EA | AERO | 01 | 2022-01-27 | 2022-03-18 | AC-2563-10 | 61 | 66.51 | 4057.11 | O
M1-02 | 20 | SO | 481318 | 5 | 0 | C10940 | UPS GND | N30 | B11 | E | EA | MRO | 02 | 2021-04-18 | 2021-08-22 | AC-6988-03 | 49 | 168.96 | 8279.04 | O
M1-02 | 30 | SO | 483865 | 10 | 2 | C10238 | BEST WAY | N60 | B11 | E | EA | DEF | 01 | 2022-03-16 | 2022-05-01 | AC-3382-02 | 33 | 59.72 | 1970.76 | O
M1-02 | 20 | SO | 488122 | 5 | 1 | C10331 | CUST PU | 2%10N30 | B14 | NC | EA | MRO | 05 | 2021-11-26 | 2022-03-14 | AC-2960-10 | 7 | 117.7 | 823.9 | P
M1-02 | 20 | SO | 482876 | 8 | 2 | C10331 | CUST PU | N45 | B07 | E | EA | AERO | 02 | 2022-03-05 | 2022-04-25 | AC-8198-01 | 71 | 85.18 | 6047.78 | O
M1-02 | 20 | BL | 486295 | 8 | 0 | C10936 | LTL | 2%10N30 | B07 | NC | EA | OEM | 01 | 2021-12-12 | 2022-04-26 | AC-1793-03 | 83 | 177.45 | 14728.35 | O
M1-02 | 30 | SO | 484200 | 4 | 1 | C10251 | CUST PU | N30 | B14 | C | EA | MRO | 02 | 2022-02-19 | 2022-05-08 | AC-8506-A | 11 | 161.1 | 1772.1 | O
M1-02 | 30 | BL | 486871 | 7 | 2 | C10787 | BEST WAY | 2%10N30 | B11 | C | EA | DEF | 01 | 2021-10-07 | 2021-12-02 | AC-7055-B | 74 | 90.5 | 6697 | O
M1-02 | 20 | SO | 486277 | 6 | 3 | C10852 | UPS GND | 2%10N30 | B07 | C | EA | OEM | 05 | 2022-02-11 | 2022-04-09 | AC-6570-05 | 56 | 148.32 | 8305.92 | O
M1-02 | 20 | BL | 480106 | 9 | 3 | C10973 | FDX 2D | 2%10N30 | B11 | E | EA | DEF | 01 | 2022-01-11 | 2022-04-21 | AC-7626-05 | 44 | 108.18 | 4759.92 | O
M1-02 | 20 | SO | 487372 | 12 | 3 | C10746 | CUST PU | N60 | B07 | D | EA | OEM | 01 | 2021-06-20 | 2021-09-18 | AC-8535-05 | 51 | 105.98 | 5404.98 | P
M1-02 | 20 | SO | 488015 | 7 | 1 | C10830 | CUST PU | N45 | B22 | A | EA | OEM | 01 | 2021-08-24 | 2022-01-08 | AC-8535-05 | 48 | 59.29 | 2845.92 | P
M1-02 | 30 | BL | 481834 | 5 | 3 | C10238 | CUST PU | N45 | B14 | NC | EA | AERO | 02 | 2021-04-13 | 2021-07-22 | AC-8370-A | 88 | 117.19 | 10312.72 | O
M1-02 | 30 | SO | 482722 | 5 | 2 | C10461 | LTL | 2%10N30 | B11 | C | EA | AERO | 05 | 2022-03-03 | 2022-04-17 | AC-4590-A | 59 | 43.18 | 2547.62 | O
M1-02 | 30 | SO | 484996 | 7 | 3 | C10758 | LTL | N60 | B22 | D | EA | AERO | 05 | 2022-04-19 | 2022-05-28 | AC-6072-03 | 50 | 112.38 | 5619 | O
M1-02 | 20 | SO | 486290 | 5 | 2 | C10331 | BEST WAY | N30 | B22 | D | EA | OEM | 01 | 2021-12-26 | 2022-04-21 | AC-8544-10 | 91 | 144.36 | 13136.76 | O
M1-02 | 20 | BL | 487453 | 5 | 0 | C10332 | CUST PU | N60 | B22 | D | EA | MRO | 02 | 2021-11-06 | 2022-03-20 | AC-5066-03 | 39 | 138.5 | 5401.5 | P
M1-02 | 20 | SO | 483047 | 1 | 3 | C10589 | LTL | N45 | B22 | D | EA | OEM | 05 | 2022-01-17 | 2022-04-10 | AC-4101-02 | 72 | 112.45 | 8096.4 | O
M1-02 | 20 | BL | 486653 | 11 | 1 | C10238 | UPS GND | N60 | B22 | B | EA | DEF | 02 | 2021-04-26 | 2021-07-16 | AC-4809-A | 84 | 160.36 | 13470.24 | O
M1-02 | 30 | SO | 480559 | 9 | 1 | C10222 | FDX 2D | 2%10N30 | B22 | A | EA | DEF | 05 | 2022-04-20 | 2022-06-05 | AC-6167-B | 34 | 105.3 | 3580.2 | O
M1-02 | 30 | SO | 486499 | 8 | 0 | C10695 | UPS GND | 2%10N30 | B07 | C | EA | MRO | 02 | 2022-01-10 | 2022-03-10 | AC-2300-02 | 17 | 119.12 | 2025.04 | O
M1-02 | 20 | SO | 482670 | 4 | 2 | C10940 | FDX 2D | N30 | B07 | A | EA | AERO | 01 | 2021-12-21 | 2022-04-12 | AC-9564-02 | 53 | 160.29 | 8495.37 | O
M1-02 | 30 | SO | 487808 | 4 | 0 | C10951 | CUST PU | N60 | B07 | D | EA | OEM | 02 | 2021-12-15 | 2022-04-14 | AC-2827-02 | 29 | 169.8 | 4924.2 | P
M1-02 | 30 | BL | 484884 | 6 | 0 | C10455 | LTL | N30 | B11 | D | EA | AERO | 05 | 2022-01-09 | 2022-04-07 | AC-6541-05 | 7 | 63.4 | 443.8 | O
M1-02 | 20 | BL | 481304 | 7 | 1 | C10530 | BEST WAY | N60 | B14 | C | EA | MRO | 02 | 2021-12-28 | 2022-03-31 | AC-2371-A | 53 | 130.25 | 6903.25 | O
M1-02 | 20 | BL | 488539 | 11 | 0 | C10280 | LTL | N60 | B11 | C | EA | MRO | 01 | 2021-12-09 | 2022-04-05 | AC-7108-10 | 42 | 176.99 | 7433.58 | P
M1-02 | 30 | SO | 483540 | 3 | 3 | C10256 | LTL | N30 | B14 | E | EA | AERO | 05 | 2022-02-20 | 2022-05-18 | AC-3999-05 | 67 | 160.93 | 10782.31 | O
M1-02 | 30 | BL | 482306 | 4 | 1 | C10461 | FDX 2D | N60 | B07 | E | EA | DEF | 05 | 2021-07-01 | 2021-08-29 | AC-9159-A | 58 | 133.47 | 7741.26 | O
M1-02 | 20 | SO | 483573 | 5 | 3 | C10746 | FDX 2D | N60 | B22 | NC | EA | OEM | 05 | 2022-01-28 | 2022-05-07 | AC-1704-A | 54 | 124.66 | 6731.64 | O
M1-02 | 30 | SO | 483046 | 12 | 1 | C10420 | CUST PU | 2%10N30 | B07 | E | EA | OEM | 05 | 2021-12-16 | 2022-04-02 | AC-6570-05 | 17 | 94.42 | 1605.14 | O
M1-02 | 30 | BL | 488109 | 2 | 0 | C10456 | FDX 2D | N60 | B11 | NC | EA | AERO | 02 | 2021-03-07 | 2021-06-05 | AC-3912-03 | 26 | 90.35 | 2349.1 | P
M1-02 | 30 | SO | 481801 | 1 | 2 | C10170 | FDX 2D | N60 | B11 | B | EA | AERO | 01 | 2022-02-20 | 2022-04-01 | AC-9448-02 | 20 | 101.35 | 2027 | O
M1-02 | 20 | SO | 482327 | 7 | 0 | C10350 | FDX 2D | 2%10N30 | B22 | NC | EA | DEF | 01 | 2021-04-19 | 2021-07-31 | AC-9473-03 | 59 | 118.54 | 6993.86 | O
M1-02 | 20 | SO | 485094 | 3 | 0 | C10331 | BEST WAY | N60 | B07 | A | EA | MRO | 05 | 2021-11-25 | 2022-03-26 | AC-8929-A | 87 | 129.05 | 11227.35 | O
M1-02 | 20 | SO | 483342 | 6 | 0 | C10461 | CUST PU | N60 | B14 | B | EA | DEF | 01 | 2022-01-15 | 2022-05-17 | AC-5791-B | 48 | 100.58 | 4827.84 | O
M1-02 | 30 | SO | 485564 | 5 | 1 | C10756 | FDX 2D | 2%10N30 | B07 | B | EA | MRO | 02 | 2022-03-31 | 2022-05-26 | AC-3456-B | 42 | 51.39 | 2158.38 | O
M1-02 | 20 | SO | 484522 | 2 | 0 | C10940 | LTL | 2%10N30 | B11 | E | EA | DEF | 01 | 2022-03-07 | 2022-04-20 | AC-3356-03 | 11 | 60.82 | 669.02 | O
M1-02 | 30 | SO | 481490 | 3 | 2 | C10806 | UPS GND | N60 | B07 | D | EA | OEM | 01 | 2021-06-21 | 2021-09-26 | AC-1141-02 | 67 | 92.17 | 6175.39 | O
M1-02 | 20 | BL | 480636 | 1 | 1 | C10251 | LTL | N60 | B07 | E | EA | DEF | 01 | 2022-02-04 | 2022-04-01 | AC-7586-02 | 41 | 58.13 | 2383.33 | O
M1-02 | 30 | SO | 481994 | 7 | 0 | C10746 | UPS GND | N60 | B07 | D | EA | OEM | 02 | 2022-02-26 | 2022-04-26 | AC-7973-10 | 39 | 109.69 | 4277.91 | O
M1-02 | 20 | SO | 489280 | 5 | 2 | C10385 | LTL | N60 | B11 | A | EA | OEM | 01 | 2022-01-20 | 2022-05-05 | AC-4830-03 | 18 | 126.39 | 2275.02 | P
M1-02 | 30 | SO | 480773 | 5 | 0 | C10186 | BEST WAY | 2%10N30 | B07 | A | EA | OEM | 01 | 2021-03-12 | 2021-06-04 | AC-8336-B | 84 | 153.49 | 12893.16 | O
M1-02 | 30 | BL | 480137 | 6 | 1 | C10420 | LTL | N45 | B07 | B | EA | OEM | 05 | 2022-02-10 | 2022-04-20 | AC-6595-01 | 80 | 107.3 | 8584 | O
M1-02 | 30 | SO | 481944 | 6 | 2 | C10756 | LTL | N30 | B14 | E | EA | OEM | 02 | 2021-12-14 | 2022-04-09 | AC-8260-A | 29 | 47.79 | 1385.91 | O
M1-02 | 20 | BL | 486032 | 5 | 2 | C10900 | UPS GND | N60 | B07 | NC | EA | MRO | 05 | 2022-03-10 | 2022-05-02 | AC-2645-01 | 99 | 81.26 | 8044.74 | O
M1-02 | 20 | SO | 481899 | 8 | 0 | C10900 | LTL | N60 | B22 | E | EA | MRO | 05 | 2022-03-30 | 2022-05-30 | AC-9725-A | 17 | 85.92 | 1460.64 | O
M1-02 | 20 | SO | 483197 | 7 | 0 | C10706 | CUST PU | N60 | B14 | B | EA | DEF | 02 | 2022-02-11 | 2022-06-06 | AC-3693-10 | 57 | 79.07 | 4506.99 | O
M1-02 | 20 | SO | 486714 | 6 | 1 | C10525 | CUST PU | N30 | B22 | A | EA | OEM | 05 | 2021-02-21 | 2021-05-30 | AC-4398-03 | 5 | 56.24 | 281.2 | O
M1-02 | 30 | SO | 489503 | 6 | 2 | C10436 | UPS GND | N60 | B07 | E | EA | OEM | 05 | 2021-05-03 | 2021-06-21 | AC-6713-10 | 35 | 98.93 | 3462.55 | P
M1-02 | 30 | SO | 485771 | 1 | 2 | C10186 | BEST WAY | N30 | B14 | D | EA | AERO | 02 | 2022-01-13 | 2022-03-21 | AC-3002-03 | 89 | 149.17 | 13276.13 | O
M1-02 | 20 | BL | 486091 | 7 | 0 | C10249 | FDX 2D | N45 | B07 | NC | EA | AERO | 05 | 2021-08-30 | 2022-01-01 | AC-8516-10 | 32 | 169.52 | 5424.64 | O
M1-02 | 20 | SO | 483193 | 4 | 2 | C10966 | BEST WAY | 2%10N30 | B07 | NC | EA | OEM | 05 | 2022-01-13 | 2022-03-23 | AC-7789-05 | 77 | 98.35 | 7572.95 | O
M1-02 | 20 | SO | 483763 | 4 | 2 | C10321 | LTL | N45 | B07 | C | EA | DEF | 02 | 2022-01-24 | 2022-06-06 | AC-1210-B | 98 | 79.42 | 7783.16 | O
M1-02 | 20 | SO | 487248 | 7 | 3 | C10222 | FDX 2D | N45 | B07 | C | EA | OEM | 05 | 2022-02-12 | 2022-05-25 | AC-4101-02 | 31 | 173.15 | 5367.65 | O
M1-02 | 20 | SO | 486432 | 1 | 1 | C10455 | CUST PU | N45 | B14 | A | EA | DEF | 01 | 2021-12-21 | 2022-03-01 | AC-7784-01 | 28 | 73.06 | 2045.68 | O
M1-02 | 20 | BL | 480465 | 8 | 0 | C10264 | BEST WAY | N30 | B14 | D | EA | MRO | 05 | 2022-03-26 | 2022-05-18 | AC-9161-B | 75 | 114.7 | 8602.5 | O
M1-02 | 20 | SO | 483500 | 5 | 3 | C10973 | UPS GND | N45 | B11 | D | EA | AERO | 05 | 2021-09-30 | 2021-11-08 | AC-6469-10 | 46 | 158.9 | 7309.4 | O
M1-02 | 30 | BL | 488530 | 4 | 1 | C10273 | BEST WAY | N30 | B11 | A | EA | DEF | 01 | 2021-12-01 | 2022-04-09 | AC-5085-05 | 35 | 47.68 | 1668.8 | P
M1-02 | 30 | SO | 480856 | 10 | 2 | C10321 | UPS GND | N60 | B07 | C | EA | DEF | 02 | 2022-01-10 | 2022-05-15 | AC-3483-B | 79 | 136.28 | 10766.12 | O
M1-02 | 20 | SO | 488676 | 9 | 3 | C10817 | BEST WAY | N60 | B11 | D | EA | OEM | 05 | 2021-02-28 | 2021-07-08 | AC-6102-10 | 41 | 111.55 | 4573.55 | P
M1-02 | 30 | BL | 480241 | 6 | 2 | C10281 | UPS GND | N30 | B07 | B | EA | OEM | 05 | 2021-12-20 | 2022-03-25 | AC-2574-A | 55 | 145.39 | 7996.45 | O
M1-02 | 30 | BL | 486317 | 11 | 3 | C10186 | UPS GND | N30 | B14 | C | EA | OEM | 05 | 2021-04-08 | 2021-08-16 | AC-5952-B | 9 | 123.27 | 1109.43 | O
M1-02 | 20 | SO | 484352 | 2 | 2 | C10756 | BEST WAY | N30 | B11 | NC | EA | DEF | 05 | 2022-02-06 | 2022-06-04 | AC-3937-10 | 59 | 75.84 | 4474.56 | O
M1-02 | 30 | SO | 481811 | 5 | 2 | C10560 | CUST PU | N45 | B22 | B | EA | AERO | 05 | 2022-01-14 | 2022-04-15 | AC-7626-05 | 48 | 94.34 | 4528.32 | O
M1-02 | 30 | SO | 488476 | 5 | 0 | C10420 | BEST WAY | N30 | B07 | A | EA | DEF | 01 | 2021-08-18 | 2021-12-19 | AC-3665-03 | 46 | 105.07 | 4833.22 | P
M1-02 | 20 | SO | 488421 | 12 | 1 | C10461 | LTL | N45 | B07 | NC | EA | OEM | 05 | 2022-02-03 | 2022-03-19 | AC-3151-05 | 58 | 118.59 | 6878.22 | P
M1-02 | 20 | SO | 485127 | 4 | 2 | C10350 | FDX 2D | N45 | B11 | B | EA | MRO | 02 | 2022-02-11 | 2022-05-21 | AC-3764-01 | 11 | 92.07 | 1012.77 | O
M1-02 | 20 | BL | 480181 | 4 | 2 | C10756 | LTL | N60 | B22 | E | EA | OEM | 01 | 2021-06-06 | 2021-09-20 | AC-6106-B | 96 | 75.26 | 7224.96 | O
M1-02 | 20 | SO | 481360 | 3 | 3 | C10544 | BEST WAY | N60 | B22 | NC | EA | DEF | 05 | 2021-04-29 | 2021-07-25 | AC-9858-01 | 41 | 122.16 | 5008.56 | O
M1-02 | 30 | BL | 483799 | 3 | 2 | C10455 | BEST WAY | N45 | B22 | A | EA | DEF | 01 | 2021-07-18 | 2021-09-07 | AC-5537-01 | 31 | 110.87 | 3436.97 | O
M1-02 | 20 | SO | 480008 | 2 | 1 | C10752 | LTL | N60 | B11 | B | EA | MRO | 01 | 2022-01-15 | 2022-04-01 | AC-7955-10 | 23 | 101.99 | 2345.77 | O
M1-02 | 30 | SO | 481563 | 11 | 1 | C10316 | CUST PU | N30 | B14 | C | EA | MRO | 02 | 2022-03-27 | 2022-04-25 | AC-6293-05 | 44 | 81.29 | 3576.76 | O
M1-02 | 20 | BL | 480547 | 6 | 3 | C10186 | FDX 2D | N45 | B14 | E | EA | MRO | 05 | 2021-01-29 | 2021-05-28 | AC-1170-05 | 40 | 99.21 | 3968.4 | O
M1-02 | 30 | SO | 481029 | 5 | 2 | C10860 | LTL | N30 | B14 | C | EA | AERO | 05 | 2022-02-22 | 2022-03-24 | AC-9587-B | 53 | 125.79 | 6666.87 | O
M1-02 | 20 | SO | 487473 | 6 | 1 | C10940 | BEST WAY | 2%10N30 | B11 | A | EA | MRO | 02 | 2021-12-23 | 2022-03-04 | AC-3665-03 | 47 | 132.06 | 6206.82 | P
M1-02 | 30 | SO | 482091 | 5 | 1 | C10526 | FDX 2D | N30 | B22 | A | EA | OEM | 01 | 2021-12-13 | 2022-04-30 | AC-2073-01 | 16 | 158.72 | 2539.52 | O
M1-02 | 30 | SO | 489790 | 10 | 1 | C10280 | BEST WAY | 2%10N30 | B07 | C | EA | MRO | 05 | 2022-02-13 | 2022-04-24 | AC-6078-10 | 26 | 26.13 | 679.38 | P
M1-02 | 30 | SO | 481949 | 7 | 0 | C10973 | FDX 2D | 2%10N30 | B22 | D | EA | AERO | 01 | 2021-12-05 | 2022-04-12 | AC-4457-B | 32 | 93.5 | 2992 | O
M1-02 | 20 | SO | 488939 | 6 | 3 | C10316 | LTL | N45 | B07 | E | EA | DEF | 01 | 2022-01-14 | 2022-04-03 | AC-9720-A | 19 | 66.92 | 1271.48 | P
M1-02 | 20 | BL | 481450 | 4 | 3 | C10936 | FDX 2D | N45 | B11 | D | EA | MRO | 01 | 2022-02-05 | 2022-06-08 | AC-1017-05 | 10 | 88.39 | 883.9 | O
M1-02 | 20 | BL | 481187 | 10 | 3 | C10936 | LTL | N30 | B07 | C | EA | DEF | 02 | 2021-11-24 | 2022-04-12 | AC-6028-B | 35 | 139.85 | 4894.75 | O
M1-02 | 20 | SO | 488955 | 2 | 0 | C10498 | FDX 2D | N30 | B07 | NC | EA | DEF | 05 | 2022-03-20 | 2022-06-07 | AC-5805-10 | 19 | 106.88 | 2030.72 | P
M1-02 | 20 | SO | 488891 | 6 | 0 | C10519 | BEST WAY | N30 | B11 | A | EA | OEM | 02 | 2022-03-12 | 2022-04-17 | AC-9591-03 | 22 | 111.23 | 2447.06 | P
M1-02 | 30 | SO | 487104 | 11 | 0 | C10264 | UPS GND | N30 | B07 | NC | EA | MRO | 02 | 2021-12-12 | 2022-04-25 | AC-7083-B | 94 | 124.61 | 11713.34 | O
M1-02 | 20 | SO | 481157 | 4 | 3 | C10305 | BEST WAY | N45 | B22 | A | EA | AERO | 01 | 2021-09-05 | 2021-11-21 | AC-4924-03 | 67 | 157.09 | 10525.03 | O
M1-02 | 20 | SO | 487764 | 4 | 1 | C10170 | LTL | N45 | B07 | NC | EA | DEF | 05 | 2022-01-31 | 2022-03-25 | AC-3912-03 | 60 | 70.61 | 4236.6 | P
M1-02 | 20 | SO | 481913 | 12 | 3 | C10752 | LTL | N30 | B22 | A | EA | AERO | 05 | 2022-04-01 | 2022-06-08 | AC-1566-10 | 31 | 120.84 | 3746.04 | O
M1-02 | 30 | SO | 482573 | 2 | 2 | C10966 | UPS GND | N30 | B07 | C | EA | OEM | 02 | 2022-03-13 | 2022-05-26 | AC-6008-A | 60 | 131.1 | 7866 | O
M1-02 | 30 | BL | 487326 | 4 | 2 | C10385 | BEST WAY | N45 | B14 | E | EA | MRO | 02 | 2021-12-27 | 2022-03-20 | AC-7160-02 | 80 | 58.44 | 4675.2 | O
M1-02 | 20 | SO | 489312 | 6 | 3 | C10752 | UPS GND | N60 | B07 | D | EA | DEF | 01 | 2022-02-10 | 2022-03-22 | AC-4109-05 | 35 | 159.55 | 5584.25 | P
M1-02 | 30 | BL | 485372 | 4 | 0 | C10170 | BEST WAY | N60 | B14 | NC | EA | DEF | 05 | 2022-01-13 | 2022-04-28 | AC-3529-A | 45 | 44.64 | 2008.8 | O
M1-02 | 20 | SO | 481149 | 10 | 1 | C10568 | UPS GND | N30 | B11 | E | EA | MRO | 02 | 2022-01-12 | 2022-04-24 | AC-7303-05 | 99 | 174.72 | 17297.28 | O
M1-02 | 20 | SO | 483634 | 10 | 3 | C10830 | LTL | N60 | B07 | D | EA | MRO | 05 | 2022-03-23 | 2022-05-25 | AC-2274-A | 23 | 160.35 | 3688.05 | O
M1-02 | 30 | SO | 481503 | 12 | 1 | C10501 | FDX 2D | N30 | B11 | NC | EA | AERO | 02 | 2022-04-17 | 2022-06-10 | AC-7789-05 | 52 | 146.07 | 7595.64 | O
M1-02 | 20 | SO | 482027 | 8 | 3 | C10526 | UPS GND | N45 | B22 | B | EA | AERO | 01 | 2022-03-20 | 2022-05-28 | AC-1557-B | 58 | 65.85 | 3819.3 | O
M1-02 | 30 | SO | 484895 | 10 | 0 | C10316 | UPS GND | N30 | B07 | C | EA | MRO | 01 | 2021-12-17 | 2022-04-19 | AC-7213-10 | 49 | 147.26 | 7215.74 | O
M1-02 | 20 | SO | 484945 | 8 | 1 | C10966 | FDX 2D | 2%10N30 | B11 | NC | EA | AERO | 05 | 2022-04-07 | 2022-05-29 | AC-6029-01 | 40 | 103.01 | 4120.4 | O
M1-02 | 20 | BL | 483328 | 2 | 2 | C10936 | BEST WAY | 2%10N30 | B22 | C | EA | DEF | 05 | 2022-04-20 | 2022-06-10 | AC-4026-03 | 55 | 138.12 | 7596.6 | O
M1-02 | 30 | SO | 480299 | 8 | 2 | C10746 | CUST PU | N60 | B14 | D | EA | MRO | 05 | 2021-11-09 | 2022-03-13 | AC-6076-02 | 97 | 152.75 | 14816.75 | O
M1-02 | 30 | SO | 482148 | 10 | 2 | C10461 | LTL | N60 | B11 | NC | EA | DEF | 02 | 2021-11-11 | 2022-03-27 | AC-8887-A | 34 | 42.89 | 1458.26 | O
M1-02 | 30 | SO | 489802 | 1 | 0 | C10973 | LTL | N30 | B07 | NC | EA | DEF | 05 | 2022-04-06 | 2022-05-19 | AC-8805-01 | 24 | 45.52 | 1092.48 | P
M1-02 | 30 | BL | 481520 | 1 | 0 | C10830 | FDX 2D | N30 | B14 | A | EA | MRO | 01 | 2022-01-14 | 2022-04-01 | AC-3053-03 | 37 | 159.16 | 5888.92 | O
M1-02 | 20 | SO | 480681 | 6 | 1 | C10860 | BEST WAY | N30 | B22 | A | EA | AERO | 01 | 2021-08-05 | 2021-09-21 | AC-5788-A | 17 | 53.17 | 903.89 | O
M1-02 | 20 | SO | 487998 | 4 | 3 | C10589 | UPS GND | 2%10N30 | B14 | B | EA | OEM | 01 | 2021-10-11 | 2022-02-04 | AC-6271-03 | 34 | 70.11 | 2383.74 | P
M1-02 | 30 | BL | 482783 | 7 | 2 | C10824 | CUST PU | N60 | B07 | A | EA | OEM | 02 | 2022-03-18 | 2022-05-10 | AC-7170-02 | 60 | 92.02 | 5521.2 | O
M1-02 | 30 | SO | 480599 | 3 | 3 | C10758 | CUST PU | N30 | B07 | C | EA | MRO | 01 | 2022-02-26 | 2022-04-11 | AC-2075-02 | 46 | 88.48 | 4070.08 | O
M1-02 | 30 | BL | 489352 | 5 | 1 | C10787 | BEST WAY | 2%10N30 | B14 | B | EA | MRO | 02 | 2021-10-26 | 2021-12-27 | AC-7894-02 | 8 | 88.17 | 705.36 | P
M1-02 | 30 | BL | 488560 | 10 | 3 | C10252 | CUST PU | 2%10N30 | B14 | B | EA | DEF | 01 | 2022-04-08 | 2022-05-11 | AC-4215-05 | 56 | 172.86 | 9680.16 | P
M1-02 | 30 | SO | 482067 | 5 | 0 | C10544 | BEST WAY | 2%10N30 | B11 | A | EA | AERO | 02 | 2022-04-19 | 2022-06-06 | AC-8284-10 | 11 | 61.47 | 676.17 | O
M1-02 | 20 | BL | 486671 | 12 | 3 | C10238 | BEST WAY | N45 | B11 | E | EA | MRO | 02 | 2022-03-04 | 2022-04-19 | AC-7801-03 | 11 | 80.09 | 880.99 | O
M1-02 | 30 | SO | 488061 | 10 | 1 | C10498 | UPS GND | N30 | B11 | B | EA | AERO | 01 | 2021-12-23 | 2022-04-15 | AC-9290-02 | 44 | 171.99 | 7567.56 | P
M1-02 | 20 | SO | 482112 | 8 | 1 | C10420 | FDX 2D | N45 | B22 | A | EA | MRO | 01 | 2022-03-26 | 2022-04-28 | AC-6433-01 | 53 | 129.97 | 6888.41 | O
M1-02 | 20 | SO | 483851 | 1 | 3 | C10568 | LTL | N45 | B11 | B | EA | MRO | 01 | 2021-09-14 | 2021-12-10 | AC-9161-B | 44 | 101.3 | 4457.2 | O
M1-02 | 20 | SO | 484478 | 5 | 0 | C10817 | UPS GND | 2%10N30 | B07 | E | EA | AERO | 01 | 2022-04-01 | 2022-05-04 | AC-6205-A | 45 | 65.2 | 2934 | O
M1-02 | 30 | SO | 489533 | 1 | 0 | C10238 | BEST WAY | N45 | B11 | E | EA | AERO | 05 | 2021-12-06 | 2022-04-03 | AC-5120-A | 38 | 61.29 | 2329.02 | P
M1-02 | 20 | BL | 480502 | 7 | 2 | C10377 | UPS GND | N45 | B14 | C | EA | AERO | 01 | 2021-05-11 | 2021-07-29 | AC-4906-02 | 27 | 52.03 | 1404.81 | O
M1-02 | 30 | SO | 488774 | 2 | 0 | C10860 | LTL | 2%10N30 | B22 | D | EA | OEM | 01 | 2021-08-27 | 2021-09-27 | AC-3359-A | 35 | 104.32 | 3651.2 | P
M1-02 | 20 | SO | 486030 | 3 | 0 | C10852 | LTL | N45 | B14 | E | EA | OEM | 01 | 2021-12-20 | 2022-04-09 | AC-8915-05 | 11 | 78.75 | 866.25 | O
M1-02 | 30 | SO | 485587 | 6 | 0 | C10170 | BEST WAY | N45 | B22 | A | EA | MRO | 02 | 2022-03-02 | 2022-05-07 | AC-1894-02 | 51 | 176.83 | 9018.33 | O
M1-02 | 30 | SO | 489772 | 2 | 3 | C10170 | FDX 2D | N30 | B11 | A | EA | AERO | 01 | 2021-11-18 | 2022-03-25 | AC-4600-10 | 19 | 52.06 | 989.14 | P
M1-02 | 20 | SO | 487516 | 3 | 1 | C10830 | UPS GND | N45 | B07 | NC | EA | AERO | 01 | 2021-06-01 | 2021-07-07 | AC-7572-B | 34 | 51.99 | 1767.66 | P
M1-02 | 20 | SO | 488604 | 6 | 3 | C10830 | UPS GND | N30 | B07 | B | EA | DEF | 02 | 2021-12-26 | 2022-04-14 | AC-8508-03 | 57 | 148.69 | 8475.33 | P
M1-02 | 20 | SO | 480065 | 8 | 0 | C10589 | FDX 2D | N60 | B22 | NC | EA | OEM | 01 | 2021-11-14 | 2022-01-14 | AC-3418-01 | 8 | 66.97 | 535.76 | O
M1-02 | 30 | SO | 484849 | 8 | 0 | C10385 | CUST PU | N60 | B22 | D | EA | DEF | 02 | 2022-04-19 | 2022-05-24 | AC-2570-B | 66 | 87.49 | 5774.34 | O
M1-02 | 20 | SO | 487799 | 5 | 1 | C10860 | LTL | N45 | B22 | E | EA | OEM | 02 | 2021-04-29 | 2021-09-11 | AC-5901-A | 59 | 162.31 | 9576.29 | P
M1-02 | 30 | BL | 485192 | 11 | 0 | C10222 | FDX 2D | N45 | B22 | E | EA | DEF | 02 | 2022-02-03 | 2022-04-21 | AC-1740-03 | 53 | 176.04 | 9330.12 | O
M1-02 | 30 | SO | 485970 | 4 | 3 | C10321 | BEST WAY | N30 | B22 | A | EA | AERO | 05 | 2022-02-10 | 2022-05-28 | AC-1084-B | 27 | 148.89 | 4020.03 | O
M1-02 | 20 | SO | 480308 | 9 | 1 | C10256 | CUST PU | N45 | B22 | NC | EA | MRO | 05 | 2021-12-27 | 2022-03-09 | AC-8853-B | 31 | 114.24 | 3541.44 | O
M1-02 | 30 | SO | 480493 | 11 | 2 | C10461 | CUST PU | 2%10N30 | B07 | E | EA | DEF | 02 | 2021-07-04 | 2021-08-30 | AC-8974-05 | 9 | 111.02 | 999.18 | O
M1-02 | 20 | SO | 485795 | 9 | 3 | C10273 | LTL | 2%10N30 | B14 | E | EA | DEF | 02 | 2022-02-10 | 2022-05-15 | AC-8716-B | 82 | 111.53 | 9145.46 | O
M1-02 | 20 | SO | 488850 | 2 | 2 | C10281 | UPS GND | 2%10N30 | B11 | B | EA | AERO | 01 | 2022-01-23 | 2022-04-17 | AC-8865-01 | 31 | 104.9 | 3251.9 | P
M1-02 | 30 | SO | 484026 | 4 | 3 | C10817 | LTL | N60 | B07 | A | EA | MRO | 01 | 2022-01-07 | 2022-04-04 | AC-4550-03 | 13 | 144.4 | 1877.2 | O
M1-02 | 30 | BL | 489664 | 1 | 1 | C10752 | UPS GND | N30 | B22 | B | EA | MRO | 05 | 2022-01-02 | 2022-03-31 | AC-7956-01 | 36 | 112.97 | 4066.92 | P
M1-02 | 30 | BL | 487287 | 4 | 3 | C10756 | CUST PU | 2%10N30 | B14 | A | EA | DEF | 01 | 2022-03-13 | 2022-05-05 | AC-1382-B | 85 | 68.2 | 5797 | O
M1-02 | 20 | BL | 484289 | 12 | 2 | C10249 | CUST PU | N60 | B22 | E | EA | AERO | 01 | 2022-01-08 | 2022-05-07 | AC-1985-05 | 95 | 115.7 | 10991.5 | O
M1-02 | 30 | SO | 485681 | 6 | 0 | C10170 | BEST WAY | N60 | B22 | B | EA | DEF | 01 | 2022-04-06 | 2022-05-20 | AC-1184-02 | 52 | 167.43 | 8706.36 | O
M1-02 | 20 | SO | 483566 | 5 | 3 | C10852 | FDX 2D | N45 | B14 | E | EA | AERO | 05 | 2021-06-02 | 2021-07-15 | AC-9582-10 | 37 | 62.64 | 2317.68 | O
M1-02 | 20 | SO | 481612 | 6 | 3 | C10544 | CUST PU | N30 | B07 | A | EA | MRO | 05 | 2022-01-18 | 2022-04-18 | AC-7714-10 | 35 | 151.99 | 5319.65 | O
M1-02 | 30 | SO | 480197 | 9 | 0 | C10455 | LTL | N30 | B11 | B | EA | MRO | 02 | 2021-10-24 | 2022-01-22 | AC-4358-02 | 91 | 138.3 | 12585.3 | O
M1-02 | 30 | SO | 483876 | 11 | 0 | C10350 | LTL | N30 | B07 | C | EA | AERO | 02 | 2021-10-16 | 2022-02-13 | AC-7355-A | 31 | 57.82 | 1792.42 | O
M1-02 | 30 | SO | 480596 | 2 | 1 | C10950 | BEST WAY | N60 | B22 | E | EA | DEF | 05 | 2022-02-21 | 2022-03-24 | AC-8706-02 | 56 | 50.3 | 2816.8 | O
M1-02 | 20 | SO | 487445 | 1 | 3 | C10327 | LTL | 2%10N30 | B14 | D | EA | OEM | 05 | 2021-12-14 | 2022-03-11 | AC-1570-02 | 58 | 95.67 | 5548.86 | P
M1-02 | 20 | SO | 488499 | 9 | 2 | C10526 | LTL | N60 | B14 | E | EA | OEM | 02 | 2021-03-05 | 2021-07-05 | AC-9141-03 | 32 | 70.47 | 2255.04 | P
M1-02 | 20 | SO | 482019 | 2 | 3 | C10860 | UPS GND | N45 | B11 | B | EA | AERO | 02 | 2021-11-03 | 2022-03-09 | AC-2648-05 | 4 | 163.86 | 655.44 | O
M1-02 | 30 | SO | 480643 | 8 | 3 | C10756 | UPS GND | N45 | B22 | B | EA | OEM | 02 | 2021-12-20 | 2022-04-02 | AC-4095-02 | 82 | 176.3 | 14456.6 | O
M1-02 | 30 | SO | 481438 | 6 | 2 | C10350 | FDX 2D | N45 | B22 | B | EA | OEM | 05 | 2021-12-19 | 2022-03-25 | AC-5841-03 | 39 | 48.89 | 1906.71 | O
M1-02 | 20 | SO | 482678 | 1 | 3 | C10786 | UPS GND | 2%10N30 | B14 | A | EA | AERO | 01 | 2022-04-15 | 2022-06-06 | AC-7483-02 | 5 | 98.16 | 490.8 | O
M1-02 | 30 | BL | 489377 | 6 | 3 | C10852 | FDX 2D | 2%10N30 | B11 | D | EA | AERO | 02 | 2022-04-03 | 2022-05-02 | AC-1891-03 | 35 | 212.89 | 7451.15 | P
M1-02 | 30 | SO | 486437 | 6 | 2 | C10256 | CUST PU | N45 | B14 | NC | EA | OEM | 01 | 2021-12-08 | 2022-04-01 | AC-1514-10 | 40 | 141.82 | 5672.8 | O
M1-02 | 30 | SO | 486457 | 9 | 1 | C10170 | LTL | N30 | B14 | D | EA | OEM | 02 | 2021-06-17 | 2021-07-29 | AC-8853-05 | 27 | 100.15 | 2704.05 | O
M1-02 | 30 | BL | 487230 | 6 | 1 | C10951 | LTL | N30 | B14 | C | EA | AERO | 02 | 2022-02-23 | 2022-05-01 | AC-7743-10 | 80 | 135.99 | 10879.2 | O
M1-02 | 30 | SO | 487127 | 4 | 3 | C10966 | CUST PU | N30 | B07 | NC | EA | DEF | 02 | 2022-04-11 | 2022-05-23 | AC-1789-10 | 73 | 59.71 | 4358.83 | O
M1-02 | 20 | SO | 489342 | 5 | 3 | C10436 | BEST WAY | N60 | B22 | B | EA | AERO | 05 | 2021-10-25 | 2022-01-17 | AC-2168-05 | 3 | 75.9 | 227.7 | P
M1-02 | 20 | BL | 482952 | 7 | 1 | C10321 | UPS GND | N60 | B14 | A | EA | OEM | 01 | 2022-03-21 | 2022-04-18 | AC-6901-10 | 69 | 57.96 | 3999.24 | O
M1-02 | 20 | BL | 483065 | 7 | 3 | C10321 | CUST PU | N60 | B07 | NC | EA | AERO | 02 | 2022-02-14 | 2022-04-19 | AC-6074-10 | 36 | 49.91 | 1796.76 | O
M1-02 | 20 | SO | 484324 | 2 | 0 | C10332 | BEST WAY | N45 | B07 | C | EA | AERO | 05 | 2021-03-16 | 2021-07-24 | AC-1791-05 | 68 | 61.5 | 4182 | O
M1-02 | 30 | BL | 489678 | 9 | 1 | C10238 | CUST PU | N30 | B14 | NC | EA | DEF | 01 | 2021-12-23 | 2022-04-22 | AC-8656-05 | 28 | 173.36 | 4854.08 | P
M1-02 | 30 | SO | 485901 | 4 | 1 | C10249 | CUST PU | 2%10N30 | B14 | A | EA | AERO | 05 | 2022-01-03 | 2022-05-12 | AC-9218-05 | 36 | 167.26 | 6021.36 | O
M1-02 | 30 | SO | 485527 | 6 | 0 | C10860 | BEST WAY | N45 | B07 | NC | EA | MRO | 01 | 2022-02-02 | 2022-03-17 | AC-2073-01 | 48 | 67.11 | 3221.28 | O
M1-02 | 30 | SO | 483947 | 5 | 3 | C10688 | BEST WAY | 2%10N30 | B22 | C | EA | AERO | 05 | 2022-01-09 | 2022-05-24 | AC-2132-B | 42 | 148.81 | 6250.02 | O
M1-02 | 20 | SO | 480437 | 3 | 3 | C10951 | LTL | 2%10N30 | B14 | A | EA | MRO | 01 | 2022-01-06 | 2022-04-04 | AC-5371-10 | 22 | 147.21 | 3238.62 | O
M1-02 | 20 | SO | 489219 | 12 | 3 | C10461 | BEST WAY | N60 | B11 | D | EA | MRO | 05 | 2021-10-19 | 2021-12-08 | AC-3001-01 | 4 | 88.14 | 352.56 | P
M1-02 | 20 | SO | 482412 | 11 | 2 | C10787 | LTL | N45 | B07 | A | EA | DEF | 05 | 2021-12-23 | 2022-05-10 | AC-6295-A | 65 | 170.54 | 11085.1 | O
M1-02 | 30 | BL | 486079 | 4 | 1 | C10327 | UPS GND | N60 | B22 | D | EA | MRO | 05 | 2022-01-12 | 2022-05-12 | AC-9245-A | 19 | 86.84 | 1649.96 | O
M1-02 | 30 | SO | 483427 | 6 | 3 | C10756 | BEST WAY | N60 | B22 | C | EA | OEM | 02 | 2021-06-16 | 2021-07-22 | AC-3156-A | 64 | 152.23 | 9742.72 | O
M1-02 | 20 | SO | 484663 | 7 | 0 | C10525 | BEST WAY | 2%10N30 | B07 | B | EA | MRO | 02 | 2022-02-26 | 2022-06-04 | AC-7135-05 | 88 | 108.5 | 9548 | O
M1-02 | 20 | BL | 489307 | 2 | 1 | C10852 | BEST WAY | N60 | B22 | D | EA | DEF | 05 | 2022-01-20 | 2022-02-18 | AC-1347-B | 6 | 29.94 | 179.64 | P
M1-02 | 20 | BL | 480231 | 12 | 1 | C10950 | BEST WAY | N60 | B14 | E | EA | AERO | 02 | 2022-01-27 | 2022-03-17 | AC-6196-10 | 76 | 144.72 | 10998.72 | O
M1-02 | 30 | SO | 480164 | 4 | 0 | C10936 | LTL | 2%10N30 | B11 | C | EA | DEF | 05 | 2022-01-15 | 2022-03-29 | AC-8571-10 | 38 | 101.67 | 3863.46 | O
M1-02 | 20 | SO | 486661 | 5 | 2 | C10420 | LTL | 2%10N30 | B07 | NC | EA | MRO | 01 | 2021-09-07 | 2021-10-23 | AC-5097-02 | 65 | 62.59 | 4068.35 | O
M1-02 | 30 | BL | 481470 | 11 | 0 | C10568 | CUST PU | N60 | B14 | C | EA | DEF | 05 | 2022-02-25 | 2022-05-28 | AC-1683-10 | 93 | 156.99 | 14600.07 | O
M1-02 | 30 | SO | 483565 | 12 | 0 | C10252 | CUST PU | 2%10N30 | B14 | D | EA | OEM | 02 | 2022-02-02 | 2022-06-10 | AC-6008-A | 25 | 97.77 | 2444.25 | O
M1-02 | 20 | SO | 480836 | 5 | 2 | C10461 | BEST WAY | 2%10N30 | B22 | B | EA | AERO | 01 | 2021-07-11 | 2021-10-26 | AC-4268-A | 47 | 61.17 | 2874.99 | O
M1-02 | 20 | SO | 480150 | 2 | 0 | C10664 | CUST PU | N30 | B14 | NC | EA | DEF | 02 | 2022-02-28 | 2022-05-08 | AC-1565-10 | 28 | 155.98 | 4367.44 | O
M1-02 | 20 | SO | 486746 | 12 | 1 | C10321 | CUST PU | 2%10N30 | B14 | B | EA | OEM | 02 | 2021-12-17 | 2022-04-17 | AC-8462-A | 98 | 177.46 | 17391.08 | O
M1-02 | 20 | SO | 485356 | 4 | 1 | C10530 | CUST PU | 2%10N30 | B07 | D | EA | OEM | 02 | 2021-05-21 | 2021-09-20 | AC-6682-01 | 91 | 123.21 | 11212.11 | O
M1-02 | 30 | SO | 482982 | 6 | 3 | C10455 | LTL | N45 | B11 | B | EA | MRO | 01 | 2022-02-24 | 2022-05-11 | AC-4026-03 | 19 | 155.42 | 2952.98 | O
M1-02 | 20 | BL | 481869 | 12 | 2 | C10852 | BEST WAY | N30 | B22 | NC | EA | MRO | 05 | 2021-07-03 | 2021-08-28 | AC-7586-02 | 69 | 118.97 | 8208.93 | O
M1-02 | 20 | SO | 488619 | 1 | 2 | C10568 | FDX 2D | N60 | B14 | A | EA | DEF | 02 | 2021-11-13 | 2021-12-25 | AC-3060-02 | 43 | 109.53 | 4709.79 | P
M1-02 | 30 | BL | 489487 | 10 | 0 | C10526 | LTL | N30 | B11 | A | EA | OEM | 05 | 2022-01-19 | 2022-03-24 | AC-3196-A | 28 | 89.47 | 2505.16 | P
M1-02 | 20 | BL | 487331 | 4 | 3 | C10664 | LTL | N60 | B11 | D | EA | MRO | 05 | 2022-01-01 | 2022-04-22 | AC-5070-03 | 65 | 137.6 | 8944 | O
M1-02 | 20 | BL | 483000 | 10 | 1 | C10350 | BEST WAY | 2%10N30 | B22 | NC | EA | MRO | 01 | 2021-12-08 | 2022-04-20 | AC-6074-10 | 31 | 103.27 | 3201.37 | O
M1-02 | 30 | BL | 480045 | 10 | 2 | C10695 | CUST PU | 2%10N30 | B14 | A | EA | AERO | 05 | 2021-09-29 | 2022-02-02 | AC-3359-A | 73 | 71.32 | 5206.36 | O
M1-02 | 30 | SO | 489113 | 7 | 1 | C10852 | UPS GND | N60 | B07 | C | EA | MRO | 02 | 2021-06-24 | 2021-08-23 | AC-9458-05 | 39 | 74.75 | 2915.25 | P
M1-02 | 30 | SO | 483017 | 2 | 1 | C10852 | BEST WAY | N45 | B11 | B | EA | OEM | 05 | 2021-04-03 | 2021-07-16 | AC-4992-10 | 23 | 90.96 | 2092.08 | O
M1-02 | 20 | SO | 481557 | 11 | 1 | C10281 | LTL | N30 | B07 | B | EA | OEM | 02 | 2022-02-17 | 2022-04-26 | AC-2467-A | 70 | 102.7 | 7189 | O
M1-02 | 20 | SO | 486880 | 3 | 3 | C10501 | CUST PU | 2%10N30 | B14 | NC | EA | OEM | 05 | 2022-02-27 | 2022-04-09 | AC-7213-10 | 56 | 103.84 | 5815.04 | O
M1-02 | 20 | SO | 487528 | 11 | 2 | C10461 | UPS GND | 2%10N30 | B11 | B | EA | MRO | 05 | 2021-10-21 | 2022-02-07 | AC-7794-A | 36 | 103.02 | 3708.72 | P
M1-02 | 30 | SO | 482990 | 1 | 3 | C10316 | CUST PU | 2%10N30 | B22 | D | EA | OEM | 02 | 2022-02-06 | 2022-06-02 | AC-3047-05 | 40 | 91.82 | 3672.8 | O
M1-02 | 30 | SO | 486941 | 9 | 1 | C10530 | BEST WAY | N45 | B07 | D | EA | AERO | 01 | 2022-02-06 | 2022-03-29 | AC-6707-10 | 43 | 143.33 | 6163.19 | O
M1-02 | 30 | SO | 488784 | 11 | 1 | C10824 | FDX 2D | N45 | B14 | B | EA | OEM | 01 | 2022-02-14 | 2022-04-05 | AC-4873-10 | 19 | 76.81 | 1459.39 | P
M1-02 | 20 | SO | 481896 | 8 | 1 | C10251 | FDX 2D | 2%10N30 | B07 | E | EA | MRO | 02 | 2021-11-17 | 2022-03-16 | AC-8538-10 | 61 | 55.79 | 3403.19 | O
M1-02 | 30 | SO | 481644 | 4 | 3 | C10501 | LTL | N30 | B11 | B | EA | AERO | 05 | 2022-03-18 | 2022-04-28 | AC-6707-10 | 30 | 98.23 | 2946.9 | O
M1-02 | 30 | SO | 484336 | 9 | 1 | C10758 | FDX 2D | N60 | B14 | NC | EA | OEM | 05 | 2021-12-11 | 2022-03-18 | AC-3257-03 | 10 | 100.82 | 1008.2 | O
M1-02 | 30 | SO | 488032 | 7 | 0 | C10251 | LTL | N45 | B11 | NC | EA | AERO | 05 | 2021-11-07 | 2022-03-15 | AC-4597-10 | 39 | 91.76 | 3578.64 | P
M1-02 | 30 | SO | 485652 | 5 | 0 | C10936 | BEST WAY | 2%10N30 | B22 | NC | EA | OEM | 01 | 2021-12-19 | 2022-04-08 | AC-2092-01 | 34 | 140.82 | 4787.88 | O
M1-02 | 20 | SO | 489401 | 10 | 0 | C10530 | FDX 2D | 2%10N30 | B07 | A | EA | AERO | 02 | 2021-12-19 | 2022-04-08 | AC-8653-01 | 24 | 79.82 | 1915.68 | P
M1-02 | 20 | SO | 486481 | 5 | 3 | C10525 | CUST PU | N45 | B14 | NC | EA | AERO | 02 | 2022-01-30 | 2022-04-06 | AC-9382-03 | 25 | 174.33 | 4358.25 | O
M1-02 | 30 | SO | 488167 | 9 | 1 | C10321 | FDX 2D | N60 | B14 | B | EA | AERO | 01 | 2022-01-15 | 2022-04-13 | AC-7062-10 | 13 | 60.42 | 785.46 | P
M1-02 | 20 | SO | 483410 | 11 | 2 | C10350 | FDX 2D | 2%10N30 | B14 | D | EA | MRO | 02 | 2022-01-17 | 2022-02-15 | AC-2308-A | 59 | 53.79 | 3173.61 | O
M1-02 | 30 | SO | 483829 | 8 | 2 | C10758 | CUST PU | N45 | B22 | A | EA | MRO | 05 | 2022-02-28 | 2022-05-23 | AC-3984-10 | 21 | 135.67 | 2849.07 | O
M1-02 | 30 | SO | 488147 | 10 | 3 | C10170 | CUST PU | N45 | B22 | C | EA | OEM | 01 | 2021-12-16 | 2022-03-23 | AC-6792-B | 38 | 85.06 | 3232.28 | P
M1-02 | 30 | SO | 480728 | 10 | 1 | C10377 | UPS GND | N60 | B14 | E | EA | OEM | 01 | 2021-08-07 | 2021-10-17 | AC-3599-02 | 50 | 117.57 | 5878.5 | O
M1-02 | 20 | SO | 486080 | 1 | 2 | C10238 | FDX 2D | N60 | B07 | NC | EA | DEF | 02 | 2022-01-16 | 2022-02-15 | AC-7692-03 | 16 | 141.46 | 2263.36 | O
M1-02 | 20 | SO | 488673 | 5 | 3 | C10211 | FDX 2D | 2%10N30 | B22 | A | EA | MRO | 05 | 2021-03-17 | 2021-06-28 | AC-3665-03 | 46 | 137.39 | 6319.94 | P
M1-02 | 30 | SO | 480483 | 5 | 0 | C10860 | UPS GND | N60 | B22 | D | EA | MRO | 05 | 2021-05-19 | 2021-06-28 | AC-5074-03 | 55 | 141.97 | 7808.35 | O
M1-02 | 30 | SO | 482614 | 11 | 0 | C10752 | CUST PU | N45 | B11 | C | EA | AERO | 02 | 2021-12-11 | 2022-04-03 | AC-5248-03 | 29 | 63.27 | 1834.83 | O
M1-02 | 30 | BL | 487101 | 5 | 3 | C10256 | BEST WAY | N30 | B11 | C | EA | AERO | 01 | 2021-05-21 | 2021-07-26 | AC-5010-A | 92 | 63.04 | 5799.68 | O
M1-02 | 30 | SO | 480784 | 12 | 0 | C10238 | LTL | N45 | B11 | E | EA | AERO | 02 | 2022-01-27 | 2022-05-18 | AC-8050-01 | 56 | 130.54 | 7310.24 | O
M1-02 | 30 | BL | 486953 | 2 | 1 | C10211 | LTL | N60 | B22 | B | EA | OEM | 02 | 2021-12-02 | 2022-03-29 | AC-4992-B | 10 | 56.05 | 560.5 | O
M1-02 | 30 | SO | 484686 | 1 | 3 | C10305 | LTL | N60 | B14 | B | EA | AERO | 01 | 2021-12-02 | 2022-03-15 | AC-7315-05 | 14 | 59.29 | 830.06 | O
M1-02 | 30 | SO | 480172 | 3 | 2 | C10688 | UPS GND | N30 | B22 | A | EA | DEF | 05 | 2022-02-10 | 2022-05-01 | AC-4443-A | 43 | 139.19 | 5985.17 | O
M1-02 | 20 | SO | 485417 | 2 | 0 | C10530 | LTL | N30 | B07 | A | EA | MRO | 05 | 2021-04-22 | 2021-07-20 | AC-1231-05 | 97 | 174.38 | 16914.86 | O
M1-02 | 20 | SO | 485640 | 9 | 3 | C10787 | BEST WAY | N60 | B07 | C | EA | OEM | 05 | 2021-10-10 | 2021-11-28 | AC-5962-02 | 93 | 101.56 | 9445.08 | O
M1-02 | 30 | SO | 486305 | 7 | 3 | C10544 | BEST WAY | N60 | B11 | A | EA | OEM | 05 | 2021-12-18 | 2022-04-24 | AC-6332-B | 42 | 44.71 | 1877.82 | O
M1-02 | 20 | BL | 483710 | 6 | 3 | C10951 | BEST WAY | N45 | B07 | D | EA | AERO | 05 | 2021-12-16 | 2022-05-04 | AC-6076-02 | 84 | 105.43 | 8856.12 | O
M1-02 | 30 | BL | 482061 | 5 | 1 | C10264 | LTL | N60 | B14 | A | EA | DEF | 02 | 2022-03-20 | 2022-05-02 | AC-2072-03 | 54 | 154.45 | 8340.3 | O
M1-02 | 30 | SO | 488631 | 6 | 3 | C10501 | UPS GND | 2%10N30 | B07 | D | EA | OEM | 05 | 2021-11-09 | 2021-12-17 | AC-2364-01 | 20 | 144.57 | 2891.4 | P
M1-02 | 30 | SO | 481407 | 10 | 3 | C10332 | FDX 2D | N60 | B22 | NC | EA | OEM | 05 | 2022-02-18 | 2022-04-14 | AC-5275-10 | 76 | 72.49 | 5509.24 | O
M1-02 | 20 | SO | 482143 | 10 | 0 | C10806 | FDX 2D | N30 | B14 | NC | EA | AERO | 01 | 2021-12-11 | 2022-03-25 | AC-8462-05 | 58 | 123.75 | 7177.5 | O
M1-02 | 20 | SO | 486395 | 8 | 0 | C10385 | UPS GND | N30 | B07 | E | EA | OEM | 05 | 2021-07-22 | 2021-09-08 | AC-7648-01 | 70 | 96.3 | 6741 | O
M1-02 | 20 | SO | 489232 | 6 | 1 | C10170 | BEST WAY | N45 | B11 | C | EA | DEF | 05 | 2022-01-11 | 2022-05-19 | AC-8463-05 | 3 | 56.29 | 168.87 | P
M1-02 | 30 | BL | 482015 | 1 | 2 | C10222 | UPS GND | N45 | B22 | E | EA | OEM | 01 | 2021-12-07 | 2022-03-21 | AC-4992-B | 39 | 103.63 | 4041.57 | O
M1-02 | 30 | SO | 482353 | 1 | 1 | C10758 | LTL | N60 | B14 | E | EA | OEM | 01 | 2022-01-05 | 2022-03-14 | AC-5777-B | 94 | 141.33 | 13285.02 | O
M1-02 | 20 | SO | 480808 | 7 | 3 | C10786 | UPS GND | N45 | B07 | D | EA | AERO | 01 | 2022-01-21 | 2022-05-22 | AC-4443-A | 62 | 89.71 | 5562.02 | O
M1-02 | 20 | SO | 480821 | 2 | 2 | C10806 | UPS GND | N30 | B11 | B | EA | OEM | 02 | 2022-04-23 | 2022-06-07 | AC-1009-10 | 81 | 76.07 | 6161.67 | O
M1-02 | 30 | SO | 482954 | 9 | 1 | C10327 | CUST PU | N60 | B22 | C | EA | MRO | 05 | 2022-03-16 | 2022-05-29 | AC-6074-10 | 23 | 102.85 | 2365.55 | O
M1-02 | 20 | SO | 488713 | 5 | 2 | C10852 | LTL | N60 | B14 | A | EA | OEM | 01 | 2021-03-23 | 2021-08-07 | AC-7108-10 | 41 | 149.6 | 6133.6 | P
M1-02 | 20 | SO | 480532 | 6 | 0 | C10530 | UPS GND | N30 | B07 | D | EA | DEF | 02 | 2022-03-16 | 2022-05-22 | AC-3788-10 | 92 | 146.86 | 13511.12 | O
M1-02 | 20 | BL | 483452 | 11 | 1 | C10461 | CUST PU | N45 | B07 | D | EA | DEF | 05 | 2021-09-02 | 2022-01-20 | AC-7549-05 | 29 | 72.89 | 2113.81 | O
M1-02 | 20 | SO | 486708 | 8 | 3 | C10830 | CUST PU | N45 | B22 | C | EA | AERO | 05 | 2021-10-23 | 2022-03-05 | AC-5291-10 | 74 | 151.04 | 11176.96 | O
M1-02 | 30 | SO | 483837 | 7 | 2 | C10331 | LTL | 2%10N30 | B22 | A | EA | DEF | 05 | 2022-02-19 | 2022-04-28 | AC-9389-03 | 85 | 112.02 | 9521.7 | O
M1-02 | 30 | BL | 483090 | 4 | 2 | C10456 | BEST WAY | 2%10N30 | B11 | C | EA | MRO | 01 | 2022-05-03 | 2022-06-10 | AC-6787-03 | 72 | 161.76 | 11646.72 | O
M1-02 | 20 | SO | 485243 | 12 | 0 | C10456 | CUST PU | N30 | B22 | E | EA | DEF | 02 | 2021-11-14 | 2022-01-11 | AC-9140-01 | 51 | 102.71 | 5238.21 | O
M1-02 | 20 | SO | 486060 | 12 | 2 | C10852 | BEST WAY | N60 | B11 | E | EA | MRO | 01 | 2022-03-08 | 2022-04-19 | AC-6573-05 | 96 | 155.82 | 14958.72 | O
M1-02 | 20 | SO | 480789 | 6 | 3 | C10786 | BEST WAY | N45 | B07 | NC | EA | OEM | 02 | 2022-02-04 | 2022-04-24 | AC-7196-A | 57 | 57.42 | 3272.94 | O
M1-02 | 30 | BL | 487694 | 10 | 0 | C10940 | LTL | N30 | B14 | C | EA | OEM | 01 | 2022-03-22 | 2022-04-28 | AC-2790-10 | 44 | 74.95 | 3297.8 | P
M1-02 | 30 | BL | 483625 | 1 | 2 | C10830 | BEST WAY | 2%10N30 | B22 | C | EA | AERO | 05 | 2022-03-25 | 2022-05-04 | AC-3156-A | 60 | 68.9 | 4134 | O
M1-02 | 30 | SO | 482153 | 2 | 2 | C10525 | CUST PU | N30 | B11 | NC | EA | DEF | 05 | 2021-12-04 | 2022-04-08 | AC-1264-02 | 61 | 58.09 | 3543.49 | O
M1-02 | 20 | SO | 486216 | 12 | 2 | C10786 | LTL | 2%10N30 | B14 | NC | EA | AERO | 05 | 2022-03-05 | 2022-05-18 | AC-8412-03 | 11 | 92.18 | 1013.98 | O
M1-02 | 30 | SO | 487739 | 9 | 1 | C10786 | LTL | N45 | B14 | C | EA | OEM | 02 | 2021-06-17 | 2021-08-28 | AC-8440-03 | 36 | 80.41 | 2894.76 | P
M1-02 | 20 | BL | 484661 | 5 | 2 | C10321 | BEST WAY | 2%10N30 | B11 | E | EA | OEM | 05 | 2022-02-12 | 2022-06-07 | AC-7154-02 | 16 | 137.5 | 2200 | O
M1-02 | 20 | SO | 482582 | 10 | 1 | C10936 | FDX 2D | N45 | B07 | B | EA | AERO | 02 | 2022-02-03 | 2022-03-14 | AC-5951-03 | 36 | 166.54 | 5995.44 | O
M1-02 | 30 | SO | 482564 | 1 | 3 | C10706 | FDX 2D | N30 | B14 | D | EA | AERO | 05 | 2022-04-05 | 2022-05-15 | AC-3682-B | 58 | 129.3 | 7499.4 | O
M1-02 | 20 | BL | 485315 | 8 | 1 | C10752 | UPS GND | 2%10N30 | B14 | D | EA | AERO | 01 | 2022-01-20 | 2022-05-15 | AC-9207-02 | 61 | 168.94 | 10305.34 | O
M1-02 | 20 | SO | 481488 | 7 | 0 | C10786 | FDX 2D | 2%10N30 | B14 | E | EA | OEM | 05 | 2021-12-10 | 2022-03-27 | AC-6381-B | 65 | 103.73 | 6742.45 | O
M1-02 | 20 | SO | 483360 | 8 | 3 | C10252 | UPS GND | N60 | B11 | E | EA | MRO | 01 | 2022-01-24 | 2022-06-09 | AC-2266-05 | 46 | 115.14 | 5296.44 | O
M1-02 | 20 | SO | 482746 | 9 | 0 | C10830 | CUST PU | 2%10N30 | B22 | A | EA | DEF | 02 | 2022-01-25 | 2022-04-02 | AC-7158-02 | 47 | 71.41 | 3356.27 | O
M1-02 | 30 | SO | 480248 | 2 | 3 | C10498 | LTL | N60 | B07 | NC | EA | OEM | 01 | 2021-11-12 | 2022-03-17 | AC-1513-03 | 44 | 50.56 | 2224.64 | O
M1-02 | 30 | SO | 483842 | 2 | 0 | C10752 | CUST PU | 2%10N30 | B22 | C | EA | OEM | 02 | 2022-02-24 | 2022-05-06 | AC-2827-02 | 23 | 117.29 | 2697.67 | O
M1-02 | 20 | SO | 483233 | 7 | 1 | C10519 | FDX 2D | 2%10N30 | B22 | E | EA | DEF | 01 | 2022-03-09 | 2022-05-31 | AC-1632-03 | 20 | 164.71 | 3294.2 | O
M1-02 | 20 | SO | 487993 | 4 | 1 | C10331 | UPS GND | N45 | B07 | B | EA | AERO | 01 | 2022-02-25 | 2022-05-20 | AC-3396-01 | 26 | 71.96 | 1870.96 | P
M1-02 | 20 | SO | 480324 | 7 | 3 | C10436 | CUST PU | 2%10N30 | B11 | NC | EA | MRO | 02 | 2022-04-28 | 2022-06-09 | AC-3945-A | 76 | 103.99 | 7903.24 | O
M1-02 | 30 | BL | 480869 | 4 | 2 | C10252 | BEST WAY | N60 | B14 | NC | EA | MRO | 05 | 2022-01-24 | 2022-05-21 | AC-1789-10 | 5 | 151.13 | 755.65 | O
M1-02 | 20 | SO | 483293 | 3 | 2 | C10589 | UPS GND | N30 | B14 | B | EA | OEM | 01 | 2022-01-31 | 2022-03-17 | AC-1894-02 | 23 | 145.89 | 3355.47 | O
M1-02 | 20 | SO | 484125 | 5 | 1 | C10256 | CUST PU | N30 | B14 | B | EA | MRO | 01 | 2021-05-26 | 2021-08-10 | AC-8083-03 | 61 | 60.05 | 3663.05 | O
M1-02 | 20 | SO | 482778 | 6 | 2 | C10525 | FDX 2D | 2%10N30 | B22 | E | EA | AERO | 05 | 2021-07-26 | 2021-10-28 | AC-8139-02 | 62 | 116.42 | 7218.04 | O
M1-02 | 30 | BL | 481248 | 3 | 3 | C10806 | UPS GND | N60 | B11 | B | EA | OEM | 01 | 2021-06-16 | 2021-08-23 | AC-8675-10 | 17 | 129.48 | 2201.16 | O
M1-02 | 20 | SO | 485643 | 5 | 2 | C10256 | UPS GND | N30 | B14 | B | EA | AERO | 05 | 2021-10-03 | 2021-11-02 | AC-7182-03 | 21 | 110.9 | 2328.9 | O
M1-02 | 30 | SO | 484813 | 2 | 3 | C10332 | BEST WAY | N45 | B07 | A | EA | OEM | 02 | 2022-02-07 | 2022-06-06 | AC-1584-B | 99 | 124.9 | 12365.1 | O
M1-02 | 20 | SO | 481632 | 9 | 3 | C10530 | FDX 2D | N30 | B14 | E | EA | OEM | 05 | 2022-01-02 | 2022-04-05 | AC-2043-B | 93 | 58.4 | 5431.2 | O
M1-02 | 30 | SO | 487213 | 9 | 2 | C10455 | FDX 2D | N30 | B07 | C | EA | AERO | 01 | 2021-07-09 | 2021-11-16 | AC-2677-01 | 82 | 90.27 | 7402.14 | O
M1-02 | 30 | BL | 481600 | 10 | 2 | C10900 | FDX 2D | 2%10N30 | B22 | C | EA | OEM | 01 | 2022-01-24 | 2022-04-30 | AC-6740-03 | 7 | 56.76 | 397.32 | O
M1-02 | 30 | SO | 485642 | 12 | 0 | C10746 | BEST WAY | N60 | B07 | E | EA | DEF | 01 | 2022-03-03 | 2022-05-24 | AC-3055-A | 9 | 105.9 | 953.1 | O
M1-02 | 20 | BL | 485814 | 1 | 2 | C10170 | LTL | N45 | B07 | D | EA | DEF | 02 | 2022-03-16 | 2022-05-22 | AC-2998-A | 51 | 87.48 | 4461.48 | O
M1-02 | 30 | SO | 485151 | 5 | 2 | C10498 | BEST WAY | N45 | B14 | A | EA | MRO | 02 | 2022-03-22 | 2022-06-06 | AC-3107-B | 9 | 43.09 | 387.81 | O
M1-02 | 20 | BL | 480266 | 6 | 2 | C10327 | BEST WAY | N45 | B11 | E | EA | DEF | 02 | 2022-03-24 | 2022-05-15 | AC-8358-03 | 77 | 70.55 | 5432.35 | O
M1-02 | 30 | SO | 481375 | 2 | 1 | C10526 | LTL | N60 | B07 | NC | EA | DEF | 05 | 2022-03-25 | 2022-05-30 | AC-2456-03 | 38 | 115.2 | 4377.6 | O
M1-02 | 30 | SO | 483991 | 4 | 2 | C10530 | FDX 2D | 2%10N30 | B11 | D | EA | MRO | 01 | 2022-03-25 | 2022-05-24 | AC-3944-B | 8 | 108.14 | 865.12 | O
M1-02 | 20 | BL | 481121 | 9 | 3 | C10327 | BEST WAY | 2%10N30 | B14 | D | EA | AERO | 01 | 2022-01-27 | 2022-05-09 | AC-9491-03 | 54 | 49.15 | 2654.1 | O
M1-02 | 30 | SO | 481987 | 5 | 2 | C10501 | BEST WAY | 2%10N30 | B11 | E | EA | DEF | 02 | 2022-02-12 | 2022-04-29 | AC-5061-A | 59 | 151.5 | 8938.5 | O
M1-02 | 20 | SO | 484618 | 9 | 3 | C10385 | BEST WAY | N45 | B14 | C | EA | DEF | 02 | 2021-12-25 | 2022-03-24 | AC-7170-02 | 19 | 163.91 | 3114.29 | O
M1-02 | 30 | SO | 484717 | 3 | 0 | C10332 | BEST WAY | N45 | B22 | A | EA | OEM | 05 | 2022-01-30 | 2022-05-22 | AC-7877-03 | 73 | 98.18 | 7167.14 | O
M1-02 | 30 | SO | 483349 | 12 | 1 | C10830 | BEST WAY | N60 | B07 | E | EA | AERO | 05 | 2021-04-18 | 2021-08-26 | AC-4393-B | 98 | 62.87 | 6161.26 | O
M1-02 | 20 | SO | 483358 | 6 | 0 | C10860 | CUST PU | 2%10N30 | B07 | C | EA | AERO | 01 | 2022-01-20 | 2022-05-08 | AC-6053-01 | 52 | 119.93 | 6236.36 | O
M1-02 | 20 | BL | 488897 | 1 | 2 | C10281 | BEST WAY | N30 | B14 | A | EA | DEF | 05 | 2022-01-10 | 2022-04-14 | AC-8805-01 | 38 | 117.48 | 4464.24 | P
M1-02 | 30 | SO | 480865 | 6 | 0 | C10664 | FDX 2D | 2%10N30 | B07 | E | EA | AERO | 02 | 2022-02-12 | 2022-06-07 | AC-5302-02 | 9 | 99.79 | 898.11 | O
M1-02 | 20 | SO | 480544 | 10 | 1 | C10170 | CUST PU | N60 | B11 | A | EA | OEM | 05 | 2021-10-17 | 2022-01-15 | AC-5035-B | 16 | 113.36 | 1813.76 | O
M1-02 | 20 | BL | 489282 | 7 | 2 | C10501 | CUST PU | 2%10N30 | B22 | E | EA | DEF | 05 | 2022-01-14 | 2022-05-30 | AC-6921-B | 22 | 105.98 | 2331.56 | P
M1-02 | 20 | SO | 480478 | 11 | 1 | C10695 | FDX 2D | 2%10N30 | B14 | B | EA | OEM | 02 | 2022-01-27 | 2022-03-28 | AC-7213-10 | 68 | 110.32 | 7501.76 | O
M1-02 | 20 | SO | 488185 | 2 | 1 | C10436 | BEST WAY | 2%10N30 | B22 | A | EA | MRO | 01 | 2022-03-02 | 2022-04-14 | AC-3755-02 | 37 | 153.55 | 5681.35 | P
M1-02 | 20 | SO | 487885 | 4 | 2 | C10252 | FDX 2D | N45 | B14 | A | EA | DEF | 01 | 2021-11-18 | 2022-01-05 | AC-6702-02 | 6 | 41.45 | 248.7 | P
M1-02 | 20 | SO | 485716 | 1 | 1 | C10758 | CUST PU | N60 | B14 | NC | EA | DEF | 01 | 2021-05-31 | 2021-09-24 | AC-4541-05 | 22 | 85.2 | 1874.4 | O
M1-02 | 30 | SO | 486887 | 2 | 0 | C10525 | CUST PU | 2%10N30 | B22 | E | EA | AERO | 02 | 2022-01-18 | 2022-04-25 | AC-4541-10 | 37 | 161.54 | 5976.98 | O
M1-02 | 20 | SO | 487654 | 10 | 0 | C10817 | UPS GND | N45 | B07 | E | EA | DEF | 02 | 2021-09-29 | 2021-12-21 | AC-1883-02 | 11 | 56.78 | 624.58 | P
M1-02 | 30 | SO | 482195 | 12 | 1 | C10455 | CUST PU | N45 | B07 | A | EA | DEF | 02 | 2021-10-19 | 2022-03-03 | AC-6787-03 | 39 | 110.14 | 4295.46 | O
M1-02 | 30 | SO | 489061 | 4 | 0 | C10530 | BEST WAY | N45 | B22 | A | EA | OEM | 01 | 2021-05-19 | 2021-10-01 | AC-8393-03 | 18 | 103.23 | 1858.14 | P
M1-02 | 30 | SO | 481269 | 5 | 0 | C10817 | UPS GND | 2%10N30 | B14 | C | EA | OEM | 01 | 2022-01-28 | 2022-06-01 | AC-8872-B | 76 | 90.57 | 6883.32 | O
M1-02 | 30 | SO | 489048 | 3 | 0 | C10951 | UPS GND | 2%10N30 | B14 | D | EA | OEM | 02 | 2022-01-06 | 2022-05-23 | AC-6632-01 | 37 | 108.99 | 4032.63 | P
M1-02 | 20 | SO | 483040 | 9 | 1 | C10950 | LTL | N45 | B22 | C | EA | DEF | 02 | 2022-03-14 | 2022-04-26 | AC-2167-03 | 91 | 153.97 | 14011.27 | O
M1-02 | 20 | SO | 484687 | 1 | 0 | C10900 | BEST WAY | 2%10N30 | B11 | E | EA | MRO | 02 | 2022-01-11 | 2022-03-28 | AC-6660-03 | 81 | 131.58 | 10657.98 | O
M1-02 | 30 | SO | 485101 | 4 | 0 | C10787 | BEST WAY | N60 | B22 | NC | EA | DEF | 05 | 2021-11-08 | 2022-01-14 | AC-9767-B | 96 | 60.62 | 5819.52 | O
M1-02 | 30 | SO | 481207 | 1 | 0 | C10256 | LTL | N45 | B14 | E | EA | AERO | 05 | 2022-03-09 | 2022-04-28 | AC-4322-10 | 30 | 81.33 | 2439.9 | O
M1-02 | 20 | SO | 487351 | 2 | 0 | C10568 | UPS GND | N60 | B22 | NC | EA | MRO | 02 | 2021-07-17 | 2021-08-22 | AC-3231-10 | 20 | 93.06 | 1861.2 | O
M1-02 | 20 | BL | 489730 | 3 | 2 | C10664 | CUST PU | 2%10N30 | B22 | A | EA | OEM | 01 | 2022-02-05 | 2022-04-09 | AC-1166-B | 31 | 120.2 | 3726.2 | P
M1-02 | 20 | SO | 481104 | 4 | 3 | C10211 | LTL | N30 | B07 | D | EA | DEF | 02 | 2021-05-30 | 2021-09-12 | AC-9788-B | 82 | 55.12 | 4519.84 | O
M1-02 | 20 | SO | 486324 | 11 | 0 | C10756 | FDX 2D | N60 | B14 | E | EA | MRO | 05 | 2022-01-28 | 2022-04-20 | AC-8706-02 | 98 | 57.15 | 5600.7 | O
M1-02 | 20 | SO | 481366 | 6 | 3 | C10664 | BEST WAY | N60 | B14 | A | EA | AERO | 05 | 2022-04-07 | 2022-05-25 | AC-3924-B | 17 | 143.31 | 2436.27 | O
M1-02 | 30 | SO | 486387 | 12 | 0 | C10222 | FDX 2D | N30 | B11 | D | EA | DEF | 05 | 2022-02-02 | 2022-05-03 | AC-9773-02 | 20 | 63.57 | 1271.4 | O
M1-02 | 30 | SO | 486846 | 9 | 2 | C10706 | BEST WAY | N60 | B07 | D | EA | OEM | 05 | 2022-01-08 | 2022-03-24 | AC-2849-B | 68 | 125.96 | 8565.28 | O
M1-02 | 30 | BL | 487003 | 3 | 1 | C10321 | LTL | 2%10N30 | B22 | E | EA | DEF | 02 | 2021-04-21 | 2021-07-16 | AC-2167-03 | 86 | 171.49 | 14748.14 | O
M1-02 | 20 | SO | 487670 | 4 | 2 | C10695 | FDX 2D | N30 | B22 | C | EA | MRO | 05 | 2021-12-10 | 2022-04-12 | AC-2274-A | 40 | 73.24 | 2929.6 | P
M1-02 | 30 | BL | 485688 | 12 | 0 | C10222 | UPS GND | N30 | B11 | C | EA | AERO | 01 | 2022-02-19 | 2022-04-14 | AC-2349-05 | 17 | 70.33 | 1195.61 | O
M1-02 | 20 | SO | 488494 | 12 | 1 | C10498 | UPS GND | N45 | B14 | E | EA | MRO | 02 | 2021-08-13 | 2021-10-09 | AC-8508-03 | 48 | 113.29 | 5437.92 | P
M1-02 | 20 | SO | 488337 | 2 | 2 | C10420 | CUST PU | N45 | B14 | D | EA | DEF | 05 | 2022-02-02 | 2022-04-17 | AC-5085-05 | 10 | 114.67 | 1146.7 | P
M1-02 | 30 | BL | 487610 | 12 | 3 | C10544 | CUST PU | N60 | B14 | E | EA | AERO | 02 | 2022-01-28 | 2022-04-15 | AC-6827-05 | 17 | 126.4 | 2148.8 | P
M1-02 | 30 | SO | 481554 | 6 | 0 | C10824 | UPS GND | N60 | B14 | E | EA | MRO | 02 | 2022-03-21 | 2022-05-17 | AC-4499-03 | 15 | 66.82 | 1002.3 | O
M1-02 | 30 | SO | 486234 | 1 | 0 | C10252 | LTL | 2%10N30 | B07 | D | EA | MRO | 01 | 2022-02-16 | 2022-05-28 | AC-8183-02 | 11 | 59.84 | 658.24 | O
M1-02 | 20 | BL | 484432 | 6 | 0 | C10589 | LTL | N60 | B11 | C | EA | OEM | 02 | 2021-11-29 | 2022-03-20 | AC-8202-05 | 79 | 97.35 | 7690.65 | O
M1-02 | 20 | SO | 488074 | 1 | 3 | C10456 | BEST WAY | 2%10N30 | B07 | B | EA | MRO | 01 | 2022-03-21 | 2022-05-01 | AC-4690-10 | 55 | 152 | 8360 | P
M1-02 | 30 | SO | 480130 | 4 | 0 | C10436 | FDX 2D | N45 | B14 | D | EA | OEM | 01 | 2022-03-07 | 2022-05-07 | AC-6946-02 | 51 | 175.2 | 8935.2 | O
M1-02 | 20 | BL | 482115 | 1 | 0 | C10746 | LTL | N60 | B07 | B | EA | MRO | 05 | 2021-04-18 | 2021-05-31 | AC-1463-02 | 38 | 115.5 | 4389 | O
M1-02 | 30 | BL | 488595 | 8 | 0 | C10787 | UPS GND | N45 | B07 | D | EA | MRO | 01 | 2021-07-12 | 2021-10-19 | AC-1601-05 | 19 | 98.77 | 1876.63 | P
M1-02 | 30 | BL | 480111 | 3 | 1 | C10281 | LTL | N30 | B11 | B | EA | DEF | 02 | 2022-02-17 | 2022-04-10 | AC-8198-01 | 35 | 137 | 4795 | O
M1-02 | 30 | SO | 482058 | 3 | 1 | C10973 | FDX 2D | 2%10N30 | B14 | NC | EA | AERO | 02 | 2022-03-18 | 2022-05-07 | AC-4104-10 | 100 | 113 | 11300 | O
M1-02 | 30 | SO | 480705 | 5 | 1 | C10264 | UPS GND | N30 | B11 | A | EA | DEF | 01 | 2022-02-06 | 2022-04-01 | AC-2425-B | 89 | 138.29 | 12307.81 | O
M1-02 | 30 | BL | 481457 | 8 | 1 | C10756 | CUST PU | 2%10N30 | B14 | C | EA | AERO | 01 | 2022-02-14 | 2022-04-14 | AC-2073-01 | 74 | 119.17 | 8818.58 | O
M1-02 | 20 | SO | 489120 | 1 | 3 | C10752 | BEST WAY | 2%10N30 | B07 | D | EA | DEF | 05 | 2022-01-02 | 2022-04-09 | AC-8653-01 | 35 | 45.13 | 1579.55 | P
M1-02 | 20 | BL | 488819 | 6 | 0 | C10331 | FDX 2D | 2%10N30 | B07 | NC | EA | DEF | 02 | 2021-08-09 | 2021-10-19 | AC-2827-02 | 5 | 174.59 | 872.95 | P
M1-02 | 20 | SO | 486972 | 7 | 3 | C10830 | CUST PU | N60 | B22 | A | EA | OEM | 01 | 2022-01-31 | 2022-04-16 | AC-6982-05 | 80 | 96.59 | 7727.2 | O
M1-02 | 30 | SO | 486454 | 4 | 1 | C10860 | LTL | N30 | B14 | NC | EA | AERO | 05 | 2022-01-19 | 2022-05-27 | AC-1565-10 | 69 | 61.7 | 4257.3 | O
M1-02 | 30 | SO | 489261 | 6 | 3 | C10786 | CUST PU | N30 | B22 | NC | EA | AERO | 01 | 2021-06-24 | 2021-09-29 | AC-9763-01 | 7 | 89.24 | 624.68 | P
M1-02 | 20 | SO | 489273 | 7 | 3 | C10305 | FDX 2D | N60 | B11 | E | EA | OEM | 05 | 2022-03-24 | 2022-05-12 | AC-4600-10 | 27 | 99.79 | 2694.33 | P
M1-02 | 20 | SO | 487409 | 7 | 2 | C10461 | BEST WAY | 2%10N30 | B22 | NC | EA | OEM | 02 | 2021-02-24 | 2021-06-14 | AC-2415-B | 6 | 126.22 | 757.32 | P
M1-02 | 20 | SO | 480749 | 2 | 2 | C10456 | BEST WAY | N45 | B22 | NC | EA | DEF | 05 | 2022-01-19 | 2022-05-27 | AC-5876-02 | 58 | 158.8 | 9210.4 | O
M1-02 | 30 | SO | 484094 | 3 | 2 | C10940 | CUST PU | N30 | B14 | A | EA | DEF | 01 | 2021-08-25 | 2021-10-20 | AC-3780-A | 5 | 166.24 | 831.2 | O
M1-02 | 30 | BL | 486980 | 11 | 1 | C10281 | UPS GND | N45 | B14 | D | EA | DEF | 05 | 2022-04-23 | 2022-06-01 | AC-7213-10 | 11 | 157.31 | 1730.41 | O
M1-02 | 30 | SO | 485809 | 11 | 0 | C10455 | CUST PU | N30 | B07 | D | EA | OEM | 01 | 2022-01-13 | 2022-05-24 | AC-1651-01 | 61 | 50.19 | 3061.59 | O
M1-02 | 20 | SO | 484477 | 5 | 3 | C10385 | FDX 2D | N45 | B22 | D | EA | DEF | 05 | 2022-03-07 | 2022-05-06 | AC-7103-B | 5 | 175.07 | 875.35 | O
M1-02 | 20 | SO | 488395 | 6 | 0 | C10461 | UPS GND | 2%10N30 | B11 | NC | EA | MRO | 02 | 2021-10-04 | 2022-01-09 | AC-2870-A | 8 | 81.72 | 653.76 | P
M1-02 | 20 | BL | 486496 | 12 | 3 | C10251 | BEST WAY | N60 | B07 | C | EA | OEM | 05 | 2022-01-20 | 2022-05-14 | AC-8345-B | 18 | 78.57 | 1414.26 | O
M1-02 | 20 | SO | 483544 | 2 | 2 | C10530 | BEST WAY | N45 | B11 | E | EA | AERO | 02 | 2022-04-08 | 2022-05-16 | AC-3456-10 | 24 | 105.25 | 2526 | O
M1-02 | 30 | BL | 487817 | 2 | 3 | C10688 | LTL | N45 | B14 | B | EA | DEF | 01 | 2021-03-19 | 2021-07-03 | AC-3287-02 | 44 | 70.61 | 3106.84 | P
M1-02 | 20 | SO | 487800 | 2 | 2 | C10951 | UPS GND | 2%10N30 | B07 | D | EA | AERO | 05 | 2022-01-06 | 2022-03-19 | AC-2960-10 | 16 | 76.56 | 1224.96 | P
M1-02 | 30 | BL | 484418 | 1 | 2 | C10249 | BEST WAY | 2%10N30 | B07 | NC | EA | OEM | 02 | 2021-12-05 | 2022-04-06 | AC-2635-B | 92 | 118.81 | 10930.52 | O
M1-02 | 30 | SO | 482753 | 11 | 0 | C10273 | BEST WAY | 2%10N30 | B11 | NC | EA | AERO | 01 | 2022-02-26 | 2022-06-02 | AC-3920-05 | 35 | 76.86 | 2690.1 | O
M1-02 | 30 | SO | 480477 | 10 | 0 | C10695 | LTL | N30 | B07 | B | EA | AERO | 01 | 2022-02-14 | 2022-05-20 | AC-7784-01 | 75 | 173.87 | 13040.25 | O
M1-02 | 20 | BL | 481937 | 1 | 3 | C10530 | UPS GND | N45 | B11 | E | EA | DEF | 02 | 2022-03-21 | 2022-05-07 | AC-6896-10 | 45 | 144.15 | 6486.75 | O
M1-02 | 30 | BL | 482124 | 3 | 2 | C10211 | CUST PU | N30 | B11 | B | EA | DEF | 02 | 2022-01-14 | 2022-04-03 | AC-3317-B | 61 | 177.64 | 10836.04 | O
M1-02 | 20 | SO | 488869 | 1 | 1 | C10940 | LTL | N45 | B07 | E | EA | DEF | 05 | 2022-02-14 | 2022-05-27 | AC-8100-02 | 25 | 25.85 | 646.25 | P
M1-02 | 30 | SO | 487493 | 10 | 2 | C10688 | FDX 2D | N45 | B14 | E | EA | MRO | 05 | 2021-07-13 | 2021-08-25 | AC-7457-B | 59 | 154.56 | 9119.04 | P
M1-02 | 20 | SO | 485145 | 8 | 0 | C10860 | LTL | 2%10N30 | B11 | B | EA | OEM | 05 | 2021-12-28 | 2022-04-21 | AC-1248-B | 75 | 42.76 | 3207 | O
M1-02 | 20 | BL | 481877 | 7 | 0 | C10321 | BEST WAY | 2%10N30 | B14 | C | EA | OEM | 05 | 2022-03-29 | 2022-05-23 | AC-7973-10 | 27 | 141.97 | 3833.19 | O
M1-02 | 20 | SO | 483407 | 3 | 3 | C10331 | BEST WAY | 2%10N30 | B22 | A | EA | AERO | 05 | 2022-01-09 | 2022-04-02 | AC-3815-B | 79 | 171.32 | 13534.28 | O
M1-02 | 30 | BL | 483705 | 6 | 0 | C10377 | FDX 2D | 2%10N30 | B07 | D | EA | DEF | 02 | 2021-12-31 | 2022-03-11 | AC-7122-03 | 57 | 154.94 | 8831.58 | O
M1-02 | 30 | SO | 485493 | 11 | 3 | C10589 | FDX 2D | N60 | B22 | C | EA | DEF | 05 | 2022-03-31 | 2022-04-28 | AC-1381-05 | 62 | 138.64 | 8595.68 | O
M1-02 | 30 | SO | 486148 | 10 | 2 | C10950 | LTL | N30 | B11 | E | EA | MRO | 02 | 2021-12-06 | 2022-03-19 | AC-5036-01 | 7 | 64.52 | 451.64 | O
M1-02 | 20 | SO | 486762 | 1 | 1 | C10830 | FDX 2D | N60 | B11 | NC | EA | OEM | 05 | 2021-05-28 | 2021-09-14 | AC-2098-10 | 14 | 122.89 | 1720.46 | O
M1-02 | 30 | SO | 487846 | 1 | 2 | C10824 | BEST WAY | N30 | B14 | A | EA | MRO | 05 | 2021-11-20 | 2022-02-19 | AC-7879-05 | 53 | 166.09 | 8802.77 | P
M1-02 | 30 | SO | 485280 | 12 | 0 | C10824 | LTL | N45 | B14 | C | EA | AERO | 05 | 2022-01-06 | 2022-04-16 | AC-8336-B | 9 | 138.84 | 1249.56 | O
M1-02 | 20 | SO | 484062 | 11 | 0 | C10664 | CUST PU | N45 | B07 | NC | EA | AERO | 02 | 2021-03-15 | 2021-06-22 | AC-7801-03 | 56 | 113.99 | 6383.44 | O
M1-02 | 30 | BL | 482809 | 7 | 2 | C10787 | BEST WAY | 2%10N30 | B07 | A | EA | AERO | 05 | 2022-01-05 | 2022-03-17 | AC-8594-B | 93 | 83.83 | 7796.19 | O
M1-02 | 30 | SO | 485520 | 2 | 1 | C10222 | BEST WAY | 2%10N30 | B14 | A | EA | DEF | 01 | 2021-12-19 | 2022-04-17 | AC-1301-B | 31 | 154.05 | 4775.55 | O
M1-02 | 30 | SO | 483602 | 8 | 1 | C10222 | BEST WAY | N60 | B11 | NC | EA | AERO | 05 | 2022-01-10 | 2022-04-26 | AC-8538-03 | 25 | 152.92 | 3823 | O
M1-02 | 30 | BL | 489740 | 6 | 0 | C10752 | CUST PU | N60 | B14 | C | EA | OEM | 05 | 2021-12-28 | 2022-04-17 | AC-3277-05 | 10 | 44.72 | 447.2 | P
M1-02 | 20 | SO | 482596 | 3 | 1 | C10264 | LTL | N30 | B11 | B | EA | AERO | 01 | 2022-01-25 | 2022-04-11 | AC-1321-05 | 19 | 62.9 | 1195.1 | O
M1-02 | 20 | BL | 483163 | 8 | 0 | C10252 | FDX 2D | N30 | B22 | D | EA | OEM | 02 | 2021-12-22 | 2022-05-01 | AC-2139-10 | 47 | 147.48 | 6931.56 | O
M1-02 | 30 | SO | 488514 | 2 | 1 | C10316 | LTL | N30 | B11 | A | EA | AERO | 05 | 2022-01-07 | 2022-03-24 | AC-5066-03 | 12 | 108.83 | 1305.96 | P
M1-02 | 30 | BL | 483010 | 6 | 2 | C10273 | CUST PU | 2%10N30 | B11 | A | EA | AERO | 02 | 2022-03-25 | 2022-06-04 | AC-2693-01 | 57 | 149.66 | 8530.62 | O
M1-02 | 20 | BL | 488921 | 3 | 3 | C10787 | FDX 2D | 2%10N30 | B11 | B | EA | AERO | 05 | 2022-01-02 | 2022-04-29 | AC-5805-10 | 12 | 133.59 | 1603.08 | P
M1-02 | 30 | SO | 489745 | 11 | 1 | C10746 | CUST PU | N60 | B22 | E | EA | AERO | 02 | 2022-04-17 | 2022-05-18 | AC-7956-01 | 6 | 112.93 | 677.58 | P
M1-02 | 30 | BL | 480738 | 1 | 2 | C10222 | BEST WAY | N30 | B11 | A | EA | AERO | 02 | 2022-03-05 | 2022-04-24 | AC-3767-10 | 32 | 102.16 | 3269.12 | O
M1-02 | 30 | SO | 482897 | 11 | 3 | C10170 | CUST PU | N30 | B11 | NC | EA | MRO | 05 | 2022-02-19 | 2022-06-07 | AC-6792-A | 27 | 122.49 | 3307.23 | O
M1-02 | 20 | SO | 487877 | 7 | 0 | C10950 | CUST PU | N45 | B07 | C | EA | AERO | 01 | 2022-01-07 | 2022-05-13 | AC-7457-B | 39 | 87 | 3393 | P
M1-02 | 20 | SO | 482275 | 12 | 1 | C10252 | UPS GND | 2%10N30 | B11 | NC | EA | DEF | 02 | 2021-12-30 | 2022-02-28 | AC-7439-02 | 6 | 66.06 | 396.36 | O
M1-02 | 20 | SO | 480144 | 4 | 0 | C10860 | FDX 2D | N30 | B14 | C | EA | OEM | 05 | 2022-03-19 | 2022-05-10 | AC-2049-05 | 88 | 42.62 | 3750.56 | O
M1-02 | 30 | BL | 483528 | 9 | 3 | C10530 | UPS GND | N45 | B11 | E | EA | AERO | 02 | 2021-05-23 | 2021-09-03 | AC-1254-10 | 12 | 48.59 | 583.08 | O
M1-02 | 30 | SO | 483207 | 5 | 1 | C10589 | UPS GND | N45 | B11 | B | EA | MRO | 02 | 2022-01-24 | 2022-06-04 | AC-2563-10 | 72 | 164.4 | 11836.8 | O
M1-02 | 30 | SO | 489601 | 5 | 3 | C10256 | UPS GND | 2%10N30 | B14 | D | EA | OEM | 02 | 2022-05-06 | 2022-06-10 | AC-4830-03 | 10 | 83.7 | 837 | P
M1-02 | 20 | BL | 485861 | 7 | 1 | C10746 | BEST WAY | N60 | B11 | A | EA | DEF | 02 | 2022-04-27 | 2022-05-30 | AC-3656-02 | 48 | 64.89 | 3114.72 | O
M1-02 | 30 | SO | 486549 | 9 | 0 | C10824 | UPS GND | N60 | B07 | A | EA | AERO | 02 | 2021-09-17 | 2022-01-29 | AC-2266-05 | 26 | 105.31 | 2738.06 | O
M1-02 | 30 | BL | 483658 | 5 | 3 | C10746 | CUST PU | 2%10N30 | B11 | A | EA | AERO | 05 | 2022-01-28 | 2022-03-15 | AC-7613-10 | 26 | 176.96 | 4600.96 | O
M1-02 | 30 | SO | 486155 | 4 | 1 | C10186 | BEST WAY | N60 | B11 | C | EA | AERO | 02 | 2022-01-30 | 2022-05-17 | AC-9168-B | 59 | 177.88 | 10494.92 | O
M1-02 | 30 | SO | 481139 | 1 | 2 | C10321 | CUST PU | N60 | B11 | E | EA | OEM | 01 | 2022-01-08 | 2022-04-05 | AC-2266-05 | 48 | 161.85 | 7768.8 | O
M1-02 | 30 | SO | 485601 | 4 | 0 | C10951 | BEST WAY | N45 | B14 | NC | EA | DEF | 02 | 2022-04-29 | 2022-06-03 | AC-8361-10 | 17 | 121.95 | 2073.15 | O
M1-02 | 30 | BL | 480936 | 6 | 1 | C10936 | FDX 2D | N60 | B11 | D | EA | MRO | 05 | 2022-02-10 | 2022-06-04 | AC-6028-B | 68 | 130.56 | 8878.08 | O
M1-02 | 20 | SO | 487228 | 12 | 2 | C10936 | FDX 2D | N45 | B14 | B | EA | DEF | 02 | 2021-06-20 | 2021-09-25 | AC-6053-01 | 77 | 127.61 | 9825.97 | O
M1-02 | 30 | SO | 487210 | 11 | 0 | C10752 | CUST PU | N60 | B14 | B | EA | DEF | 01 | 2022-03-02 | 2022-05-21 | AC-6169-A | 52 | 126.86 | 6596.72 | O
M1-02 | 30 | SO | 482386 | 9 | 1 | C10455 | CUST PU | N45 | B22 | E | EA | AERO | 02 | 2021-12-26 | 2022-04-14 | AC-1513-03 | 90 | 83.09 | 7478.1 | O
M1-02 | 20 | SO | 481130 | 12 | 1 | C10525 | CUST PU | N45 | B14 | B | EA | MRO | 01 | 2021-05-02 | 2021-09-17 | AC-9295-03 | 91 | 148.33 | 13498.03 | O
M1-02 | 20 | BL | 485887 | 10 | 3 | C10544 | BEST WAY | N60 | B22 | NC | EA | AERO | 01 | 2022-03-05 | 2022-04-04 | AC-6644-03 | 78 | 78.31 | 6108.18 | O
M1-02 | 30 | SO | 487695 | 2 | 1 | C10560 | UPS GND | N45 | B22 | NC | EA | AERO | 05 | 2022-01-01 | 2022-04-19 | AC-8508-03 | 34 | 135.09 | 4593.06 | P
M1-02 | 30 | BL | 485087 | 11 | 2 | C10273 | BEST WAY | 2%10N30 | B07 | NC | EA | MRO | 05 | 2022-02-26 | 2022-06-06 | AC-5275-10 | 39 | 147.5 | 5752.5 | O
M1-02 | 30 | BL | 488809 | 5 | 2 | C10498 | UPS GND | 2%10N30 | B22 | B | EA | MRO | 05 | 2022-02-27 | 2022-06-05 | AC-2960-10 | 57 | 102.04 | 5816.28 | P
M1-02 | 30 | BL | 486852 | 12 | 3 | C10852 | UPS GND | 2%10N30 | B14 | E | EA | AERO | 05 | 2022-01-03 | 2022-05-01 | AC-2214-A | 86 | 61.83 | 5317.38 | O
M1-02 | 20 | BL | 484302 | 7 | 0 | C10377 | LTL | N60 | B22 | B | EA | MRO | 01 | 2021-02-06 | 2021-06-15 | AC-3764-01 | 71 | 72.43 | 5142.53 | O
M1-02 | 30 | SO | 485225 | 10 | 2 | C10940 | CUST PU | N45 | B07 | E | EA | AERO | 02 | 2022-01-18 | 2022-04-03 | AC-2371-A | 56 | 160.86 | 9008.16 | O
M1-02 | 30 | SO | 483260 | 11 | 0 | C10806 | CUST PU | N30 | B14 | B | EA | OEM | 01 | 2022-04-01 | 2022-05-28 | AC-9459-10 | 31 | 176.73 | 5478.63 | O
M1-02 | 30 | SO | 480588 | 5 | 1 | C10900 | FDX 2D | N30 | B14 | A | EA | AERO | 01 | 2021-12-15 | 2022-05-04 | AC-1740-03 | 29 | 165.9 | 4811.1 | O
M1-02 | 20 | SO | 489714 | 10 | 0 | C10758 | FDX 2D | 2%10N30 | B22 | C | EA | OEM | 02 | 2022-03-25 | 2022-06-05 | AC-1060-10 | 23 | 40.4 | 929.2 | P
M1-02 | 20 | SO | 483023 | 7 | 3 | C10316 | BEST WAY | N45 | B11 | B | EA | MRO | 02 | 2022-03-13 | 2022-04-10 | AC-3297-05 | 35 | 132.75 | 4646.25 | O
M1-02 | 20 | SO | 485081 | 4 | 1 | C10498 | BEST WAY | N30 | B11 | E | EA | OEM | 02 | 2021-05-30 | 2021-07-02 | AC-5246-01 | 58 | 143.47 | 8321.26 | O
M1-02 | 20 | SO | 483792 | 8 | 1 | C10940 | CUST PU | N45 | B07 | NC | EA | MRO | 02 | 2021-12-11 | 2022-04-22 | AC-8073-10 | 85 | 61.44 | 5222.4 | O
M1-02 | 20 | BL | 489351 | 3 | 2 | C10436 | LTL | N30 | B22 | D | EA | OEM | 05 | 2021-12-31 | 2022-05-05 | AC-4074-03 | 13 | 135.06 | 1755.78 | P
M1-02 | 20 | SO | 488580 | 8 | 3 | C10544 | LTL | N45 | B07 | A | EA | MRO | 05 | 2021-09-19 | 2022-01-13 | AC-1601-05 | 46 | 89.9 | 4135.4 | P
M1-02 | 30 | SO | 487153 | 8 | 1 | C10501 | BEST WAY | N60 | B22 | NC | EA | DEF | 02 | 2021-06-01 | 2021-09-18 | AC-3597-01 | 73 | 109.86 | 8019.78 | O
M1-02 | 20 | SO | 480475 | 10 | 0 | C10852 | UPS GND | 2%10N30 | B14 | NC | EA | DEF | 02 | 2022-04-01 | 2022-05-20 | AC-4045-B | 27 | 104.06 | 2809.62 | O
M1-02 | 20 | SO | 482839 | 8 | 1 | C10560 | BEST WAY | 2%10N30 | B11 | E | EA | OEM | 01 | 2022-04-11 | 2022-05-12 | AC-2958-B | 62 | 168.75 | 10462.5 | O
M1-02 | 20 | SO | 482103 | 7 | 2 | C10251 | FDX 2D | N45 | B11 | D | EA | OEM | 05 | 2022-01-19 | 2022-05-25 | AC-5260-10 | 83 | 151.29 | 12557.07 | O
M1-02 | 20 | SO | 483911 | 1 | 0 | C10951 | UPS GND | 2%10N30 | B11 | A | EA | AERO | 01 | 2021-04-11 | 2021-06-11 | AC-9875-03 | 57 | 58.1 | 3311.7 | O
M1-02 | 20 | SO | 482262 | 7 | 1 | C10688 | UPS GND | N45 | B14 | D | EA | OEM | 02 | 2021-09-25 | 2021-12-30 | AC-5631-01 | 22 | 105.85 | 2328.7 | O
M1-02 | 20 | SO | 484648 | 4 | 1 | C10222 | FDX 2D | N60 | B22 | A | EA | MRO | 05 | 2021-09-26 | 2021-11-13 | AC-7955-10 | 68 | 88.17 | 5995.56 | O
M1-02 | 30 | SO | 487066 | 11 | 0 | C10966 | LTL | N60 | B07 | B | EA | OEM | 01 | 2022-02-15 | 2022-04-03 | AC-5278-A | 85 | 78.54 | 6675.9 | O
M1-02 | 20 | SO | 488234 | 3 | 2 | C10331 | UPS GND | N45 | B11 | B | EA | MRO | 01 | 2022-02-28 | 2022-05-11 | AC-5066-03 | 55 | 125.33 | 6893.15 | P
M1-02 | 20 | BL | 487676 | 12 | 1 | C10817 | BEST WAY | N30 | B11 | B | EA | DEF | 02 | 2021-03-26 | 2021-07-21 | AC-6019-B | 10 | 157.92 | 1579.2 | P
M1-02 | 30 | SO | 481258 | 12 | 0 | C10377 | UPS GND | 2%10N30 | B22 | E | EA | OEM | 01 | 2022-01-03 | 2022-05-21 | AC-6433-01 | 16 | 81.53 | 1304.48 | O
M1-02 | 20 | SO | 481295 | 7 | 0 | C10316 | CUST PU | N60 | B14 | D | EA | DEF | 05 | 2022-01-26 | 2022-04-19 | AC-2693-01 | 36 | 97.75 | 3519 | O
M1-02 | 30 | SO | 485536 | 5 | 2 | C10860 | CUST PU | 2%10N30 | B22 | D | EA | MRO | 01 | 2021-12-29 | 2022-05-10 | AC-6261-05 | 47 | 86.56 | 4068.32 | O
M1-02 | 20 | BL | 485156 | 10 | 0 | C10756 | CUST PU | 2%10N30 | B07 | D | EA | DEF | 05 | 2022-01-05 | 2022-05-04 | AC-6570-05 | 71 | 72.76 | 5165.96 | O
M1-02 | 20 | SO | 483638 | 5 | 3 | C10589 | LTL | 2%10N30 | B11 | NC | EA | AERO | 01 | 2021-05-06 | 2021-06-08 | AC-8698-10 | 77 | 117.06 | 9013.62 | O
M1-02 | 20 | SO | 482432 | 7 | 3 | C10211 | CUST PU | N45 | B14 | B | EA | DEF | 05 | 2022-03-15 | 2022-05-01 | AC-4065-10 | 58 | 135.51 | 7859.58 | O
M1-02 | 20 | SO | 482454 | 7 | 1 | C10544 | BEST WAY | N30 | B07 | D | EA | OEM | 05 | 2021-12-30 | 2022-04-02 | AC-7626-05 | 51 | 135.13 | 6891.63 | O
M1-02 | 20 | SO | 480213 | 7 | 1 | C10280 | BEST WAY | 2%10N30 | B22 | E | EA | DEF | 05 | 2022-03-19 | 2022-04-17 | AC-5284-02 | 47 | 45.05 | 2117.35 | O
M1-02 | 20 | SO | 485253 | 6 | 3 | C10900 | LTL | N60 | B14 | C | EA | MRO | 01 | 2022-02-22 | 2022-05-18 | AC-8853-B | 43 | 112.2 | 4824.6 | O
M1-02 | 20 | SO | 485916 | 7 | 0 | C10940 | FDX 2D | 2%10N30 | B22 | A | EA | DEF | 01 | 2021-08-09 | 2021-12-08 | AC-1557-B | 72 | 171.71 | 12363.12 | O
M1-02 | 20 | SO | 484396 | 4 | 2 | C10170 | FDX 2D | N60 | B11 | NC | EA | DEF | 05 | 2022-02-11 | 2022-05-04 | AC-3117-02 | 57 | 99.96 | 5697.72 | O
M1-02 | 20 | SO | 481549 | 11 | 1 | C10568 | CUST PU | N30 | B07 | A | EA | AERO | 05 | 2022-02-16 | 2022-05-13 | AC-5838-05 | 57 | 131.3 | 7484.1 | O
M1-02 | 20 | SO | 486361 | 4 | 1 | C10273 | LTL | N45 | B07 | E | EA | AERO | 01 | 2022-03-05 | 2022-05-28 | AC-3538-02 | 15 | 106.77 | 1601.55 | O
M1-02 | 30 | SO | 481114 | 6 | 2 | C10706 | CUST PU | 2%10N30 | B07 | B | EA | MRO | 02 | 2021-08-26 | 2021-11-28 | AC-3181-02 | 36 | 54.97 | 1978.92 | O
M1-02 | 20 | SO | 488262 | 6 | 1 | C10238 | FDX 2D | N30 | B22 | E | EA | MRO | 02 | 2021-07-12 | 2021-11-23 | AC-5713-01 | 27 | 149.08 | 4025.16 | P
M1-02 | 30 | SO | 484766 | 5 | 0 | C10273 | UPS GND | N45 | B11 | NC | EA | MRO | 05 | 2021-02-22 | 2021-06-18 | AC-4541-10 | 13 | 85.33 | 1109.29 | O
M1-02 | 30 | SO | 484262 | 6 | 1 | C10456 | LTL | 2%10N30 | B14 | E | EA | AERO | 01 | 2022-02-13 | 2022-06-03 | AC-5302-02 | 37 | 146.66 | 5426.42 | O
M1-02 | 20 | SO | 481690 | 11 | 1 | C10350 | FDX 2D | 2%10N30 | B14 | A | EA | DEF | 01 | 2021-02-09 | 2021-06-20 | AC-6946-02 | 62 | 42.87 | 2657.94 | O
M1-02 | 30 | BL | 484074 | 3 | 0 | C10519 | UPS GND | N30 | B11 | B | EA | MRO | 01 | 2022-02-24 | 2022-04-24 | AC-4001-10 | 5 | 138.33 | 691.65 | O
M1-02 | 30 | SO | 488946 | 7 | 1 | C10544 | LTL | N60 | B22 | B | EA | AERO | 05 | 2021-12-12 | 2022-04-10 | AC-7956-01 | 21 | 113.58 | 2385.18 | P
M1-02 | 30 | SO | 485572 | 7 | 2 | C10327 | FDX 2D | N30 | B14 | NC | EA | OEM | 05 | 2021-03-29 | 2021-07-17 | AC-2081-A | 21 | 130.32 | 2736.72 | O
M1-02 | 30 | SO | 483962 | 4 | 3 | C10249 | CUST PU | N30 | B22 | E | EA | MRO | 01 | 2022-01-12 | 2022-03-30 | AC-8139-02 | 24 | 166.08 | 3985.92 | O
M1-02 | 30 | SO | 485881 | 5 | 0 | C10332 | CUST PU | N60 | B11 | E | EA | DEF | 05 | 2022-03-02 | 2022-05-27 | AC-8956-B | 18 | 134 | 2412 | O
M1-02 | 30 | SO | 481183 | 11 | 2 | C10305 | CUST PU | 2%10N30 | B11 | D | EA | AERO | 01 | 2021-10-05 | 2022-01-05 | AC-5781-02 | 90 | 113.29 | 10196.1 | O
M1-02 | 30 | SO | 482324 | 3 | 2 | C10186 | LTL | N30 | B07 | NC | EA | AERO | 02 | 2022-01-27 | 2022-05-25 | AC-5876-02 | 21 | 108.05 | 2269.05 | O
M1-02 | 30 | SO | 480155 | 4 | 0 | C10951 | UPS GND | N30 | B07 | NC | EA | MRO | 01 | 2021-12-17 | 2022-03-25 | AC-7801-03 | 18 | 44.18 | 795.24 | O
M1-02 | 30 | SO | 487171 | 4 | 1 | C10530 | FDX 2D | N45 | B14 | NC | EA | OEM | 02 | 2022-03-06 | 2022-05-13 | AC-9652-03 | 78 | 153.59 | 11980.02 | O
M1-02 | 20 | SO | 484080 | 6 | 3 | C10251 | CUST PU | N60 | B22 | E | EA | DEF | 01 | 2022-03-24 | 2022-06-03 | AC-1883-02 | 31 | 85.81 | 2660.11 | O
M1-02 | 20 | SO | 482043 | 6 | 0 | C10589 | BEST WAY | N45 | B07 | NC | EA | AERO | 01 | 2022-02-02 | 2022-04-19 | AC-7749-05 | 64 | 128.13 | 8200.32 | O
M1-02 | 30 | SO | 481757 | 9 | 1 | C10327 | FDX 2D | 2%10N30 | B22 | C | EA | OEM | 05 | 2022-02-19 | 2022-03-31 | AC-5415-01 | 27 | 168.03 | 4536.81 | O
M1-02 | 20 | SO | 480958 | 12 | 3 | C10786 | BEST WAY | N30 | B22 | E | EA | AERO | 02 | 2021-07-18 | 2021-08-16 | AC-9458-02 | 9 | 90.88 | 817.92 | O
M1-02 | 20 | BL | 488917 | 7 | 1 | C10498 | UPS GND | 2%10N30 | B07 | C | EA | DEF | 05 | 2021-10-28 | 2021-12-05 | AC-4972-05 | 40 | 130.86 | 5234.4 | P
M1-02 | 30 | SO | 488301 | 6 | 2 | C10746 | FDX 2D | N30 | B07 | D | EA | AERO | 02 | 2022-03-06 | 2022-04-09 | AC-6792-B | 43 | 137.73 | 5922.39 | P
M1-02 | 20 | SO | 485915 | 8 | 3 | C10787 | UPS GND | N30 | B22 | A | EA | DEF | 05 | 2022-03-15 | 2022-05-05 | AC-2133-01 | 16 | 93.81 | 1500.96 | O
M1-02 | 20 | SO | 481401 | 7 | 1 | C10222 | LTL | N60 | B11 | C | EA | DEF | 05 | 2021-11-21 | 2022-03-30 | AC-3055-A | 64 | 85.87 | 5495.68 | O
M1-02 | 20 | BL | 487711 | 12 | 1 | C10377 | FDX 2D | 2%10N30 | B22 | NC | EA | MRO | 02 | 2021-11-28 | 2022-04-12 | AC-4386-01 | 41 | 76.74 | 3146.34 | P
M1-02 | 30 | SO | 485462 | 4 | 2 | C10273 | FDX 2D | N60 | B22 | D | EA | AERO | 05 | 2022-03-04 | 2022-06-05 | AC-4400-10 | 7 | 95.84 | 670.88 | O
M1-02 | 30 | SO | 480351 | 11 | 0 | C10900 | BEST WAY | 2%10N30 | B22 | NC | EA | MRO | 01 | 2022-02-11 | 2022-05-22 | AC-2958-B | 41 | 64.57 | 2647.37 | O
M1-02 | 30 | SO | 487614 | 8 | 1 | C10568 | UPS GND | N30 | B22 | E | EA | DEF | 05 | 2021-10-27 | 2022-01-05 | AC-4873-10 | 38 | 58.4 | 2219.2 | P
M1-02 | 20 | SO | 480112 | 11 | 3 | C10385 | CUST PU | N60 | B11 | D | EA | DEF | 05 | 2021-08-14 | 2021-11-10 | AC-6891-02 | 38 | 139.47 | 5299.86 | O
M1-02 | 30 | BL | 488903 | 9 | 1 | C10211 | CUST PU | N45 | B07 | D | EA | MRO | 02 | 2021-06-25 | 2021-10-10 | AC-6670-10 | 19 | 59.52 | 1130.88 | P
M1-02 | 30 | SO | 484975 | 11 | 2 | C10256 | FDX 2D | 2%10N30 | B11 | A | EA | AERO | 02 | 2022-02-15 | 2022-04-27 | AC-6792-A | 16 | 44.38 | 710.08 | O
M1-02 | 30 | BL | 487905 | 1 | 3 | C10455 | BEST WAY | 2%10N30 | B22 | B | EA | MRO | 01 | 2021-11-07 | 2022-01-28 | AC-8440-03 | 6 | 74.71 | 448.26 | P
M1-02 | 20 | SO | 482145 | 6 | 2 | C10852 | CUST PU | N45 | B22 | NC | EA | OEM | 05 | 2022-02-13 | 2022-05-19 | AC-5998-05 | 40 | 52.38 | 2095.2 | O
M1-02 | 20 | BL | 489644 | 7 | 2 | C10525 | UPS GND | N30 | B22 | E | EA | OEM | 02 | 2022-01-08 | 2022-05-28 | AC-9720-A | 37 | 62.02 | 2294.74 | P
M1-02 | 30 | BL | 488102 | 8 | 2 | C10966 | BEST WAY | N30 | B07 | D | EA | MRO | 01 | 2022-02-01 | 2022-04-20 | AC-3231-10 | 37 | 152.8 | 5653.6 | P
M1-02 | 30 | SO | 484856 | 8 | 2 | C10455 | FDX 2D | N60 | B07 | NC | EA | AERO | 02 | 2021-12-17 | 2022-03-13 | AC-6281-10 | 35 | 52.85 | 1849.75 | O
M1-02 | 20 | SO | 485202 | 6 | 3 | C10461 | BEST WAY | 2%10N30 | B14 | E | EA | MRO | 05 | 2022-03-30 | 2022-05-13 | AC-1140-01 | 10 | 98.71 | 987.1 | O
M1-02 | 30 | BL | 486523 | 2 | 3 | C10787 | FDX 2D | N45 | B22 | E | EA | DEF | 02 | 2021-07-04 | 2021-08-02 | AC-2958-B | 72 | 70.03 | 5042.16 | O
M1-02 | 30 | SO | 484793 | 6 | 0 | C10331 | CUST PU | N45 | B14 | E | EA | AERO | 01 | 2021-02-21 | 2021-06-07 | AC-5841-03 | 11 | 134.37 | 1478.07 | O
M1-02 | 20 | SO | 486618 | 2 | 0 | C10280 | BEST WAY | N60 | B07 | B | EA | MRO | 01 | 2022-02-23 | 2022-06-05 | AC-7170-B | 66 | 55.34 | 3652.44 | O
M1-02 | 30 | SO | 482004 | 1 | 2 | C10281 | LTL | N45 | B22 | D | EA | AERO | 02 | 2022-03-15 | 2022-05-22 | AC-6691-B | 52 | 151.82 | 7894.64 | O
M1-02 | 30 | SO | 488398 | 6 | 1 | C10385 | CUST PU | 2%10N30 | B07 | B | EA | OEM | 02 | 2022-01-03 | 2022-05-11 | AC-3287-02 | 14 | 107.21 | 1500.94 | P
M1-02 | 30 | SO | 487092 | 2 | 1 | C10860 | BEST WAY | N30 | B22 | D | EA | OEM | 01 | 2022-03-08 | 2022-05-12 | AC-7785-01 | 83 | 175.45 | 14562.35 | O
M1-02 | 30 | BL | 487907 | 12 | 1 | C10973 | CUST PU | 2%10N30 | B22 | C | EA | AERO | 01 | 2021-10-29 | 2021-12-23 | AC-4082-10 | 15 | 116.08 | 1741.2 | P
M1-02 | 30 | SO | 486383 | 8 | 0 | C10824 | LTL | N45 | B11 | C | EA | DEF | 01 | 2022-04-03 | 2022-05-10 | AC-3287-02 | 12 | 81.66 | 979.92 | O
M1-02 | 30 | SO | 482743 | 11 | 1 | C10688 | FDX 2D | 2%10N30 | B07 | C | EA | OEM | 01 | 2021-12-22 | 2022-04-09 | AC-2364-01 | 66 | 166.53 | 10990.98 | O
M1-02 | 30 | BL | 484445 | 5 | 1 | C10966 | LTL | 2%10N30 | B07 | E | EA | OEM | 02 | 2022-02-18 | 2022-04-15 | AC-2723-03 | 59 | 48.39 | 2855.01 | O
M1-02 | 30 | BL | 486298 | 5 | 1 | C10966 | FDX 2D | N60 | B11 | NC | EA | MRO | 02 | 2022-02-06 | 2022-05-17 | AC-5526-A | 99 | 59.8 | 5920.2 | O
M1-02 | 20 | SO | 489721 | 5 | 1 | C10525 | LTL | N60 | B07 | B | EA | MRO | 01 | 2021-05-08 | 2021-07-06 | AC-6604-01 | 5 | 59.49 | 297.45 | P
M1-02 | 30 | BL | 486685 | 3 | 1 | C10498 | FDX 2D | 2%10N30 | B07 | C | EA | OEM | 05 | 2022-02-15 | 2022-05-11 | AC-6487-02 | 69 | 154.37 | 10651.53 | O
M1-02 | 30 | SO | 481085 | 4 | 2 | C10222 | CUST PU | N45 | B14 | D | EA | AERO | 02 | 2022-04-13 | 2022-05-24 | AC-8716-B | 34 | 176.62 | 6005.08 | O
M1-02 | 20 | BL | 489065 | 5 | 0 | C10752 | FDX 2D | N60 | B22 | A | EA | OEM | 02 | 2022-03-08 | 2022-04-05 | AC-4600-10 | 11 | 120.33 | 1323.63 | P
M1-02 | 30 | SO | 489003 | 11 | 0 | C10589 | LTL | N30 | B11 | NC | EA | DEF | 05 | 2022-02-08 | 2022-05-11 | AC-2250-05 | 27 | 110.26 | 2977.02 | P
M1-02 | 20 | SO | 485412 | 7 | 3 | C10560 | LTL | N60 | B14 | C | EA | AERO | 01 | 2021-04-13 | 2021-08-12 | AC-8361-10 | 12 | 111.68 | 1340.16 | O
M1-02 | 30 | SO | 481343 | 11 | 2 | C10525 | BEST WAY | N30 | B14 | A | EA | DEF | 02 | 2022-01-19 | 2022-06-07 | AC-2755-05 | 90 | 172.61 | 15534.9 | O
M1-02 | 20 | SO | 485657 | 2 | 2 | C10589 | CUST PU | 2%10N30 | B07 | E | EA | MRO | 02 | 2022-02-17 | 2022-04-08 | AC-7613-10 | 63 | 110.57 | 6965.91 | O
M1-02 | 30 | BL | 480032 | 1 | 2 | C10525 | LTL | N30 | B11 | NC | EA | DEF | 01 | 2021-09-23 | 2022-02-02 | AC-9815-05 | 6 | 46.55 | 279.3 | O
M1-02 | 30 | SO | 481825 | 2 | 1 | C10211 | BEST WAY | N60 | B07 | E | EA | DEF | 05 | 2022-02-23 | 2022-06-06 | AC-9397-10 | 57 | 86.39 | 4924.23 | O
M1-02 | 20 | SO | 489783 | 3 | 2 | C10966 | BEST WAY | 2%10N30 | B22 | B | EA | DEF | 05 | 2021-12-27 | 2022-04-05 | AC-4777-10 | 21 | 100.91 | 2119.11 | P
M1-02 | 20 | SO | 484022 | 11 | 3 | C10966 | BEST WAY | 2%10N30 | B22 | A | EA | MRO | 01 | 2021-05-25 | 2021-07-08 | AC-7788-A | 99 | 111.84 | 11072.16 | O
M1-02 | 30 | SO | 489290 | 7 | 1 | C10249 | BEST WAY | N45 | B11 | C | EA | AERO | 01 | 2022-01-20 | 2022-04-15 | AC-3196-A | 38 | 139.46 | 5299.48 | P
M1-02 | 30 | SO | 481534 | 6 | 3 | C10746 | CUST PU | N60 | B22 | C | EA | DEF | 02 | 2022-04-17 | 2022-05-23 | AC-9292-01 | 36 | 73.25 | 2637 | O
M1-02 | 20 | BL | 480730 | 5 | 3 | C10436 | LTL | N45 | B14 | NC | EA | MRO | 01 | 2022-01-10 | 2022-05-29 | AC-4936-01 | 83 | 46.59 | 3866.97 | O
M1-02 | 30 | SO | 484930 | 3 | 0 | C10525 | CUST PU | 2%10N30 | B11 | E | EA | OEM | 01 | 2022-02-17 | 2022-03-20 | AC-8703-B | 83 | 86.72 | 7197.76 | O
M1-02 | 30 | SO | 481333 | 8 | 0 | C10664 | UPS GND | N60 | B22 | A | EA | OEM | 01 | 2022-02-02 | 2022-06-07 | AC-6482-03 | 17 | 145.6 | 2475.2 | O
M1-02 | 30 | SO | 483935 | 10 | 3 | C10211 | FDX 2D | N45 | B07 | B | EA | DEF | 02 | 2021-05-14 | 2021-07-23 | AC-8336-B | 35 | 113.27 | 3964.45 | O
M1-02 | 30 | SO | 480036 | 2 | 0 | C10940 | LTL | N45 | B11 | A | EA | AERO | 05 | 2022-01-15 | 2022-05-21 | AC-4065-10 | 76 | 148.93 | 11318.68 | O
M1-02 | 30 | SO | 488361 | 8 | 2 | C10461 | FDX 2D | 2%10N30 | B22 | A | EA | OEM | 01 | 2021-09-23 | 2022-02-10 | AC-8194-03 | 40 | 166.93 | 6677.2 | P
M1-02 | 20 | BL | 484853 | 10 | 3 | C10321 | BEST WAY | N60 | B07 | D | EA | OEM | 05 | 2021-12-14 | 2022-04-21 | AC-1310-B | 8 | 66.78 | 534.24 | O
M1-02 | 20 | SO | 486824 | 6 | 3 | C10498 | CUST PU | N45 | B14 | E | EA | AERO | 05 | 2021-03-06 | 2021-06-13 | AC-5035-B | 25 | 137.26 | 3431.5 | O
M1-02 | 30 | SO | 487196 | 9 | 1 | C10746 | LTL | N60 | B07 | A | EA | AERO | 05 | 2022-02-14 | 2022-06-07 | AC-3815-B | 40 | 100.71 | 4028.4 | O
M1-02 | 20 | SO | 481186 | 3 | 2 | C10940 | BEST WAY | 2%10N30 | B22 | NC | EA | MRO | 02 | 2022-01-10 | 2022-04-20 | AC-1637-A | 30 | 142.79 | 4283.7 | O
M1-02 | 30 | SO | 481782 | 1 | 3 | C10756 | FDX 2D | N45 | B22 | B | EA | OEM | 02 | 2021-06-18 | 2021-08-30 | AC-2755-05 | 100 | 101.33 | 10133 | O
M1-02 | 20 | SO | 482487 | 7 | 3 | C10170 | FDX 2D | 2%10N30 | B22 | E | EA | MRO | 01 | 2022-02-25 | 2022-04-02 | AC-2334-02 | 69 | 42.31 | 2919.39 | O
M1-02 | 20 | SO | 481571 | 12 | 2 | C10350 | CUST PU | 2%10N30 | B14 | E | EA | MRO | 05 | 2021-10-25 | 2022-01-10 | AC-8579-10 | 58 | 119.76 | 6946.08 | O
M1-02 | 30 | SO | 484222 | 3 | 2 | C10951 | CUST PU | N60 | B07 | B | EA | MRO | 01 | 2022-04-14 | 2022-05-17 | AC-8201-A | 37 | 116.22 | 4300.14 | O
M1-02 | 20 | SO | 480022 | 2 | 3 | C10273 | UPS GND | 2%10N30 | B22 | B | EA | MRO | 02 | 2022-02-07 | 2022-06-07 | AC-1883-02 | 58 | 115.14 | 6678.12 | O
M1-02 | 30 | SO | 487239 | 9 | 2 | C10273 | LTL | N60 | B11 | D | EA | DEF | 01 | 2022-02-10 | 2022-05-25 | AC-2648-05 | 47 | 117.76 | 5534.72 | O
M1-02 | 20 | SO | 487950 | 5 | 2 | C10526 | CUST PU | N60 | B14 | B | EA | DEF | 05 | 2021-04-27 | 2021-07-15 | AC-3675-B | 46 | 165.91 | 7631.86 | P
M1-02 | 20 | SO | 481992 | 5 | 1 | C10249 | CUST PU | N30 | B14 | E | EA | MRO | 05 | 2021-05-31 | 2021-09-23 | AC-9564-02 | 97 | 89.69 | 8699.93 | O
M1-02 | 20 | SO | 480375 | 11 | 0 | C10461 | UPS GND | N45 | B07 | D | EA | OEM | 01 | 2022-02-10 | 2022-05-17 | AC-7743-10 | 90 | 175.35 | 15781.5 | O
M1-02 | 30 | SO | 485270 | 10 | 2 | C10830 | UPS GND | N45 | B14 | D | EA | AERO | 05 | 2021-09-24 | 2021-12-19 | AC-8378-01 | 34 | 162.57 | 5527.38 | O
M1-02 | 30 | SO | 480575 | 9 | 3 | C10530 | FDX 2D | 2%10N30 | B07 | D | EA | MRO | 05 | 2021-12-29 | 2022-05-17 | AC-6691-B | 93 | 52.36 | 4869.48 | O
M1-02 | 30 | BL | 486741 | 1 | 0 | C10973 | FDX 2D | 2%10N30 | B14 | NC | EA | DEF | 01 | 2022-01-09 | 2022-05-18 | AC-8050-01 | 29 | 96.27 | 2791.83 | O
M1-02 | 30 | SO | 486918 | 7 | 3 | C10332 | CUST PU | N30 | B07 | B | EA | OEM | 01 | 2022-01-22 | 2022-04-02 | AC-1382-B | 70 | 127.59 | 8931.3 | O
M1-02 | 20 | SO | 484906 | 2 | 3 | C10461 | BEST WAY | N30 | B11 | C | EA | AERO | 01 | 2021-11-19 | 2022-02-16 | AC-6774-02 | 13 | 80.75 | 1049.75 | O
M1-02 | 30 | SO | 481930 | 3 | 1 | C10806 | UPS GND | N60 | B11 | NC | EA | MRO | 01 | 2021-01-15 | 2021-05-28 | AC-4924-03 | 68 | 144.54 | 9828.72 | O
M1-02 | 20 | SO | 483372 | 6 | 3 | C10211 | FDX 2D | 2%10N30 | B11 | NC | EA | OEM | 01 | 2021-12-01 | 2022-01-25 | AC-9773-02 | 8 | 152.1 | 1216.8 | O
M1-02 | 20 | BL | 482860 | 10 | 3 | C10321 | BEST WAY | N60 | B22 | E | EA | DEF | 02 | 2022-01-22 | 2022-05-29 | AC-8050-01 | 90 | 72.38 | 6514.2 | O
M1-02 | 30 | SO | 482819 | 6 | 2 | C10350 | CUST PU | N60 | B22 | NC | EA | OEM | 01 | 2022-01-26 | 2022-05-29 | AC-1140-01 | 54 | 95.33 | 5147.82 | O
M1-02 | 20 | SO | 483306 | 6 | 0 | C10332 | BEST WAY | N30 | B14 | A | EA | DEF | 01 | 2022-02-03 | 2022-05-06 | AC-9459-10 | 27 | 110.43 | 2981.61 | O
M1-02 | 30 | SO | 485920 | 8 | 2 | C10951 | UPS GND | N45 | B14 | NC | EA | MRO | 05 | 2022-03-02 | 2022-06-02 | AC-4953-10 | 94 | 55.58 | 5224.52 | O
M1-02 | 20 | SO | 480420 | 5 | 3 | C10316 | BEST WAY | N45 | B07 | D | EA | MRO | 02 | 2021-10-29 | 2021-12-09 | AC-2895-B | 8 | 76.76 | 614.08 | O
M1-02 | 30 | BL | 488833 | 11 | 3 | C10281 | LTL | 2%10N30 | B07 | D | EA | DEF | 05 | 2021-12-14 | 2022-03-24 | AC-8665-02 | 4 | 76.56 | 306.24 | P
M1-02 | 20 | BL | 486445 | 4 | 1 | C10498 | BEST WAY | N45 | B11 | B | EA | DEF | 01 | 2022-02-18 | 2022-04-24 | AC-5023-B | 65 | 71.11 | 4622.15 | O
M1-02 | 30 | SO | 486123 | 11 | 1 | C10281 | FDX 2D | N30 | B07 | NC | EA | AERO | 02 | 2021-12-24 | 2022-05-02 | AC-5659-02 | 47 | 162.51 | 7637.97 | O
M1-02 | 30 | SO | 488033 | 1 | 1 | C10252 | UPS GND | N45 | B22 | NC | EA | OEM | 02 | 2021-05-22 | 2021-09-27 | AC-8440-03 | 30 | 79.06 | 2371.8 | P
M1-02 | 20 | SO | 485130 | 10 | 2 | C10824 | BEST WAY | N30 | B22 | A | EA | MRO | 01 | 2022-01-20 | 2022-04-25 | AC-1337-02 | 51 | 104.26 | 5317.26 | O
M1-02 | 20 | SO | 487423 | 7 | 2 | C10273 | CUST PU | 2%10N30 | B14 | C | EA | OEM | 01 | 2021-12-24 | 2022-02-04 | AC-2790-10 | 60 | 137.02 | 8221.2 | P
M1-02 | 20 | BL | 487790 | 1 | 2 | C10786 | CUST PU | N60 | B14 | C | EA | OEM | 05 | 2021-08-23 | 2021-11-28 | AC-8827-A | 49 | 42.73 | 2093.77 | P
M1-02 | 30 | BL | 482890 | 9 | 2 | C10568 | LTL | N60 | B11 | NC | EA | DEF | 02 | 2022-01-23 | 2022-04-27 | AC-2274-A | 55 | 122.83 | 6755.65 | O
M1-02 | 20 | SO | 483928 | 5 | 1 | C10252 | BEST WAY | 2%10N30 | B14 | B | EA | AERO | 01 | 2022-04-03 | 2022-05-19 | AC-1254-10 | 93 | 97.13 | 9033.09 | O
M1-02 | 30 | SO | 483507 | 6 | 3 | C10385 | FDX 2D | N30 | B11 | D | EA | DEF | 01 | 2021-10-28 | 2021-12-04 | AC-3788-10 | 76 | 155.87 | 11846.12 | O
M1-02 | 30 | SO | 485162 | 7 | 3 | C10222 | CUST PU | N45 | B14 | B | EA | DEF | 01 | 2021-12-09 | 2022-04-27 | AC-3014-10 | 37 | 69.83 | 2583.71 | O
M1-02 | 20 | SO | 486970 | 5 | 3 | C10756 | BEST WAY | 2%10N30 | B07 | E | EA | MRO | 01 | 2021-09-28 | 2022-02-14 | AC-4775-03 | 30 | 142.84 | 4285.2 | O
M1-02 | 20 | SO | 484983 | 6 | 3 | C10498 | FDX 2D | N60 | B07 | B | EA | DEF | 01 | 2022-02-02 | 2022-05-31 | AC-4906-02 | 62 | 48.15 | 2985.3 | O
M1-02 | 30 | SO | 489463 | 9 | 1 | C10824 | CUST PU | N30 | B11 | B | EA | MRO | 01 | 2022-03-02 | 2022-05-26 | AC-5805-10 | 39 | 95.58 | 3727.62 | P
M1-02 | 30 | BL | 486478 | 5 | 0 | C10852 | UPS GND | N30 | B07 | B | EA | DEF | 02 | 2022-02-15 | 2022-04-01 | AC-9541-B | 39 | 164.32 | 6408.48 | O
M1-02 | 30 | SO | 484462 | 12 | 3 | C10264 | LTL | N30 | B11 | A | EA | MRO | 02 | 2021-12-08 | 2022-04-15 | AC-3896-05 | 75 | 177.44 | 13308 | O
M1-02 | 30 | BL | 482957 | 8 | 3 | C10519 | BEST WAY | N60 | B11 | A | EA | AERO | 05 | 2022-02-15 | 2022-04-03 | AC-2967-A | 68 | 46.7 | 3175.6 | O
M1-02 | 30 | SO | 488482 | 7 | 2 | C10316 | CUST PU | N60 | B11 | C | EA | DEF | 01 | 2021-08-17 | 2021-09-18 | AC-2415-B | 21 | 86.17 | 1809.57 | P
M1-02 | 20 | SO | 480825 | 11 | 2 | C10211 | UPS GND | N60 | B11 | A | EA | DEF | 02 | 2022-01-20 | 2022-05-28 | AC-5963-02 | 10 | 161.9 | 1619 | O
M1-02 | 20 | SO | 487457 | 6 | 2 | C10900 | FDX 2D | N45 | B22 | NC | EA | DEF | 01 | 2021-05-17 | 2021-09-11 | AC-3929-10 | 46 | 99.93 | 4596.78 | P
M1-02 | 30 | BL | 482877 | 5 | 1 | C10817 | LTL | 2%10N30 | B07 | D | EA | DEF | 02 | 2022-01-22 | 2022-06-05 | AC-2645-01 | 6 | 127.95 | 767.7 | O
M1-02 | 30 | SO | 487663 | 11 | 1 | C10817 | CUST PU | N30 | B22 | D | EA | DEF | 01 | 2022-01-13 | 2022-02-24 | AC-3696-02 | 14 | 46.93 | 657.02 | P
M1-02 | 30 | SO | 489510 | 2 | 0 | C10316 | BEST WAY | N60 | B22 | D | EA | DEF | 01 | 2022-01-06 | 2022-05-16 | AC-9622-10 | 23 | 96.67 | 2223.41 | P
M1-02 | 20 | SO | 480233 | 10 | 2 | C10695 | FDX 2D | N30 | B22 | A | EA | AERO | 02 | 2022-03-12 | 2022-06-02 | AC-5731-10 | 76 | 128.45 | 9762.2 | O
M1-02 | 20 | SO | 482220 | 2 | 3 | C10706 | FDX 2D | N45 | B11 | B | EA | DEF | 01 | 2022-04-04 | 2022-05-20 | AC-3529-A | 41 | 176.57 | 7239.37 | O
M1-02 | 30 | SO | 485696 | 10 | 3 | C10256 | LTL | N30 | B07 | D | EA | AERO | 02 | 2022-01-01 | 2022-05-02 | AC-7405-02 | 28 | 76.97 | 2155.16 | O
M1-02 | 30 | SO | 486103 | 10 | 1 | C10758 | LTL | N45 | B07 | D | EA | OEM | 05 | 2021-11-23 | 2022-03-31 | AC-1409-05 | 12 | 162.81 | 1953.72 | O
M1-02 | 30 | BL | 487360 | 6 | 0 | C10806 | CUST PU | N60 | B22 | A | EA | DEF | 01 | 2021-04-14 | 2021-08-06 | AC-3755-02 | 57 | 77.46 | 4415.22 | P
M1-02 | 30 | SO | 488693 | 2 | 1 | C10251 | CUST PU | N30 | B22 | E | EA | AERO | 01 | 2022-02-21 | 2022-06-08 | AC-8194-03 | 46 | 78.07 | 3591.22 | P
M1-02 | 30 | BL | 489700 | 5 | 3 | C10498 | FDX 2D | 2%10N30 | B14 | D | EA | OEM | 01 | 2021-12-23 | 2022-04-09 | AC-3196-A | 8 | 67.87 | 542.96 | P
M1-02 | 20 | SO | 489391 | 5 | 2 | C10787 | BEST WAY | N30 | B14 | B | EA | OEM | 01 | 2021-07-04 | 2021-09-21 | AC-3592-B | 36 | 85.29 | 3070.44 | P
M1-02 | 30 | BL | 480790 | 7 | 0 | C10560 | FDX 2D | 2%10N30 | B22 | NC | EA | OEM | 05 | 2022-01-11 | 2022-04-29 | AC-2998-A | 28 | 59.48 | 1665.44 | O
M1-02 | 20 | SO | 488194 | 4 | 3 | C10824 | LTL | N60 | B22 | B | EA | MRO | 01 | 2021-12-20 | 2022-04-19 | AC-3755-02 | 14 | 46.58 | 652.12 | P
M1-02 | 30 | SO | 489091 | 8 | 0 | C10824 | LTL | N30 | B11 | NC | EA | AERO | 02 | 2021-08-04 | 2021-12-18 | AC-1392-B | 13 | 31.26 | 406.38 | P
M1-02 | 30 | BL | 488931 | 6 | 0 | C10664 | LTL | 2%10N30 | B14 | NC | EA | AERO | 02 | 2022-02-26 | 2022-05-21 | AC-6713-10 | 14 | 119.87 | 1678.18 | P
M1-02 | 20 | SO | 480555 | 2 | 3 | C10350 | CUST PU | N30 | B11 | B | EA | AERO | 02 | 2022-02-06 | 2022-04-17 | AC-9652-03 | 70 | 42.26 | 2958.2 | O
M1-02 | 30 | SO | 487559 | 5 | 2 | C10786 | FDX 2D | N30 | B22 | D | EA | MRO | 05 | 2022-02-27 | 2022-05-26 | AC-4215-05 | 18 | 68.44 | 1231.92 | P
M1-02 | 30 | BL | 485446 | 12 | 0 | C10950 | LTL | N45 | B11 | D | EA | AERO | 02 | 2021-10-10 | 2022-02-10 | AC-2790-10 | 44 | 149.73 | 6588.12 | O
M1-02 | 30 | SO | 486961 | 2 | 2 | C10526 | CUST PU | N45 | B11 | NC | EA | MRO | 02 | 2021-04-14 | 2021-08-05 | AC-8641-05 | 86 | 171.53 | 14751.58 | O
M1-02 | 20 | SO | 483394 | 8 | 0 | C10498 | UPS GND | 2%10N30 | B14 | D | EA | OEM | 01 | 2022-01-29 | 2022-04-03 | AC-3293-A | 41 | 174.61 | 7159.01 | O
M1-02 | 20 | BL | 488563 | 2 | 1 | C10817 | LTL | N30 | B07 | C | EA | DEF | 05 | 2022-02-17 | 2022-05-08 | AC-2723-03 | 55 | 110.87 | 6097.85 | P
M1-02 | 20 | SO | 488749 | 12 | 3 | C10936 | LTL | 2%10N30 | B07 | B | EA | AERO | 02 | 2021-10-17 | 2021-12-04 | AC-4386-01 | 4 | 127.07 | 508.28 | P
M1-02 | 30 | SO | 480204 | 8 | 3 | C10936 | CUST PU | N30 | B22 | B | EA | MRO | 02 | 2022-02-05 | 2022-03-07 | AC-5537-01 | 4 | 129.08 | 516.32 | O
M1-02 | 20 | SO | 481213 | 6 | 2 | C10589 | LTL | N30 | B11 | E | EA | OEM | 01 | 2022-02-02 | 2022-05-26 | AC-2561-05 | 32 | 166.35 | 5323.2 | O
M1-02 | 30 | SO | 483686 | 7 | 1 | C10940 | CUST PU | N60 | B07 | D | EA | OEM | 05 | 2022-03-24 | 2022-05-30 | AC-2146-05 | 80 | 44.72 | 3577.6 | O
M1-02 | 30 | SO | 484639 | 4 | 2 | C10501 | BEST WAY | N30 | B07 | B | EA | AERO | 02 | 2021-07-12 | 2021-10-03 | AC-5088-05 | 37 | 170.07 | 6292.59 | O
M1-02 | 20 | SO | 482229 | 1 | 0 | C10973 | FDX 2D | N45 | B22 | D | EA | MRO | 02 | 2022-03-26 | 2022-05-25 | AC-3382-02 | 8 | 85.99 | 687.92 | O
M1-02 | 20 | SO | 480804 | 5 | 0 | C10305 | CUST PU | 2%10N30 | B14 | C | EA | AERO | 05 | 2022-03-12 | 2022-04-21 | AC-3293-01 | 96 | 103.12 | 9899.52 | O
M1-02 | 30 | BL | 484248 | 4 | 1 | C10321 | FDX 2D | N60 | B14 | B | EA | MRO | 01 | 2022-01-24 | 2022-05-24 | AC-5088-05 | 43 | 106.01 | 4558.43 | O
M1-02 | 30 | SO | 480226 | 9 | 0 | C10806 | LTL | N45 | B14 | D | EA | DEF | 05 | 2022-01-13 | 2022-03-22 | AC-4241-02 | 80 | 86.39 | 6911.2 | O
M1-02 | 20 | SO | 484583 | 4 | 0 | C10385 | CUST PU | N60 | B14 | B | EA | DEF | 02 | 2022-02-27 | 2022-05-23 | AC-4014-01 | 89 | 112.52 | 10014.28 | O
M1-02 | 30 | BL | 485782 | 5 | 2 | C10238 | LTL | 2%10N30 | B07 | A | EA | AERO | 02 | 2022-03-27 | 2022-06-06 | AC-4029-A | 16 | 151.78 | 2428.48 | O
M1-02 | 20 | SO | 487964 | 4 | 1 | C10940 | CUST PU | 2%10N30 | B14 | A | EA | MRO | 01 | 2022-02-18 | 2022-06-07 | AC-3755-02 | 40 | 68.75 | 2750 | P
M1-02 | 30 | BL | 489165 | 7 | 1 | C10966 | BEST WAY | N30 | B22 | C | EA | DEF | 02 | 2022-01-09 | 2022-05-23 | AC-1960-B | 34 | 120.58 | 4099.72 | P
M1-02 | 30 | SO | 487618 | 7 | 2 | C10695 | UPS GND | 2%10N30 | B22 | E | EA | DEF | 01 | 2021-03-07 | 2021-06-05 | AC-5486-03 | 45 | 154.7 | 6961.5 | P
M1-02 | 20 | BL | 487757 | 10 | 1 | C10273 | BEST WAY | N60 | B07 | C | EA | OEM | 05 | 2021-07-07 | 2021-10-11 | AC-2092-01 | 17 | 139.47 | 2370.99 | P
M1-02 | 20 | BL | 481964 | 3 | 2 | C10966 | UPS GND | N60 | B14 | C | EA | OEM | 05 | 2021-12-25 | 2022-05-10 | AC-7720-10 | 50 | 134.96 | 6748 | O
M1-02 | 20 | SO | 481739 | 6 | 0 | C10170 | BEST WAY | N45 | B22 | A | EA | OEM | 02 | 2021-12-20 | 2022-04-24 | AC-6273-05 | 39 | 103.1 | 4020.9 | O
M1-02 | 30 | SO | 486946 | 5 | 0 | C10251 | LTL | N45 | B11 | D | EA | MRO | 05 | 2022-02-26 | 2022-04-15 | AC-8083-03 | 22 | 174.97 | 3849.34 | O
M1-02 | 20 | SO | 480509 | 6 | 3 | C10273 | BEST WAY | N60 | B14 | D | EA | OEM | 01 | 2022-02-27 | 2022-05-13 | AC-2072-03 | 49 | 133.91 | 6561.59 | O
M1-02 | 20 | SO | 483479 | 3 | 1 | C10461 | UPS GND | 2%10N30 | B22 | E | EA | MRO | 02 | 2022-03-16 | 2022-04-21 | AC-4792-03 | 71 | 161.61 | 11474.31 | O
M1-02 | 20 | SO | 483191 | 12 | 3 | C10281 | BEST WAY | N45 | B14 | B | EA | AERO | 02 | 2022-03-22 | 2022-05-29 | AC-1480-01 | 97 | 111.77 | 10841.69 | O
M1-02 | 30 | SO | 483870 | 7 | 2 | C10706 | LTL | N60 | B22 | C | EA | MRO | 02 | 2022-02-06 | 2022-06-10 | AC-8361-10 | 82 | 112.53 | 9227.46 | O
M1-02 | 30 | SO | 486515 | 1 | 3 | C10852 | FDX 2D | N60 | B14 | NC | EA | DEF | 02 | 2022-02-24 | 2022-04-09 | AC-9159-A | 74 | 151.95 | 11244.3 | O
M1-02 | 20 | SO | 482459 | 12 | 3 | C10817 | BEST WAY | N60 | B14 | E | EA | OEM | 02 | 2022-01-12 | 2022-04-25 | AC-6433-A | 17 | 102.14 | 1736.38 | O
M1-02 | 30 | SO | 486770 | 6 | 0 | C10186 | CUST PU | N60 | B22 | C | EA | AERO | 01 | 2021-10-11 | 2022-02-25 | AC-4208-A | 26 | 61.33 | 1594.58 | O
M1-02 | 20 | SO | 486379 | 8 | 2 | C10211 | UPS GND | N60 | B11 | C | EA | AERO | 01 | 2022-03-21 | 2022-06-08 | AC-2924-03 | 92 | 92.54 | 8513.68 | O
M1-02 | 30 | SO | 482047 | 4 | 2 | C10455 | LTL | N30 | B11 | B | EA | AERO | 05 | 2021-12-05 | 2022-02-11 | AC-9858-01 | 74 | 55.32 | 4093.68 | O
M1-02 | 30 | SO | 488447 | 5 | 2 | C10951 | BEST WAY | N30 | B11 | B | EA | AERO | 02 | 2021-06-10 | 2021-09-02 | AC-6549-A | 33 | 109.84 | 3624.72 | P
M1-02 | 30 | SO | 481383 | 10 | 0 | C10350 | BEST WAY | N30 | B07 | C | EA | MRO | 01 | 2022-03-04 | 2022-04-03 | AC-9218-05 | 66 | 122.79 | 8104.14 | O
M1-02 | 30 | SO | 489216 | 6 | 0 | C10249 | BEST WAY | N45 | B14 | A | EA | MRO | 01 | 2022-02-03 | 2022-05-11 | AC-2135-A | 9 | 69.52 | 625.68 | P
M1-02 | 20 | BL | 487303 | 7 | 0 | C10331 | LTL | N60 | B07 | A | EA | MRO | 01 | 2021-12-28 | 2022-03-17 | AC-5249-10 | 40 | 173.31 | 6932.4 | O
M1-02 | 30 | SO | 483888 | 6 | 0 | C10377 | UPS GND | N30 | B14 | A | EA | DEF | 05 | 2022-03-09 | 2022-04-26 | AC-3142-05 | 72 | 102.92 | 7410.24 | O
M1-02 | 20 | SO | 488744 | 9 | 3 | C10951 | BEST WAY | N30 | B11 | B | EA | AERO | 02 | 2021-03-26 | 2021-07-03 | AC-9084-10 | 26 | 161.47 | 4198.22 | P
M1-02 | 30 | SO | 484108 | 10 | 3 | C10589 | FDX 2D | N60 | B22 | NC | EA | DEF | 01 | 2022-01-23 | 2022-03-24 | AC-1843-10 | 82 | 55.89 | 4582.98 | O
M1-02 | 20 | SO | 488782 | 5 | 2 | C10238 | BEST WAY | N30 | B22 | NC | EA | OEM | 05 | 2021-12-04 | 2022-03-21 | AC-4082-10 | 27 | 59.18 | 1597.86 | P
M1-02 | 30 | SO | 481328 | 9 | 3 | C10252 | UPS GND | 2%10N30 | B11 | E | EA | AERO | 02 | 2022-03-03 | 2022-05-08 | AC-7955-10 | 66 | 79.48 | 5245.68 | O
M1-02 | 30 | SO | 480938 | 8 | 0 | C10589 | BEST WAY | N30 | B14 | A | EA | AERO | 02 | 2022-01-29 | 2022-06-08 | AC-7720-10 | 76 | 89.98 | 6838.48 | O
M1-02 | 30 | SO | 489174 | 5 | 0 | C10706 | BEST WAY | N45 | B22 | D | EA | MRO | 05 | 2022-02-01 | 2022-05-04 | AC-3285-10 | 2 | 27.23 | 54.46 | P
M1-02 | 30 | SO | 482246 | 6 | 0 | C10316 | BEST WAY | N45 | B22 | E | EA | OEM | 02 | 2022-01-26 | 2022-03-27 | AC-8579-10 | 35 | 78.93 | 2762.55 | O
M1-02 | 20 | SO | 487978 | 1 | 0 | C10706 | LTL | N45 | B14 | C | EA | AERO | 05 | 2022-02-21 | 2022-04-13 | AC-7375-B | 16 | 70.74 | 1131.84 | P
M1-02 | 20 | SO | 485872 | 5 | 3 | C10461 | LTL | N45 | B07 | B | EA | AERO | 01 | 2021-10-14 | 2022-02-18 | AC-3239-01 | 96 | 96.5 | 9264 | O
M1-02 | 30 | SO | 486066 | 2 | 1 | C10519 | FDX 2D | N30 | B07 | E | EA | AERO | 01 | 2022-01-28 | 2022-06-09 | AC-6689-03 | 95 | 109.6 | 10412 | O
M1-02 | 30 | SO | 485037 | 11 | 1 | C10966 | CUST PU | 2%10N30 | B14 | C | EA | AERO | 01 | 2022-01-09 | 2022-05-20 | AC-3944-B | 10 | 139.43 | 1394.3 | O
M1-02 | 30 | SO | 486370 | 2 | 0 | C10589 | FDX 2D | N30 | B14 | B | EA | AERO | 01 | 2021-09-02 | 2021-11-26 | AC-7483-02 | 81 | 44.96 | 3641.76 | O
M1-02 | 20 | SO | 488023 | 11 | 2 | C10350 | CUST PU | N60 | B22 | D | EA | MRO | 05 | 2021-08-31 | 2021-12-24 | AC-9688-B | 28 | 155.42 | 4351.76 | P
M1-02 | 20 | SO | 482545 | 12 | 2 | C10786 | FDX 2D | 2%10N30 | B11 | E | EA | AERO | 05 | 2022-03-07 | 2022-05-26 | AC-9740-01 | 63 | 62.74 | 3952.62 | O
M1-02 | 20 | SO | 486860 | 5 | 0 | C10824 | FDX 2D | 2%10N30 | B22 | NC | EA | MRO | 01 | 2022-04-03 | 2022-05-12 | AC-8540-01 | 81 | 150.08 | 12156.48 | O

## Do Not Make List
Item Number | Hold Reason | Hold Date | Release Needed From
AC-1084-B | Engineering Hold - Material Deviation | 2021-10-26 | Quality Engineering
AC-1293-A | Engineering Hold - Material Deviation | 2022-03-14 | Product Engineering
AC-1448-02 | Engineering Hold - Drawing Rev Pending | 2022-03-20 | Customer
AC-1514-10 | Engineering Hold - NCR Open | 2021-07-19 | Product Engineering
AC-1570-02 | Engineering Hold - Drawing Rev Pending | 2022-04-12 | Customer
AC-1599-03 | Engineering Hold - Customer Spec Change | 2022-01-14 | Customer
AC-1601-05 | Engineering Hold - NCR Open | 2021-06-27 | Quality Engineering
AC-1648-A | Engineering Hold - First Article Rejected | 2022-02-28 | Product Engineering
AC-1883-02 | Engineering Hold - NCR Open | 2021-09-05 | Customer
AC-1894-02 | Engineering Hold - Drawing Rev Pending | 2021-10-09 | Product Engineering
AC-2063-10 | Engineering Hold - NCR Open | 2021-08-20 | Quality Engineering
AC-2081-A | Engineering Hold - First Article Rejected | 2022-02-20 | Quality Engineering
AC-2092-01 | Engineering Hold - First Article Rejected | 2022-02-26 | Product Engineering
AC-2133-01 | Engineering Hold - NCR Open | 2021-11-09 | Customer
AC-2274-A | Engineering Hold - Drawing Rev Pending | 2021-05-26 | Product Engineering
AC-2334-02 | Engineering Hold - Customer Spec Change | 2021-09-08 | Customer
AC-2349-05 | Engineering Hold - Drawing Rev Pending | 2022-04-24 | Customer
AC-2363-03 | Engineering Hold - Material Deviation | 2022-03-15 | Product Engineering
AC-2364-01 | Engineering Hold - First Article Rejected | 2022-05-08 | Customer
AC-2371-A | Engineering Hold - NCR Open | 2022-02-20 | Quality Engineering
AC-2415-B | Engineering Hold - NCR Open | 2022-03-06 | Quality Engineering
AC-2569-02 | Engineering Hold - Material Deviation | 2021-11-21 | Customer
AC-2651-03 | Engineering Hold - First Article Rejected | 2021-07-28 | Quality Engineering
AC-2723-03 | Engineering Hold - First Article Rejected | 2022-05-07 | Quality Engineering
AC-2790-10 | Engineering Hold - Material Deviation | 2021-12-29 | Customer
AC-2827-02 | Engineering Hold - Drawing Rev Pending | 2021-11-22 | Quality Engineering
AC-2849-B | Engineering Hold - Customer Spec Change | 2022-04-16 | Customer
AC-2870-A | Engineering Hold - First Article Rejected | 2021-09-02 | Quality Engineering
AC-2960-10 | Engineering Hold - First Article Rejected | 2022-05-05 | Product Engineering
AC-2967-A | Engineering Hold - Material Deviation | 2021-06-15 | Customer
AC-3047-05 | Engineering Hold - NCR Open | 2022-03-04 | Product Engineering
AC-3053-03 | Engineering Hold - Material Deviation | 2022-04-30 | Customer
AC-3060-02 | Engineering Hold - NCR Open | 2021-08-12 | Product Engineering
AC-3103-B | Engineering Hold - Customer Spec Change | 2021-09-10 | Quality Engineering
AC-3141-10 | Engineering Hold - Drawing Rev Pending | 2021-11-19 | Quality Engineering
AC-3151-05 | Engineering Hold - Drawing Rev Pending | 2021-05-21 | Customer
AC-3231-10 | Engineering Hold - Material Deviation | 2022-03-09 | Product Engineering
AC-3257-03 | Engineering Hold - Customer Spec Change | 2021-11-02 | Customer
AC-3287-02 | Engineering Hold - Drawing Rev Pending | 2021-12-01 | Product Engineering
AC-3359-A | Engineering Hold - First Article Rejected | 2021-09-24 | Quality Engineering
AC-3396-01 | Engineering Hold - Material Deviation | 2021-09-29 | Product Engineering
AC-3471-10 | Engineering Hold - NCR Open | 2021-09-17 | Quality Engineering
AC-3665-03 | Engineering Hold - Drawing Rev Pending | 2021-05-16 | Quality Engineering
AC-3675-B | Engineering Hold - Material Deviation | 2022-03-14 | Customer
AC-3696-02 | Engineering Hold - NCR Open | 2021-09-11 | Customer
AC-3755-02 | Engineering Hold - Material Deviation | 2022-03-30 | Product Engineering
AC-3912-03 | Engineering Hold - Customer Spec Change | 2021-08-09 | Quality Engineering
AC-3929-10 | Engineering Hold - First Article Rejected | 2022-04-18 | Product Engineering
AC-4082-10 | Engineering Hold - Material Deviation | 2021-06-23 | Quality Engineering
AC-4215-05 | Engineering Hold - NCR Open | 2021-07-12 | Product Engineering
AC-4250-A | Engineering Hold - NCR Open | 2021-11-22 | Product Engineering
AC-4386-01 | Engineering Hold - Customer Spec Change | 2022-01-07 | Product Engineering
AC-4597-10 | Engineering Hold - Material Deviation | 2021-06-19 | Quality Engineering
AC-4607-A | Engineering Hold - Customer Spec Change | 2021-12-26 | Product Engineering
AC-4645-05 | Engineering Hold - Material Deviation | 2022-03-19 | Quality Engineering
AC-4690-10 | Engineering Hold - NCR Open | 2021-11-17 | Quality Engineering
AC-4792-10 | Engineering Hold - Material Deviation | 2022-04-27 | Quality Engineering
AC-4825-B | Engineering Hold - Customer Spec Change | 2021-09-17 | Customer
AC-4873-10 | Engineering Hold - Material Deviation | 2022-03-14 | Quality Engineering
AC-4938-10 | Engineering Hold - Material Deviation | 2021-12-21 | Quality Engineering
AC-4980-01 | Engineering Hold - NCR Open | 2022-02-23 | Customer
AC-5066-03 | Engineering Hold - Customer Spec Change | 2021-05-26 | Product Engineering
AC-5069-03 | Engineering Hold - NCR Open | 2021-06-08 | Customer
AC-5085-05 | Engineering Hold - Material Deviation | 2022-05-10 | Product Engineering
AC-5486-03 | Engineering Hold - Customer Spec Change | 2021-05-20 | Product Engineering
AC-5597-01 | Engineering Hold - First Article Rejected | 2022-04-29 | Customer
AC-5713-01 | Engineering Hold - First Article Rejected | 2022-02-06 | Quality Engineering
AC-5901-A | Engineering Hold - Material Deviation | 2022-03-03 | Product Engineering
AC-6019-B | Engineering Hold - First Article Rejected | 2022-03-29 | Quality Engineering
AC-6102-10 | Engineering Hold - NCR Open | 2022-02-24 | Quality Engineering
AC-6271-03 | Engineering Hold - First Article Rejected | 2021-08-14 | Customer
AC-6493-05 | Engineering Hold - Drawing Rev Pending | 2022-01-02 | Product Engineering
AC-6549-A | Engineering Hold - Customer Spec Change | 2021-06-16 | Product Engineering
AC-6702-02 | Engineering Hold - Customer Spec Change | 2022-02-17 | Customer
AC-6792-B | Engineering Hold - Customer Spec Change | 2021-06-27 | Quality Engineering
AC-6827-05 | Engineering Hold - Drawing Rev Pending | 2022-02-20 | Quality Engineering
AC-6861-01 | Engineering Hold - NCR Open | 2021-10-30 | Product Engineering
AC-7019-10 | Engineering Hold - Customer Spec Change | 2021-08-30 | Product Engineering
AC-7062-10 | Engineering Hold - Material Deviation | 2021-12-05 | Customer
AC-7108-10 | Engineering Hold - Drawing Rev Pending | 2021-12-21 | Product Engineering
AC-7167-A | Engineering Hold - Material Deviation | 2022-05-07 | Customer
AC-7176-02 | Engineering Hold - First Article Rejected | 2021-08-31 | Customer
AC-7219-A | Engineering Hold - Drawing Rev Pending | 2021-10-02 | Customer
AC-7338-02 | Engineering Hold - Customer Spec Change | 2021-12-08 | Quality Engineering
AC-7375-B | Engineering Hold - Drawing Rev Pending | 2021-11-04 | Product Engineering
AC-7397-01 | Engineering Hold - NCR Open | 2021-12-23 | Quality Engineering
AC-7457-B | Engineering Hold - First Article Rejected | 2021-06-20 | Customer
AC-7555-03 | Engineering Hold - Material Deviation | 2022-05-20 | Customer
AC-7572-B | Engineering Hold - NCR Open | 2022-01-11 | Product Engineering
AC-7582-02 | Engineering Hold - Drawing Rev Pending | 2022-05-02 | Customer
AC-7794-A | Engineering Hold - Material Deviation | 2021-11-05 | Customer
AC-7879-05 | Engineering Hold - Material Deviation | 2021-08-10 | Customer
AC-8035-02 | Engineering Hold - NCR Open | 2021-10-16 | Product Engineering
AC-8194-03 | Engineering Hold - First Article Rejected | 2021-06-24 | Quality Engineering
AC-8328-B | Engineering Hold - Material Deviation | 2021-05-08 | Quality Engineering
AC-8440-03 | Engineering Hold - Customer Spec Change | 2021-05-11 | Quality Engineering
AC-8498-A | Engineering Hold - Customer Spec Change | 2022-04-18 | Customer
AC-8508-03 | Engineering Hold - NCR Open | 2021-06-02 | Customer
AC-8535-05 | Engineering Hold - Material Deviation | 2021-11-20 | Customer
AC-8665-02 | Engineering Hold - First Article Rejected | 2022-02-28 | Product Engineering
AC-8814-03 | Engineering Hold - Customer Spec Change | 2022-04-01 | Customer
AC-8827-A | Engineering Hold - Drawing Rev Pending | 2021-06-13 | Quality Engineering
AC-8989-01 | Engineering Hold - NCR Open | 2021-06-15 | Quality Engineering
AC-8994-B | Engineering Hold - Drawing Rev Pending | 2021-06-08 | Customer
AC-9001-05 | Engineering Hold - Drawing Rev Pending | 2021-09-24 | Quality Engineering
AC-9025-05 | Engineering Hold - Customer Spec Change | 2021-12-16 | Product Engineering
AC-9084-10 | Engineering Hold - Material Deviation | 2021-08-05 | Product Engineering
AC-9141-03 | Engineering Hold - Material Deviation | 2021-12-20 | Quality Engineering
AC-9206-05 | Engineering Hold - Drawing Rev Pending | 2022-03-08 | Product Engineering
AC-9246-03 | Engineering Hold - First Article Rejected | 2021-11-04 | Customer
AC-9290-02 | Engineering Hold - Customer Spec Change | 2021-07-13 | Product Engineering
AC-9332-01 | Engineering Hold - NCR Open | 2022-02-09 | Product Engineering
AC-9448-05 | Engineering Hold - Drawing Rev Pending | 2022-03-22 | Customer
AC-9453-B | Engineering Hold - Customer Spec Change | 2022-02-13 | Quality Engineering
AC-9688-B | Engineering Hold - Material Deviation | 2022-04-16 | Customer

## Credit Hold List
Cust # | Hold Reason | Hold Date
C10305 | Over Credit Limit | 2022-03-20
C10249 | Over Credit Limit | 2022-04-29
C10758 | Over Credit Limit | 2022-03-17
C10756 | Over Credit Limit | 2022-04-07